## Sheet1
County | Rte | ADT | Location | Miles | Rating | Work Class | Work Type/(Bridge #) | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | Beyond
Buena Vista | 003 | 1660 | DRAINAGE DITCH, 3.3 MI E OF US | 0 | 66 | Rebuild | Bridge Replacement (016230) | 2018: 800
71
Buena Vista | 003 | 1660 | RACCOON RIVER, 2.5 MI E OF US | 0 | 69 | Rebuild | Bridge Replacement (016220) | 2018: 1200
71
Buena Vista | 071 | 4970 | S JCT IA 7 TO IA 3 | 9.8 | 0 | Modernize | Pavement Widening | 2014: 1996
Calhoun | 004 | 3580 | SCL OF POMEROY TO 0.2 MI N OF | 3.4 |  | Preserve | Pavement Rehab/Widen | 2014: 1700
N JCT IA 7
Calhoun | 175 | 1940 | E OF LOHRVILLE | 0 |  | Rebuild | Right of Way | 2014: 15
[7 empty] | Culvert Replacement | 2015: 50
Carroll | 141 | 1900 | STREAM, 6.6 MI E OF CO RD N33 | 0 | 28 | Rebuild | Bridge Replacement (017310) | 2014: 652
Carroll | 141 | 1400 | DEDHAM CREEK, 0.4 MI W OF CO R | 0 | 57 | Rebuild | Bridge Replacement (017290) | 2015: 718
|  |  | D N33 |  |  |  | Right of Way | 2015: 15
Carroll | 141 | 1840 | EAST NISHNABOTNA RIVER, 0.5 MI | 0 | 75 | Preserve | Bridge Deck Overlay (017280) | 2015: 192
W OF US 71
Cherokee | 003 | 2320 | CLEGHORN TO 0.3 MI E OF US 59 | 9 | 0 | Preserve | Pavement Rehab | 2014: 5953
Cherokee | 031 | 1480 | FOUR MILE CREEK, 1.1 MI S OF C | 0 | 70 | Rebuild | Bridge Replacement (019510) | 2015: 642
O RD L51
Clay | 018 | 3080 | OCHEYEDAN RIVER, 2.3 MI W OF C | 0 | 18 | Rebuild | Right of Way | 2014: 15
|  |  | O RD M27 |  |  |  | Bridge Replacement (020300) | 2017: 1150
Clay | 018 | 2800 | O'BRIEN CO TO N JCT US 71 | 12.1 | 0 | Modernize | Pavement Widening | 2014: 2950
Crawford | 030 | 3120 | DITCH, 0.5 MI N OF IA 37 | 0 | 84 | Rebuild | Bridge Replacement (021200) | 2014: 481
Crawford | 030 | 3650 | WILLOW CREEK, 1.4 MI E OF ARIO | 0 | 63 | Preserve | Bridge Deck Overlay (021290) | 2014: 432
N
Dickinson | 009 | 4500 | E JCT US 71 TO 0.5 MI E OF W J | 6.9 | 0 | Preserve | Pavement Rehab | 2014: 2560
CT CO RD N25 (STATE SHARE)
Dickinson | 071 | 5200 | SPIRIT LAKE TO E JCT IA 9 | 4.5 | 0 | Preserve | Pavement Rehab | 2014: 1906
Dickinson | 086 | 1920 | IA 9 TO JUST N OF MINNESOTA | 4.9 | 21 | Rebuild | Erosion Control | 2014: 400
Emmet | 004 | 1980 | DITCH, 2.5 MI N OF CO RD B14 | 0 | 65 | Rebuild | Right of Way | 2014: 15
[7 empty] | Bridge Replacement (024260) | 2015: 1151
Emmet | 004 | 1980 | DITCH, 1.6 MI N OF CO RD B14 | 0 | 49 | Rebuild | Right of Way | 2014: 15
[7 empty] | Bridge Replacement (024250) | 2015: 720
Ida | 031 | 850 | STREAM, 5.3 MI N OF IA 20 | 0 | 100 | Preserve | Bridge Deck Overlay (029171) | 2015: 172
Ida | 059 | 1740 | SILVER CREEK, 1.1 MI N OF CO R | 0 | 86 | Preserve | Bridge Deck Overlay (029150) | 2018: 200
D D15
Ida | 059 | 1740 | SILVER CREEK, 2.1 MI N OF CO R | 0 | 87 | Preserve | Bridge Deck Overlay (029160) | 2018: 200
D D15
Ida | 175 | 2265 | IN BATTLE CREEK, FROM WALNUT S | 0.4 | 67 | Rebuild | Grade and Pave | 2014: 1750
|  |  | T TO CHESTNUT ST |  |  |  | Right of Way | 2014: 10
Lyon | 009 | 3650 | MOON CREEK, 0.5 MI E OF W JCT | 0 | 74 | Preserve | Bridge Deck Overlay (034535) | 2015: 308
US 75
Lyon | 009 | 4610 | ROCK RIVER, 0.5 MI E OF E JCT | 0 | 86 | Preserve | Bridge Deck Overlay (034645) | 2015: 574
US 75
Lyon | 009 | 3080 | MUD CREEK, 0.1 MI W OF CO RD K | 0 | 99 | Preserve | Bridge Deck Overlay (034601) | 2017: 240
30
Monona | 029 | 13400 | CO RD K42 OVER I-29, 1.7 MI N | 0 | 56 | Preserve | Bridge Deck Overlay (037310) | 2015: 431
OF IA 175
Monona | 029 | 12700 | ABANDONED RR, 5.1 MI N OF CO R | 0 | 97 | Preserve | Bridge Deck Overlay (028410) | 2016: 348
D F20 (NB)
Monona | 029 | 12700 | ABANDONED RR, 5.1 MI N OF CO R | 0 | 96 | Preserve | Bridge Deck Overlay (028420) | 2016: 348
D F20 (SB)
Monona | 141 | 2110 | SIMMONS CREEK, 0.8 MI W OF IA | 0 | 44 | Rebuild | Bridge Replacement (036740) | 2014: 2558
175
Monona | 175 | 1600 | MISSOURI RIVER E OF DECATUR, N | 0 | 15 | Preserve | Bridge Cleaning (036810) |  |  | 22 | 22 | 22 | 22
|  |  | E (STATE SHARE) |  |  |  | Bridge Painting (036810) | 2015: 2723
Monona | 183 | 660 | STREAM, 3.1 MI S OF CO RD E54 | 0 | 52 | Rebuild | Right of Way | 2014: 15
[7 empty] | Bridge Replacement (037130) | 2015: 1354
O'Brien | 010 | 1660 | MILL CREEK, 2.5 MI W OF W JCT | 0 | 99 | Preserve | Bridge Deck Overlay (038360) | 2018: 350
US 59
O'Brien | 018 | 4140 | LITTLE FLOYD RIVER, 0.1 MI W O | 0 | 42 | Preserve | Bridge Deck Overlay (038230) | 2018: 200
F E JCT CO RD L40
Palo Alto | 004 | 2040 | DRAINAGE DITCH, 5.2 MI N OF N | 8 | 61 | Preserve | Bridge Replacement (039240) | 2018: 625
JCT US 18
Plymouth | 003 | 1390 | DITCH, 2.6 MI W OF CO RD K42 | 0 | 41 | Rebuild | Right of Way | 2016: 15
[7 empty] | Bridge Replacement (039800) | 2016: 488
Plymouth | 075 | 12500 | DRY CREEK, 3.4 MI N OF CO RD C | 0 | 59 | Preserve | Bridge Deck Overlay (039550) | 2017: 250
60 (SB)
Plymouth | 075 | 13800 | DITCH, 1.0 MI N OF CO RD C60 ( | 0 | 62 | Preserve | Bridge Replacement (039410) | 2014: 165
SB)
Plymouth | 075 | 13800 | DITCH, 1.0 MI N OF CO RD C60 ( | 0 | 86 | Preserve | Ditch Improvement | 2014: 80
|  |  | NB) |  |  |  | Bridge Replacement (039400) | 2014: 165
Pocahontas | 003 | 2550 | LIZZARD CREEK, 0.3 MI W OF IA | 0 | 45 | Rebuild | Bridge Replacement (040100) | 2018: 800
4
Sac | 071 | 2220 | BOYER RIVER, 0.7 MI S OF N JCT | 0 | 85 | Preserve | Bridge Deck Overlay (046660) | 2017: 290
IA 175
Sac | 071 | 2200 | E JCT IA 175 TO W JCT IA 175 | 17 | 0 | Preserve | Pavement Rehab | 2014: 1100
Sac | 071 | 3390 | S OF SCL OF EARLY TO S JCT IA | 10.2 | 0 | Modernize | Pavement Widening | 2014: 1782
7
Sac | 196 | 1040 | RACCOON RIVER, 1.1 MI N OF US | 0 | 49 | Rebuild | Wetland Mitigation | 2015: 150
|  |  | 71 |  |  |  | Bridge Replacement (046750) | 2015: 3106
Sac | 196 | 1040 | CEDAR CREEK, 0.2 MI S OF CO RD | 0 | 47 | Rebuild | Bridge Replacement (046730) | 2015: 2185
|  |  | D36 |  |  |  | Wetland Mitigation | 2015: 100
Sac | 196 | 740 | US 71 TO CO RD D36 | 7.8 | 0 | Rebuild | Right of Way | 2014: 1000
[7 empty] | Grade and Pave | 2015: 18270
Sioux | 010 | 3070 | DRY CREEK, 0.9 MI E OF IA 12 | 0 | 94 | Preserve | Bridge Deck Overlay (048481) | 2015: 363
Sioux | 075 | 3200 | WEST FORK FLOYD RIVER, 2.8 MI | 0 | 98 | Preserve | Bridge Deck Overlay (048370) | 2014: 173
S OF CO RD B58
Sioux | 075 | 3200 | WEST FORK FLOYD RIVER, 2.3 MI | 0 | 91 | Preserve | Bridge Deck Overlay (048380) | 2014: 177
S OF CO RD B58
Woodbury | 012 | 9700 | IN SIOUX CITY, FROM US 20/75 T | 5.1 |  | Preserve | Right of Way | 2014: 125
O VIADUCT
Woodbury | 020 | 2240 | E OF MOVILLE TO W OF CORRECTIO | 12.5 | 54 | Construct | Wetland Mitigation | 2014: 120; 2015: 400
|  |  | NVILLE |  |  |  | Culvert New (X) | 2014: 2804; 2017: 2098
[7 empty] | Grading | 2014: 33169; 2017: 18351
[7 empty] | Bridge New (NEW) | 2014: 5524; 2017: 953
[7 empty] | Right of Way | 2014: 2500
[7 empty] | Traffic Signs | 2016: 50; 2018: 62
[7 empty] | Pave | 2016: 17959; 2018: 19611
Woodbury | 020 | 7100 | WEST FORK LITTLE SIOUX RIVER, | 0 | 65 | Rebuild | Right of Way | 2015: 15
|  |  | 0.1 MI W OF IA 140 (EB) |  |  |  | Bridge Replacement (052920) | 2018: 2088
Woodbury | 020 | 9100 | ELLIOT CREEK, 6.0 MI W OF IA 1 | 0 | 70 | Rebuild | Bridge Replacement (052890) | 2018: 2028
40 (EB)
Woodbury | 020 | 2240 | IN CORRECTIONVILLE | 0.7 | 0 | Rebuild | Right of Way | 2014: 600
[7 empty] | Grade and Pave | 2015: 10015
Woodbury | 029 | 1030 | CO RD D51 INTERCHANGE, 1.8 MI | 0.7 | 34 | Rebuild | Traffic Signs | 2014: 65
|  |  | N OF SALIX |  |  |  | Bridge Replacement (053660) | 2014: 2697
[7 empty] | Grade and Pave | 2014: 7336
[7 empty] | Lighting | 2014: 45
[7 empty] | Right of Way | 2014: 120
[7 empty] | Erosion Control | 2015: 150
Woodbury | 029 | 1080 | CO RD K25 INTERCHANGE (SALIX), | 0.3 | 63 | Rebuild | Right of Way | 2015: 800; 2016: 45
|  |  | 6.4 MI N OF IA 141 |  |  |  | Bridge Replacement (053650) | 2016: 5000
[7 empty] | Grade and Pave | 2016: 2207
[7 empty] | Traffic Signs | 2016: 65
Woodbury | 029 | 12700 | IA 141 OVER I-29 | 0 | 65 | Preserve | Bridge Deck Overlay (053230) | 2018: 300
Woodbury | 029 | 36000 | RECONSTRUCTION IN SIOUX CITY | 12 | 28 | Rebuild | Traffic Signs |  | 1568 | 1911 | 1712 | 1193 | 623
[7 empty] | Grade and Pave |  | 30456 | 29543 | 47546 | 31582 | 12546
[7 empty] | Bridge Replacement (053740) |  | 22336 | 21939 | 20945 | 11474 | 3097
[7 empty] | Erosion Control | 2014: 261; 2015: 273; 2016: 285
[7 empty] | Culvert Replacement | 2014: 57
[7 empty] | Right of Way | 2014: 2000
Woodbury | 077 | 31700 | MISSOURI RIVER IN SIOUX CITY ( | 0 | 79 | Preserve | Bridge Cleaning (052811) |  | 24 | 24 | 24 | 24 | 24
|  |  | STATE SHARE) |  |  |  | Bridge Painting (052811) | 2014: 750
Woodbury | 129 | 22700 | MISSOURI RIVER IN SIOUX CITY ( | 0 | 74 | Preserve | Bridge Cleaning (600765) |  | 28 | 28 | 28 | 28 | 28
|  |  | STATE SHARE) |  |  |  | Bridge Painting (600765) | 2015: 500
Woodbury | 141 | 1780 | WEST BRANCH LITTLE SIOUX, 0.8 | 0 | 42 | Preserve | Bridge Deck Overlay (053270) | 2017: 370
MI E OF CO RD K64
Woodbury | 141 | 1790 | GARRETSON DITCH, 6.4 MI E OF I | 0 | 61 | Preserve | Bridge Replacement (053250) | 2018: 920
-29
Woodbury | 376 | 8600 | FLOYD RIVER, 1.1 MI S OF CO RD | 0 | 58 | Preserve | Bridge Deck Overlay (053060) | 2014: 744
D12 IN SIOUX CITY
Woodbury | 376 | 6900 | RR & TAFT ST, 0.1 MI S OF CO R | 0 | 47 | Rebuild | Right of Way | 2014: 20
|  |  | D D12 IN SIOUX CITY (NB) |  |  |  | Bridge Replacement (053070) | 2016: 4678