## Slide 1: Utility program
Iowa Department of Transportation

## Slide 2: Administration & Coordination
Central Office
District offices
Field offices

## Slide 3: www.menti.com
Code 57 11 68

## Slide 4: Accommodation & Coordination

## Slide 5: Central Office – Right of Way Bureau
Program Administrator – Deanne Popp
Program Leader - Policy Administrator
Utility Reimbursement Agreements
Utility Reimbursements
Initiatives
UTILITY RELOCATION COORDINATOR – JEFF MCCOLLOGH
Accommodation Specialist
Project Scheduling
Project Plan Submittals

## Slide 6: Engineering Operations Technicians
Utility Accommodation Permit Review
Project Coordination Assistance
Utility Work Plan Review
Other permits

## Slide 13: District Utility Coordinators
District 1 – Jerry Lavine
District 2 – Tracy Meise
District 3 – Kelly Mulvihill
District 4 – Kurtis Shackelford
District 5 – Bonnie Clancy
District 6 – Steve Flockhart (FT DUC)
Project Coordination
Utility Work Plan Review
Utility Accommodation Permit Review
Utility Reimbursement Agreement Review

## Slide 15: Utility Accommodation and Coordination
Communication
is KEY
Annual 5-year Construction Program
Share with all Utilities
DOT Annual Meeting
Regular correspondence (written or verbal)
Local City Meetings Monthly, Bi-Monthly, Quarterly Meetings
Easy way to present information and get Utility input
Best coordinators know the utility contacts in their areas and communicate regularly

## Slide 16: Iowa Administrative Code 761-115 (306A)
Utility Accommodation (Utility Permits)
  Primary and Interstate Roads
Utility Adjustments for highway projects Chapter 115.25 - (Point 25 Projects)
  All projects except
    Accelerated schedules
    No anticipated utility adjustments

## Slide 17: Point25 Process (Overview)
IAC 761-115.25 = Point 25 Process
  Only for state highway improvement projects
  Requires multiple notifications and responses
  If all Notifications submittals are met:
    Non-responsive utility can be held liable for project delay damages
    Utility and Contractor settle directly
    State is provider of evidence
    State cannot take on liability of either party

## Slide 18: UTILITY EVENT OVERVIEW U Event (00)
Utility Research / Identification
Completed for All projects where utility conflicts are anticipated Prerequisites: Final Concept Completion
    Previous utility permits
    Previous utility Reimbursement agreements
    Field examinations (Concept Reviews)
    Existing utility maps
    Iowa One Call (Design Request)
      Identifies underground utilities with-in project limits

## Slide 19: UTILITY EVENT OVERVIEW U Event (02)
Project Notification to Utility Companies
  Required on all Point 25 Projects
    Prerequisites: Completed D02 (Field Exam Plans / General project layout Only / anticipated new ROW lines not determined, proposed new cross sections not available
    Request maps or plans from utility companies on existing facility locations (90 days to reply)
    Request notification if utility is currently located in private easement (Reimbursable Relocation Agreement)
    Goal is for the event to be early enough in the process to allow for modifications to the design to avoid major utility relocations ( HP gas, OH Electrical Transmission lines, major communication duct banks)

## Slide 20: UTILITY EVENT OVERVIEW U Event (03)
1st Project Plan Submittal to Utility Companies
  Required on all Point 25 Projects
  Prerequisites: Completed Preliminary Design (D05) and new proposed ROW layout (R01)
  Requires all impacted utilities to submit a relocation plan (90 days to reply)
  What is an acceptable relocation plan?
    Relocation must be shown on project plans and cross section sheets

## Slide 28: UTILITY EVENT OVERVIEW U Event (04)
2nd Project Plan Submittal to Utility Companies
  Required on all Point 25 Projects
  Prerequisites: Completed Design (D05) and ROW layout (R01)
  Requires all impacted utilities to resubmit their relocation plans if any project design changes occurred after the U03 submittal (60 days to reply)

## Slide 29: UTILITY EVENT OVERVIEW U Event (05)
Utility Reimbursement Agreement
  Handled through the ROW Bureau – Utilities Section
  Available when a private utility is NOT located with-in public ROW
  Utility owned is located private easement
  Prerequisites:
    Private easement documentation
    Proposed relocation plan shown on IADOT project plan sheets and cross sections
    Itemized relocation cost estimate

## Slide 30: UTILITY EVENT OVERVIEW U Event (06)
  Required on all Point 25 Projects
  Prerequisites:
    All New ROW purchases are completed or have a clearly defined possession date
    Final utility relocation work plan approval
    Reimbursement agreement executed (if applicable)
    Utility Accommodation Permit Issued by EOT
    If coordination with contractor is required then the notice to proceed may be contingent upon the contractors schedule

## Slide 31: UTILITY EVENT OVERVIEW U Event (07)
Utility Bid Attachment
  Required on all Point 25 Projects (Recommended for Non-Point 25 projects)
      Provides a verbal explanation of conflict locations and resolution
      Provides an anticipated start and completion date for each utility companies relocation
      Provides utility company contact name , phone #, email address
      UBA is sent to office of contracts prior to letting and is included in the project proposal bid documents
      UBA is for the use of the bidding contractors so they are aware of the utilities relocation plan and timeline, or if a particular utility has been non-responsive

## Slide 33: Questions?
Thank you!