## Slide 1: Utility Reimbursement Agreements
Iowa Department of Transportation

## Slide 2: Right of Way Bureau Utilities Section
Relocation of utility facility is necessary to accommodate construction
Is existing facility located on or off public right of way (ROW)?
On public ROW ~
  Relocate at utility company expense
On private easement ~
  Eligible for reimbursement
  Must provide evidence of easement(s)
  Establishes state’s authority to reimburse

## Slide 3: Prerequisites
Private easement documentation
Proposed relocation work plan
Itemized estimate of relocation costs

## Slide 4: Easement Documentation
Must cover the area where the facilities are currently located
Include the corresponding parcel number(s) from DOT plans for cross reference
Establishes state’s authority to reimburse

## Slide 5: Proposed Relocation Work Plan – EXHIBIT A
Show existing location of facilities
1
Show proposed location of facilities
2
Overlay on DOT plans and cross sections
3

## Slide 6: Detailed Estimate of Relocation Costs – EXHIBIT B
Segregate direct, indirect & “unallowable” costs
1
Cost Accounting Standards
Work Order System
2
Ability to accumulate costs to a project
3

## Slide 7: Direct Costs
Benefit one project and only one project
Include:
Materials, labor, equipment, etc.
Salaries & expenses
Engineering
Other services directly related to the project

## Slide 8: Overhead & Indirect Costs
Costs incurred to run a business
Include:
Eligible - must be actual costs incurred: administration, accounting fees, insurance, legal fees, some labor & salaries
Not eligible – advertising, sales promotion, interest on borrowings, contributions, donations, entertainment, fines, penalties, lobbying, research programs, first-class travel, 5-star hotels over the government per diem allowances

## Slide 9: Betterments
Necessitated by the requirements of the highway construction are reimbursable
At the election of the utility and NOT attributable to the highway project are NOT reimbursable
  Increased service capacity
  Service improvements
Can be an applied percentage to the estimate

## Slide 10: Necessitated by Construction
Economy (non-stocked items may be uneconomical to purchase)
Compliance with governmental laws & ordinances
Compliance with regulatory commission or codes
Replacements that are of equivalent standard although not identical
Required by current design practices regularly followed by the company in its own work and for which there is a direct benefit of the highway project, or required by the highway project.

## Slide 11: Salvage Credit
Salvage value of materials removed
Recovered from temporary use
Accepted for reuse by the utility

## Slide 12: Putting it all together
Item | Amount |  | Eligible Costs | 
Design | $75,000.00 |  | $57,692.31 | 
Materials | $250,000.00 |  | $192,307.69 | 
Labor | $500,000.00 |  | $384,615.38 | 
Subtotal | $825,000.00 |  | $634,615.38 | 
Indirect (allowable) | $165,000.00 |  | $126,923.08 | 
Indirect (unallowable) | $82,500.00 |  | $0.00 | 
Betterment (credit) | $15,000.00 |  | -$15,000.00 | 
Salvage (credit) | $5,000.00 |  | -$5,000.00 | 
Total | $1,092,500.00 |  | $741,538.46 | 
Length on Public ROW | 1,500 | ft | 23% | non-reimbursable
Length on Private Easement | 5,000 | ft | 77% | reimbursable
Total relocation length | 6,500 | ft | 100% | 
 | Contract Amount |  | $741,538.46 | 

## Slide 13: Scope of Work
Clear description of the work required
Size(s) of facility
Length of relocation
  On public ROW (at company expense)
  On private easement (eligible for reimbursement)
Tabulation of conflict points
  Crossings
  Poles
  Vaults
  Ducts

## Slide 14: Method for Performance
Competitive bidding (solicit bids from a contractor)
Force account (in-house labor)

## Slide 15: Agreement Document
Pre-Audit
Estimates over $50,000
DOT Auditors – Finance Office
Review detailed estimate – Cost Accounting Standards
Ability to segregate costs
Send for signature
Staff Action
Agreements over $50,000
DOT approval to enter into agreement with external party
DOT may then sign agreement
Fully executed agreement

## Slide 16: Change Orders
Minor changes necessary…
Must receive approval from DOT for more major changes
Costs will exceed 125% of the estimate ~ unless the increase is $10K or under
Request approval in writing to Central Office
Updated itemized cost estimate
Explanation of increased costs
Only reimburse additional cost if approved by DOT in writing

## Slide 17: Invoices
Expenses must be incurred prior to the date of the invoice
Progress payments allowed
Indicate Progress or Final on the Invoice

## Slide 18: Invoices – include the following:
Company name
Date of invoice
Agreement number
Project number (ROW preferred)
Beginning and ending date of work
Itemized statement of actual costs
Percent complete
Total claimed to date
Company project or activity numbers
If final, show “FINAL”
If progress, show “PROGRESS”
Total of all progress payments will not exceed 90% of agreement amount
Typically 10% retainage

## Slide 19: Final Payment
Final Audit
Submit all invoices & supporting documents for internal review
Determination whether charges are in line with estimates
Request repayment if company has been overpaid
Release retainage if all is in compliance
Certificate of Completion
Disclaimer of Interest in Realty
In exchange for reimbursement
Releases company’s interest in all real estate acquired for project where facility was originally located
Company retains any easement rights outside of ROW
Retainage
Form 517112
Fill out and submit to DUC
DUC reviews and signs if relocation is complete and acceptable
Pay the retainage to utility company, if any

## Slide 20: Form 517112
Certificate of Completion and Acknowledgement of Utility Work
Project information
Field completion date
Related to agreement - YES
Sign and date
Submit to DUC

## Slide 21: Questions?
UTILITY REIMBURSEMENT AGREEMENTS

## Slide 22: What’s next?
Consider the possibilities…

## Slide 23: Continued Automation
Improve processes
Electronic Permitting System
  Guided submittal of permit application
  Track the progress of the permits
  Incorporate communication & workflow
Utility Coordination Matrix
  Resolution and management of utility conflicts on projects
  Track the progress of DOT projects
  Track the progress of individual conflicts
  Incorporate communication & workflow

## Slide 24: Electronic Permitting System
Internal Testing
External approvals
Options for property owner as applicant (i.e. tile lines)
Timing & due dates
Maps
External Testing
By invitation

## Slide 25: Utility Conflict Matrix
Process Workflow
Who What When How
Testing
Small project
By invitation

## Slide 26: Traditional Utility Coordination
The 3 C’s of Utility Coordination
Communicate – share information about out projects (early & often)
Coordinate – timelines for plan submittals (Point25); DUCs in each DOT District
Cooperate – operational meetings, easement purchase, ROW acquisitions
The missing “C”
Commitment – timely information with due dates, relocation work plans with timelines for relocations

## Slide 27: What’s the goal?
Avoid and minimize utility impacts
Strategies
Conflict analysis
Design alternatives

## Slide 28: Paradigm Shift
Avoid – design around utilities
Minimize – lessen the impact – fewer relocations
Accommodate – utilities in the ROW
Mitigate – relocate out of ROW

## Slide 29: How do we design around?
Root of the issue…
Need accurate locations
MUST know what’s below – precise locations

## Slide 30: How do we know?
Lack of accurate and complete data
OneCall
SUE
Traditional potholing
SUE
New technologies
Lidar – georeferenced locations
3D modeling – accurate depictions
Better design solutions
Avoid/minimize impacts during a project

## Slide 31: What about after the project?
Or, the next project…
Maintain information
Enterprise technology
Partnerships
Align with resources

## Slide 32: GIS & As-Builts
Who’s where & what’s what
Database of information
Who, what, where
Retrievable for future use

## Slide 33: www.menti.com
Code 57 11 68

## Slide 34: What are your thoughts?
Do you see a benefit to having a shared GIS of utility locations?
What are obstacles?
Who are the partners?
Do you think it’s achievable?
Are you willing to be an advocate?
How can you help?

## Slide 35: Thank you…
Any questions?

## Slide 36: Open Discussion