## Five Year Program
2021 - 2025 Five Year Program
This information is valid for the date of Commission approval of 6/9/2020
PROJECT ESTIMATED COSTS X $1000
COUNTY | ROUTE | LOCATION | PSS PIN | PSS PROJECT NUMBER | TYPE OF WORK | 2021 | 2022 | 2023 | 2024 | 2025
Adair | 25 | Greenfield to I-80 |  |  | Pavement Rehab | 1350
|  | Greenfield to I-80 | 20-01-025-010 | STPN-025-3(35)--2J-01 | Microsurfacing | 1350
Adair | 25 | I-80 Interchange |  |  | Bridge Deck Overlay |  | 333
|  | I-80 Interchange | 17-01-025-010 | BRFN-025-3(34)--39-01 | Bridge Deck Overlay |  | 333
Adair | 80 | Cass Co to IA 25 (WB) |  |  | Pavement Rehab |  |  |  |  | 8977
|  | Cass Co to IA 25 (WB) | 15-01-080-010 | IMX-080-2(238)73--02-01 | HMA Resurfacing with Milling |  |  |  |  | 8977
Adair | 80 | IA 25 to Madison Co (EB) |  |  | Pavement Rehab |  | 2866
|  | IA 25 to Madison Co (EB) | 18-01-080-020 | IMN-080-2(256)86--0E-01 | HMA Resurfacing |  | 2866
Adair | 92 | Grand River 1.0 mi W of Co Rd P28 |  |  | Bridge Deck Overlay |  |  |  |  | 490
|  | Grand River 1.0 mi W of Co Rd P28 | 20-01-092-010 | BRFN-092-3(42)--39-01 | Bridge Deck Overlay |  |  |  |  | 490
Adair | 92 | W Fork Nodaway River 1.6 mi E of Co Rd N51 |  |  | Bridge Replacement |  |  |  | 1800
|  | W Fork Nodaway River 1.6 mi E of Co Rd N51 | 19-01-092-010 | BRF-092-3(40)--38-01 | Bridge-Unspecified |  |  |  | 1800
Adams | 148 | Middle Nodaway River 1.8 mi S of S Jct Co Rd H20 |  |  | Bridge Deck Overlay | 712
|  | Middle Nodaway River 1.8 mi S of S Jct Co Rd H20 | 16-02-148-010 | BRFN-148-2(17)--39-02 | Bridge Deck Overlay | 712
Audubon | 71 | Stream 1.1 mi N of Co Rd F65 |  |  | Bridge Replacement |  |  |  |  | 860
|  | Stream 1.1 mi N of Co Rd F65 | 20-05-071-010 | BRFN-071-4(55)--39-05 | Bridge-Unspecified |  |  |  |  | 860
Cass | 6 | East Nishnabotna River 2.6 mi E of IA 48 |  |  | Bridge Deck Overlay |  |  | 817
|  | East Nishnabotna River 2.6 mi E of IA 48 | 18-15-006-010 | BRFN-006-2(45)--39-15 | Bridge Deck Overlay |  |  | 817
Cass | 6 | Indian Creek 0.4 mi E of IA 48 |  |  | Bridge Deck Overlay |  | 460
|  | Indian Creek 0.4 mi E of IA 48 | 17-15-006-010 | BRFN-006-2(44)--39-15 | Bridge Deck Overlay |  | 460
Cass | 80 | 0.7 MI E OF IA 173 TO 0.7 MI W OF US 71 (EB & WB) |  |  | Pavement Planing |  | 2338
|  | 0.7 mi E of IA 173 to 0.7 mi W of US 71 (WB) and 0.7 mi W of US 71 to Adair Co (EB) | 16-15-080-050 | IMN-080-1(474)55--0E-15 | Pavement Planing/Grooving |  | 2338
Cass | 80 | 570th St 2.0 mi W of IA 173 (EB & WB) |  |  | Grade and Pave |  |  | 1500
|  | 570th St 2.0 mi W of IA 173 (EB & WB) | 18-15-080-020 | IMN-080-1(495)53--0E-15 | PCC Pavement - Grade and Replace |  |  | 1500
Cass | 80 | 770th St 1.9 mi E of IA 148 (EB & WB) |  |  | Bridge Rehabilitation |  |  |  | 3000
|  | 770th St 1.9 mi E of IA 148 Interchange (EB & WB) | 19-15-080-010 | IMN-080-2(257)72--0E-15 | Reconstruction - Bridge Deck Replacement |  |  |  | 3000
Cass | 80 | IA 148 Interchange |  |  | Bridge Rehabilitation |  |  |  |  | 1270
|  | IA 148 Interchange | 20-15-080-020 | IMN-080-2(258)67--0E-15 | Reconstruction - Bridge Deck Replacement |  |  |  |  | 1270
Cass | 80 | POTTAWATTAMIE CO TO 0.3 MI W OF CO RD G30 (VAR LOC) |  |  | Pavement Rehab |  |  |  |  | 3190
|  | Pottawattamie Co to 0.3 mi W of Co Rd G30 - Various Locations (EB/WB) | 20-15-080-030 | IMN-080-1(525)50--0E-15 | HMA Resurfacing with Milling |  |  |  |  | 3190
Cass | 80 | Pottawattamie Co to E of IA 173 (WB) |  |  | Pavement Rehab |  | 1401
|  | Pottawattamie Co to E of the IA 173 Interchange (WB) | 18-15-080-030 | IMN-080-1(508)50--0E-15 | HMA Resurfacing |  | 1401
Cass | 83 | East Nishnabotna River 1.1 mi W of W Jct US 6 |  |  | Bridge Deck Overlay |  | 431
|  | East Nichnabotna River 1.1 mi W of W Jct US 6 | 17-15-083-010 | BRFN-083-0(44)--39-15 | Bridge Deck Overlay |  | 431
Cass | 92 | Sevenmile Creek 1.7 mi W of W Jct US 71 |  |  | Bridge Replacement |  |  | 2528
|  | Sevenmile Creek 1.7 mi W of W Jct US 71 | 18-15-092-010 | BRF-092-2(44)--38-15 | Bridge-Unspecified |  |  | 2528
Dallas | 6 | S of 302nd Pl to Greenwood Hills Dr in Adel (state share) |  |  | Pavement Rehab/Widen |  | 1000
|  | S of 302nd Pl to Greenwood Hills Dr in Adel (state share) | 18-25-006-010 | NHSN-006-3(71)--2R-25 | HMA Pavement Widening/HMA Resurfacing |  | 1000
Dallas | 80 | Co Rd R16 to Co Rd R22/Ute Ave |  |  | Traffic Signs |  |  | 925
|  | Co Rd R16 to Co Rd R22/Ute Ave | 19-25-080-020 | ITS-080-3(254)113--25-25 | ITS Integration |  |  | 200
|  | Co Rd R16 to Co Rd R22/Ute Ave | 19-25-080-020 | ITS-080-3(255)113--25-25 | ITS Infrastructure |  |  | 650
|  | Co Rd R16 to Co Rd R22/Ute Ave | 19-25-080-020 | ITS-080-3(256)113--25-25 | ITS Equipment |  |  | 75
Dallas | 80 | S RACCOON RIVER AND N RACCOON RIVER E OF US 169 (EB & WB) |  |  | Bridge Rehabilitation | 500
|  | S Raccoon River 1.5 mi E of US 169 and N Raccoon River 2.3 mi E of US 169 (EB/WB) | 20-25-080-050 | IMN-080-3(295)112--0E-25 | Bridge Repair | 500
Dallas | 80 | US 6 / US 169 Interchange |  |  | Pavement Widen | 1137
|  | US 6 / US 169 Interchange | 18-25-080-010 | IMN-080-3(280)110--0E-25 | HMA Pavement Widening | 1137
[5 empty] | Traffic Signals | 523
|  | US 6 / US 169 Interchange | 18-25-080-010 | IMN-080-3(262)110--0E-25 | Traffic Signals | 523
Dallas | 80 | US 6/169 in De Soto to Co Rd R16 |  |  | Bridge Replacement |  | 11975 |  | 13171
|  | South Raccoon River 1.5 mi E of US 6/169 (EB & WB) | 17-25-080-020 | IM-080-3(222)112--13-25 | Bridge Replacement-PPCB |  | 5319
|  | Old Portland Rd 2.1 mi E of US 6/169 | 17-25-080-020 | IM-080-3(223)112--13-25 | Bridge Replacement-PPCB |  |  |  | 1684
|  | North Raccoon River 2.3 mi E of US 6/169 (EB & WB) | 17-25-080-020 | IM-080-3(224)112--13-25 | Bridge Replacement-PPCB |  | 6656
|  | South Raccoon River 1.5 mi E of US 6/169 (WB) | 17-25-080-020 | IM-080-3(241)112--13-25 | Bridge Replacement-PPCB |  |  |  | 5135
|  | North Raccoon River 2.3 mi E of US 6/169 (WB) | 17-25-080-020 | IM-080-3(242)112--13-25 | Bridge Replacement-PPCB |  |  |  | 6352
[5 empty] | Erosion Control |  |  |  |  | 239
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | IMN-080-3(225)110--0E-25 | Erosion Control |  |  |  |  | 239
[5 empty] | Grade and Pave |  |  |  | 10657
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | IM-080-3(239)110--13-25 | Unknown Pavement - Grade and New |  |  |  | 10657
[5 empty] | Grading |  | 5767
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | IM-080-3(219)110--13-25 | Grading |  | 5767
[5 empty] | Lighting |  |  |  | 75
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | IM-080-3(221)110--13-25 | Lighting |  |  |  | 75
[5 empty] | Paving |  |  | 9137
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | IM-080-3(238)110--13-25 | Unknown Pavement - New |  |  | 9137
[5 empty] | Right of Way |  | 50
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | IMN-080-3(226)110--0E-25 | Right Of Way |  | 50
[5 empty] | Traffic Signs |  |  | 250 | 1175
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | IM-080-3(220)110--13-25 | Traffic Signs |  |  | 250
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | IM-080-3(240)110--13-25 | Traffic Signs |  |  |  | 250
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | ITS-080-3(251)110--25-25 | ITS Integration |  |  |  | 200
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | ITS-080-3(252)110--25-25 | ITS Infrastructure |  |  |  | 650
|  | US 6/169 in De Soto to Co Rd R16 | 17-25-080-020 | ITS-080-3(253)110--25-25 | ITS Equipment |  |  |  | 75
Dallas | 80 | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy |  |  | Bridge Replacement |  |  | 1369 | 1860 | 1944
|  | UP RR 2.3 mi W of I-35 | 18-25-080-020-01 | IM-NHS-080-3(284)121--03-25 | Bridge Replacement-PPCB |  |  | 1369
|  | UP RR 2.3 mi W of I-35 | 18-25-080-020-01 | IM-NHS-080-3(288)121--03-25 | Bridge Replacement-PPCB |  |  |  | 1860
|  | UP RR 2.3 mi W of I-35 | 18-25-080-020-01 | IM-NHS-080-3(292)121--03-25 | Bridge Replacement-PPCB |  |  |  |  | 1944
[5 empty] | Culvert Extension |  |  | 274 | 286
|  | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 18-25-080-020-01 | IM-NHS-080-3(285)118--03-25 | RCB Culvert Extension - Single Box |  |  | 274
|  | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 18-25-080-020-01 | IM-NHS-080-3(289)118--03-25 | RCB Culvert Extension - Single Box |  |  |  | 286
[5 empty] | Grade and Pave |  |  | 8901 | 9302 | 9720
|  | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 18-25-080-020-01 | IM-NHS-080-3(282)118--03-25 | Unknown Pavement - Grade and New |  |  | 8901
|  | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 18-25-080-020-01 | IM-NHS-080-3(286)118--03-25 | Unknown Pavement - Grade and New |  |  |  | 9302
|  | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 18-25-080-020-01 | IM-NHS-080-3(290)118--03-25 | Unknown Pavement - Grade and New |  |  |  |  | 9720
[5 empty] | Right of Way |  |  | 550
|  | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 18-25-080-020-01 | IMN-080-3(294)118--0E-25 | Right Of Way |  |  | 550
[5 empty] | Traffic Signs |  |  | 800 | 800 | 500
|  | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 18-25-080-020-01 | IM-080-3(283)118--13-25 | Traffic Signs |  |  | 800
|  | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 18-25-080-020-01 | IM-080-3(287)118--13-25 | Traffic Signs |  |  |  | 800
|  | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 18-25-080-020-01 | IM-080-3(291)118--13-25 | Traffic Signs |  |  |  |  | 500
Dallas | 80 | WEIGH STATION 2.0 MI E OF VAN METER |  |  | Weigh Scale Improvement | 1000
|  | Weigh Station 2.0 mi E of Van Meter Interchange (Inspection Bldg/Pit Barn) | 20-25-080-040 | IMN-080-3(281)115--0E-25 | Weigh Scale Building - New | 1000
Dallas | 169 | S OF N RACCOON RIVER 1.4 MI N OF US 6 |  |  | Pipe Culverts |  |  |  | 399
|  | S of N Raccoon River Bridge 1.4 mi N of US 6 | 20-25-169-010 | NHSN-169-4(67)--2R-25 | Storm Sewer/Intakes |  |  |  | 399
[5 empty] | Right of Way |  |  |  | 2
|  | S of N Raccoon River Bridge 1.4 mi N of US 6 | 20-25-169-010 | NHSN-169-4(68)--2R-25 | Right Of Way |  |  |  | 2
Fremont | 2 | 0.8 mi E of the Missouri River to Horse Creek Ditch |  |  | Bridge New | 2000
|  | Overflow Bridge 2.2 mi W of I-29 (EB/WB) | 19-36-002-070-01 | ER-002-1(135)--28-36 | Bridge New-CCS | 2000
Fremont | 2 | Ditch 2.8 mi E of I-29 |  |  | Bridge Replacement |  |  |  | 3500
|  | Drainage Ditch 2.8 mi E of I-29 | 19-36-002-030 | BRF-002-1(114)--38-36 | Bridge-Unspecified |  |  |  | 3500
Fremont | 2 | Ditch 3.1 mi E of I-29 |  |  | Bridge Replacement |  |  |  | 3500
|  | Drainage Ditch 3.1 mi E of I-29 | 19-36-002-040 | BRF-002-1(116)--38-36 | Bridge-Unspecified |  |  |  | 3500
Fremont | 2 | Fisher Creek 2.2 mi W of US 59 |  |  | Bridge Deck Overlay |  |  |  | 450
|  | Fisher Creek 2.2 mi W of US 59 | 19-36-002-020 | BRFN-002-1(120)--39-36 | Bridge Deck Overlay |  |  |  | 450
Fremont | 2 | Missouri River E of Nebraska City (State Share) |  |  | Bridge Cleaning | 21 | 21 | 21 | 21 | 21
|  | Missouri River E of Nebraska City | 16-36-002-020 | BRFN-002-1(105)--39-36 | Bridge Cleaning | 21
|  | Missouri River E of Nebraska City | 16-36-002-020 | BRFN-002-1(109)--39-36 | Bridge Cleaning |  | 21
|  | Missouri River E of Nebraska City | 16-36-002-020 | BRFN-002-1(110)--39-36 | Bridge Cleaning |  |  | 21
|  | Missouri River E of Nebraska City | 16-36-002-020 | BRFN-002-1(112)--39-36 | Bridge Cleaning |  |  |  | 21
|  | Missouri River E of Nebraska City | 16-36-002-020 | BRFN-002-1(134)--39-36 | Bridge Cleaning |  |  |  |  | 21
Fremont | 2 | Missouri River E of Nebraska City (State Share) |  |  | Bridge Deck Overlay | 799
|  | Missouri River E of Nebraska City | 16-36-002-030 | BRFN-002-1(106)--39-36 | Bridge Deck Overlay | 799
Fremont | 2 | Missouri River Overflow east of Missouri River |  |  | Erosion Control | 150
|  | Missouri River east 0.8 mi. | 19-36-002-070 | NHSN-002-1(124)--2R-36 | Erosion Control | 150
[5 empty] | Mitigation | 523
|  | Copeland Bend Wetland Mitigation Site for the IA 2 Overflow Bridges | 19-36-002-070-02 | NHSN-002-1(133)--2R-36 | Wetland Mitigation | 523
Fremont | 2 | Stream 3.9 mi E of I-29 |  |  | Bridge Replacement |  |  |  | 3500
|  | Stream 3.9 mi E of I-29 | 16-36-002-060 | BRFN-002-1(108)--39-36 | Bridge Deck Overlay |  |  |  | 3500
Fremont | 29 | 1.5 mi N of Co Rd L31 to 1.0 mi N of Co Rd J18 (SB) |  |  | Pavement Rehab |  |  | 1047
|  | 1.5 mi N of Co Rd L31 to 1 mi N of Co Rd J18 (SB) | 18-36-029-020 | IMN-029-1(119)17--0E-36 | HMA Resurfacing |  |  | 1047
Fremont | 29 | 200th St 5.4 mi N of IA 2 |  |  | Bridge Deck Overlay |  |  |  |  | 710
|  | 200th St 5.4 mi N of IA 2 | 20-36-029-020 | IMN-029-1(131)16--0E-36 | Bridge Deck Overlay |  |  |  |  | 710
Fremont | 29 | ABANDONED RR 1.6 MI S OF IA 2 (SB) |  |  | Bridge Deck Overlay |  |  |  | 800
|  | Abandoned RR and Local Rd 1.6 mi S of IA 2 (SB) | 19-36-029-020 | IMN-029-1(120)9--0E-36 | Bridge Deck Overlay |  |  |  | 800
Fremont | 29 | MAIN DITCH #6 0.4 MI S OF IA 333 (NB & SB) |  |  | Bridge Deck Overlay |  | 1725
|  | Main Ditch #6 0.4 mi S of IA 333 (NB & SB) | 17-36-029-020 | IMN-029-1(116)1--0E-36 | Bridge Deck Overlay |  | 1725
Fremont | 29 | Missouri to 1.0 mi S of IA 2 (NB) |  |  | Pavement Rehab |  | 2226
|  | Missouri State Line to 1 mi S of IA 2 (NB) | 18-36-029-010 | IMN-029-1(118)0--0E-36 | HMA Resurfacing |  | 2226
Guthrie | 25 | Brushy Creek 3.2 mi N of IA 44 |  |  | Bridge Deck Overlay |  |  |  |  | 780
|  | Brushy Creek 3.2 mi N of IA 44 | 20-39-025-010 | BRFN-025-4(41)--39-39 | Bridge Deck Overlay |  |  |  |  | 780
Guthrie | 44 | Middle Raccoon River 1.2 mi W of IA 4 |  |  | Bridge Deck Overlay | 772
|  | Middle Raccoon River 1.2 mi W of IA 4 | 16-39-044-010 | BRFN-044-4(44)--39-39 | Bridge Deck Overlay | 772
Harrison | 29 | Soldier Creek 4.0 mi N of IA 127 (NB/SB) |  |  | Bridge Replacement |  |  |  |  | 4060
|  | Soldier Creek 4.0 mi N of IA 127 (NB/SB) | 20-43-029-020 | IMX-029-5(263)85--02-43 | Bridge-Unspecified |  |  |  |  | 4060
Harrison | 29 | US 30 Interchange in Missouri Valley |  |  | Lighting | 690
|  | US 30 Interchange in Missouri Valley | 20-43-029-010 | IMN-029-4(129)76--0E-43 | Lighting | 690
Harrison | 30 | Missouri River E of Blair Nebraska (State Share) |  |  | Bridge Cleaning | 35 | 35 | 35 | 35 | 35
|  | Missouri River E of Blair, Nebraska | 16-43-030-020 | BRFN-030-1(159)--39-43 | Bridge Cleaning | 35
|  | Missouri River E of Blair, Nebraska | 16-43-030-020 | BRFN-030-1(162)--39-43 | Bridge Cleaning |  | 35
|  | Missouri River E of Blair, Nebraska | 16-43-030-020 | BRFN-030-1(174)--39-43 | Bridge Cleaning |  |  | 35
|  | Missouri River E of Blair, Nebraska | 16-43-030-020 | BRFN-030-1(187)--39-43 | Bridge Cleaning |  |  |  | 35
|  | Missouri River E of Blair, Nebraska | 16-43-030-020 | BRFN-030-1(189)--39-43 | Bridge Cleaning |  |  |  |  | 35
Harrison | 30 | Missouri River E of Blair Nebraska (State share) |  |  | Bridge Rehabilitation |  |  | 125
|  | Missouri River E of Blair, Nebraska | 18-43-030-020 | BRFN-030-1(177)--39-43 | Bridge Repair |  |  | 125
Harrison | 30 | Missouri River to I-29 |  |  | Pave Shoulder | 1624
|  | Missouri River to I-29 | 19-43-030-010 | HSIPX-030-1(188)--3L-43 | HMA Paved Shoulder - New | 1624
[5 empty] | Pavement Rehab | 4114
|  | Missouri River to I-29 | 19-43-030-010 | NHSX-030-1(190)--3H-43 | HMA Resurfacing with Milling | 4114
Harrison | 30 | Missouri Valley Bypass |  |  | Culvert New |  |  |  |  | 1914
|  | Missouri Valley Bypass | 18-43-030-010 | NHSX-030-1(181)--3H-43 | RCB Culvert New - Single Box |  |  |  |  | 1914
[5 empty] | Grading |  |  |  |  | 42342
|  | Missouri Valley Bypass | 18-43-030-010 | NHSX-030-1(180)--3H-43 | Grading |  |  |  |  | 42342
[5 empty] | Right of Way |  |  |  | 6800
|  | Missouri Valley Bypass | 18-43-030-010 | NHSN-030-1(176)--2R-43 | Right Of Way |  |  |  | 6800
Harrison | 30 | Stream 2.3 mi E of Co Rd F32 |  |  | Bridge Replacement |  | 1273
|  | Stream 2.3 mi E of Co Rd F32 | 17-43-030-030 | BRFN-030-1(164)--39-43 | Bridge Replacement-PPCB |  | 1273
[5 empty] | Right of Way |  | 10
|  | Stream 2.3 mi E of Co Rd F32 | 17-43-030-030 | NHSN-030-1(165)--2R-43 | Right Of Way |  | 10
Harrison | 30 | Stream 3.4 mi E of IA 44 |  |  | Bridge Replacement |  |  |  |  | 1020
|  | Stream 3.4 mi E of IA 44 | 20-43-030-020 | BRF-030-1(191)--38-43 | Bridge-Unspecified |  |  |  |  | 1020
Harrison | 30 | Wilson Ditch 2.1 mi W of I-29 |  |  | Bridge Replacement |  | 928
|  | Wilson Ditch 2.1 mi W of I-29 | 17-43-030-040 | BRFN-030-1(166)--39-43 | RCB Culvert Replacement - Twin Box |  | 928
[5 empty] | Right of Way |  | 10
|  | Wilson Ditch 2.1 mi W of I-29 | 17-43-030-040 | NHSN-030-1(167)--2R-43 | Right Of Way |  | 10
Harrison | 127 | Steer Creek 0.5 mi E of IA 183 |  |  | Bridge Deck Overlay |  |  | 740
|  | Steer Creek 0.5 mi E of IA 183 | 18-43-127-010 | BRFN-127-1(26)--39-43 | Bridge Deck Overlay |  |  | 740
Madison | 169 | North River 3.5 mi N of N Jct IA 92 |  |  | Bridge Deck Overlay |  | 378
|  | North River 3.5 mi N of N Jct IA 92 | 17-61-169-010 | BRFN-169-3(47)--39-61 | Bridge Deck Overlay |  | 378
Mills | 29 | Rest Area N of US 34 (NB) |  |  | Rest Area Improvement |  | 3971
|  | NB Rest Area N of US 34 | 10-65-029-010 | IMN-029-2(72)38--0E-65 | Rest Area Building - New |  | 3971
Mills | 34 | BNSF RR 0.9 mi E of Co Rd L55 |  |  | Bridge Rehabilitation | 1309
|  | BNSF RR 0.9 mi E of Co Rd L55 | 18-65-034-010 | BRF-034-1(111)--38-65 | Bridge Rehabilitation | 1309
Mills | 34 | Douglas Creek 0.7 mi E of W Jct Co Rd H34 |  |  | Bridge Rehabilitation | 592
|  | Douglas Creek 0.7 mi E of W Jct Co Rd H34 | 19-65-034-010 | BRF-034-1(114)--38-65 | Reconstruction - Bridge Deck Replacement | 592
Mills | 34 | Missouri River N of Plattsmouth Nebraska |  |  | Traffic Signs |  |  |  |  | 300
|  | Missouri River N of Plattsmouth Nebraska | 17-65-034-020 | ITS-034-1(107)--25-65 | ITS Integration |  |  |  |  | 300
Mills | 34 | Missouri River N of Plattsmouth Nebraska (State Share) |  |  | Bridge Cleaning | 45 | 45 | 45 | 45 | 45
|  | Missouri River N of Plattsmouth Nebraska | 12-65-034-020 | BRFN-034-1(103)--39-65 | Bridge Cleaning | 45
|  | Missouri River N of Plattsmouth Nebraska | 12-65-034-020 | BRFN-034-1(104)--39-65 | Bridge Cleaning |  | 45
|  | Missouri River N of Plattsmouth Nebraska | 12-65-034-020 | BRFN-034-1(110)--39-65 | Bridge Cleaning |  |  | 45
|  | Missouri River N of Plattsmouth Nebraska | 12-65-034-020 | BRFN-034-1(113)--39-65 | Bridge Cleaning |  |  |  | 45
|  | Missouri River N of Plattsmouth Nebraska | 12-65-034-020 | BRFN-034-1(119)--39-65 | Bridge Cleaning |  |  |  |  | 45
Mills | 275 | N of NCL of Tabor to US 34 |  |  | Pave Shoulder | 1483
|  | N of the NCL of Tabor to US 34 | 20-65-275-010 | HSIPX-275-2(24)--3L-65 | HMA Paved Shoulder - New | 1483
[5 empty] | Pavement Rehab | 3543
|  | N of the NCL of Tabor to US 34 | 20-65-275-010 | STP-275-2(23)--2C-65 | HMA Resurfacing with Milling | 3543
Montgomery | 34 | Middle Nodaway River 3.0 mi E of US 71 |  |  | Bridge Deck Overlay |  |  | 638
|  | Middle Nodaway River 3.0 mi E of US 71 | 18-69-034-010 | BRFN-034-2(65)--39-69 | Bridge Deck Overlay |  |  | 638
Montgomery | 34 | Tarkio River 0.7 mi W of Co Rd M63 |  |  | Bridge Deck Overlay |  |  |  |  | 450
|  | Tarkio River 0.7 mi W of Co Rd M63 | 20-69-034-020 | BRFN-034-2(68)--39-69 | Bridge Deck Overlay |  |  |  |  | 450
Montgomery | 34 | W of IA 48 to Co Rd H34 |  |  | Grade and Pave |  |  |  | 14022
|  | W of IA 48 to Co Rd H34 | 16-69-034-010 | NHSX-034-2(60)--3H-69 | PCC Pavement - Grade and Replace |  |  |  | 14022
Montgomery | 34 | West Nodaway River 0.3 mi W of US 71 (EB & WB) |  |  | Bridge Deck Overlay |  | 1342
|  | West Nodaway River 0.3 mi W of US 71 (EB & WB) | 17-69-034-010 | BRFN-034-2(63)--39-69 | Bridge Deck Overlay |  | 1342
Montgomery | 34 | West Nodaway River 0.3 mi W of US 71 (EB) |  |  | Right of Way |  | 4
|  | West Nodaway River 0.3 mi W of US 71 | 20-69-034-010 | NHSN-034-2(67)--2R-69 | Right Of Way |  | 4
[5 empty] | Rip Rap |  | 1155
|  | West Nodaway River 0.3 mi W of US 71 | 20-69-034-010 | NHSN-034-2(66)--2R-69 | Revetment |  | 1155
Montgomery | 48 | E Nishnabotna River 1.9 mi S of Co Rd H14 |  |  | Bridge Deck Overlay | 459
|  | E Nishnabotna River 1.9 mi S of Co Rd H14 | 16-69-048-010 | BRFN-048-2(49)--39-69 | Bridge Deck Overlay | 459
Page | 59 | East Nishnabotna River 1.0 mi N of IA 48 |  |  | Bridge Replacement |  |  | 6475
|  | East Nishnabotna River 1.0 mi N of IA 48 | 16-73-059-010 | BRF-059-1(31)--38-73 | Bridge Replacement-PPCB |  |  | 6475
[5 empty] | Right of Way |  | 40
|  | East Nishnabotna River 1.0 mi N of IA 48 | 16-73-059-010 | NHSN-059-1(32)--2R-73 | Right Of Way |  | 30
|  | East Nishnabotna River 1.0 mi N of IA 48 | 16-73-059-010 | NHSN-059-1(33)--2R-36 | Right Of Way |  | 10
Pottawattamie | 29 | 25th St 1.0 mi S of N 16th St in Council Bluffs (NB & SB) |  |  | Bridge Rehabilitation |  |  |  |  | 1900
|  | 25th St 1.0 mi S of N 16th St in Council Bluffs (NB & SB) | 20-78-029-030 | IMN-029-3(262)56--0E-78 | Reconstruction - Bridge Deck Replacement |  |  |  |  | 1900
Pottawattamie | 29 | CC RR 2.1 mi N of US 6 in Council Bluffs (SB) |  |  | Bridge Rehabilitation |  |  |  |  | 3170
|  | CC RR 2.1 mi N of US 6 in Council Bluffs (SB) | 20-78-029-040 | IMN-029-3(264)56--0E-78 | Reconstruction - Bridge Deck Replacement |  |  |  |  | 3170
Pottawattamie | 29 | Co Rd G12 0.4 mi N of I-880 |  |  | Bridge Replacement |  | 1684
|  | Co Rd G12 Interchange 0.4 mi N of I-880 | 16-78-029-070 | BRFIMX-029-4(113)72--14-78 | Bridge Replacement-PPCB |  | 1684
[5 empty] | Grade and Pave |  | 1775
|  | Co Rd G12 Interchange 0.4 mi N of I-880 | 16-78-029-070 | IMX-029-4(112)72--02-78 | PCC Pavement - Grade and Replace |  | 1775
[5 empty] | Lighting |  | 80
|  | Co Rd G12 Interchange 0.4 mi N of I-880 | 16-78-029-070 | IMX-029-4(116)72--02-78 | Lighting |  | 80
[5 empty] | Traffic Signs |  | 250
|  | Co Rd G12 Interchange 0.4 mi N of I-880 | 16-78-029-070 | IMX-029-4(115)72--02-78 | Traffic Signs |  | 250
Pottawattamie | 29 | Ditch 0.5 mi S of I-880 |  |  | Bridge Replacement |  | 1703
|  | Ditch 0.5 mi S of I-880 | 16-78-029-040-02 | IMX-029-4(111)71--02-78 | RCB Culvert Replacement - Twin Box |  | 1703
Pottawattamie | 29 | Ditch 1.6 mi S of I-880 |  |  | Bridge Replacement |  | 912
|  | Ditch 1.6 mi S of I-880 | 16-78-029-040-01 | IMX-029-4(110)70--02-78 | RCB Culvert Replacement - Twin Box |  | 912
Pottawattamie | 29 | Ditch 2.4 mi S of I-880 |  |  | Bridge Replacement |  | 1207
|  | Ditch 2.4 mi S of I-880 | 16-78-029-040 | IMX-029-4(109)69--02-78 | RCB Culvert Replacement - Triple Box |  | 1207
[5 empty] | Traffic Signs |  | 60
|  | Ditch 2.4 mi S of I-880 | 16-78-029-040 | ITS-029-4(120)69--25-78 | Intelligent Work Zone (IWZ) |  | 60
Pottawattamie | 59 | At Jct IA 92 |  |  | Bridge Replacement |  |  |  |  | 2540
|  | At Jct IA 92 | 20-78-059-020 | BRF-059-3(47)--38-78 | Bridge-Unspecified |  |  |  |  | 2540
Pottawattamie | 59 | Co Rd G30 to SCL of Avoca |  |  | Pavement Rehab | 3449
|  | Co Rd G30 to SCL of Avoca | 20-78-059-010 | NHSX-059-3(46)--3H-78 | HMA Resurfacing with Milling | 3449
Pottawattamie | 59 | E Branch W Nishnabotna River 1.0 mi S of IA 83 |  |  | Bridge Replacement |  |  | 2875
|  | East Branch West Nishnabotna River 1.0 mi S of IA 83 | 18-78-059-010 | BRF-059-3(44)--38-78 | Bridge-Unspecified |  |  | 2875
Pottawattamie | 59 | I-80 Interchange at Avoca (NB & SB) |  |  | Bridge Deck Overlay |  | 647
|  | I-80 Interchange at Avoca (NB/SB) | 17-78-059-010 | BRFN-059-3(40)--39-78 | Bridge Deck Overlay |  | 647
Pottawattamie | 59 | Stream 0.2 mi S of Co Rd G30 in Hancock |  |  | Bridge Replacement | 879
|  | Stream 0.2 mi S of Co Rd G30 in Hancock | 16-78-059-020 | BRFN-059-3(38)--39-78 | RCB Culvert Replacement - Twin Box | 879
Pottawattamie | 59 | Stream 2.4 mi N of IA 92 |  |  | Bridge Deck Overlay |  | 138
|  | Stream 2.4 mi N of IA 92 | 16-78-059-010 | BRFN-059-3(37)--39-78 | Bridge Deck Overlay |  | 138
Pottawattamie | 80 | 0.1 mi W of Silver Creek Bridge to Cass Co (EB/WB) |  |  | Pavement Rehab |  |  |  |  | 5583
|  | 0.1 mi W of Silver Creek Bridge to Cass Co (EB/WB) | 20-78-080-090 | IMX-080-1(524)35--02-78 | HMA Resurfacing with Milling |  |  |  |  | 5583
Pottawattamie | 80 | 0.4 mi E of I-880 to 0.1 mi W of Silver Creek Bridge (EB & WB) |  |  | Pavement Rehab |  |  |  |  | 2692
|  | 0.4 mi E of I-880 to 0.1 mi W of Silver Creek Bridge (EB & WB) | 20-78-080-070 | IMN-080-1(522)28--0E-78 | HMA Resurfacing with Milling |  |  |  |  | 2692
Pottawattamie | 80 | 0.4 mi E of I-880 to 0.1 mi W of Silver Creek Bridge (WB) |  |  | Pavement Planing |  |  |  |  | 1053
|  | 0.4 mi E of I-880 to 0.1 mi W of Silver Creek Bridge (WB) | 20-78-080-080 | IMN-080-1(523)28--0E-78 | Pavement Planing/Grooving |  |  |  |  | 1053
Pottawattamie | 80 | 24th St to Indian Creek in Council Bluffs |  |  | Grading |  |  | 1750
|  | 24th St Interchange to Indian Creek in Council Bluffs | 20-78-080-010 | IMN-080-1(516)2--0E-78 | Grading |  |  | 1750
Pottawattamie | 80 | Abandoned RR 3.0 mi E of I-880 (Bridge Removal EB & WB) |  |  | Grade and Pave |  |  |  |  | 520
|  | Abaondoned RR 3.0 mi E of I-880 (Bridge Removal EB & WB) | 20-78-080-060 | IMN-080-1(521)30--0E-78 | PCC Pavement - Grade and New |  |  |  |  | 520
Pottawattamie | 80 | Co Rd G30 Interchange |  |  | Bridge Deck Overlay |  |  |  |  | 800
|  | Co Rd G30 Interchange | 20-78-080-050 | IMN-080-1(520)18--0E-78 | Bridge Deck Overlay |  |  |  |  | 800
Pottawattamie | 80 | Co Rd G30 to Co Rd L66 |  |  | Guardrail | 2000
|  | Co Rd G30 to Co Rd L66 | 20-78-080-030 | IHSIPX-080-1(518)18--08-78 | Guardrail | 2000
Pottawattamie | 80 | Co Rd M16 Interchange at Shelby |  |  | Bridge Deck Overlay |  | 272
|  | Co Rd M16 Interchange at Shelby | 17-78-080-010 | IMN-080-1(481)34--0E-78 | Bridge Deck Overlay |  | 272
Pottawattamie | 80 | Franklin Ave to US 6 in Council Bluffs |  |  | Pavement Rehab |  |  |  |  | 3658
|  | Franklin Ave to US 6 in Council Bluffs | 20-78-080-020 | IMN-080-1(517)6--0E-78 | HMA Resurfacing |  |  |  |  | 3658
Pottawattamie | 80 | I-29/80/480 Interstates In Council Bluffs (CBIS) State Share |  |  | Bridge Painting |  | 240 | 290 | 650
|  | CBIS Section 4 - I-29/I-480 Systems Interchange | 04-78-029-010-04 | IMN-029-3(229)54--0E-78 | Bridge Painting |  |  |  | 550
|  | CBIS Section 3 - East Systems Interchange | 04-78-029-010-03 | IMN-080-1(497)4--0E-78 | Bridge Painting |  | 240
|  | CBIS Section 3 - South Expressway / Ramp F | 04-78-029-010-03 | IMN-080-1(498)3--0E-78 | Bridge Painting |  |  | 290
|  | CBIS Section - Madison Ave Interchange | 04-78-029-010-03 | IMN-080-1(499)5--0E-78 | Bridge Painting |  |  |  | 100
[5 empty] | Bridge Replacement | 47469 | 81950
|  | I-29 / 480 / US 6 (Broadway) Interchange in Council Bluffs (NB) | 04-78-029-010-04 | IM-029-3(192)54--13-78 | Bridge New-Steel Girder | 15621
|  | I-29 / 480 / US 6 (Broadway) Interchange in Council Bluffs (SB) | 04-78-029-010-04 | IM-029-3(193)54--13-78 | Bridge New-Steel Girder | 21027
|  | W-N Connector I-480 to I-29 over Ramp H (US 6 WB), WB W Broadway, SB Frontage Rd, and I-29 (Ramp F) | 04-78-029-010-04 | IM-029-3(221)54--13-78 | Bridge New-Steel Girder |  | 15562
|  | N-W Connector I-29 to I-480 over WB W Broadway and SB Frontage Rd (Ramp A) | 04-78-029-010-04 | IM-029-3(222)54--13-78 | Bridge New-Steel Girder |  | 7772
|  | I-29 (US 6 WB/EB) over 9th Ave (NB/SB) | 04-78-029-010-04 | IM-029-3(70)53--13-78 | Bridge Replacement-PPCB |  | 2561
|  | I-29 over 2nd Ave (NB/SB) | 04-78-029-010-04 | IM-029-3(71)54--13-78 | Bridge Replacement-PPCB |  | 4001
|  | I-29 over W Broadway (NB/SB) | 04-78-029-010-04 | IM-029-3(73)54--13-78 | Bridge Replacement-PPCB |  | 4432
|  | I-29 over Ave G (NB/SB) | 04-78-029-010-04 | IM-029-3(74)54--13-78 | Bridge Replacement-PPCB |  | 5990
|  | I-80 EB In Council Bluffs Over Madison Ave. | 04-78-029-010-03 | IM-080-1(313)5--13-78 | Bridge Replacement-PPCB |  | 3105
|  | I-80 WB In Council Bluffs Over BNSF R.R, Mosquito Creek & Valley View Dr. 0.25 Mile E. Of Madison Ave. | 04-78-029-010-03 | IM-080-1(314)5--13-78 | Bridge Replacement-Steel Girder |  | 11080
|  | I-480 Connector (US 6 EB) to Ramp C and Ramp F over 40th St | 04-78-029-010-04 | IM-480-1(166)0--13-78 | Bridge New-Steel Girder |  | 4275
|  | I-480 WB Connector (US 6 WB) from Ramp A and Ramp H over 40th St | 04-78-029-010-04 | IM-480-1(167)0--13-78 | Bridge New-Steel Girder |  | 3825
|  | In Council Bluffs I-29 NB Over Nebraska Ave. & UP Spur Line | 04-78-029-010-02 | IM-NHS-029-3(142)53--03-78 | Bridge Replacement-Steel Girder | 5560
|  | I-29 SB In Council Bluffs Over Nebraska Ave. & UP R. R. Spur Line | 04-78-029-010-02 | IM-NHS-029-3(68)53--03-78 | Bridge Replacement-Steel Girder | 5261
|  | In Council Bluffs Over BN/SF R.R./Mosquito Creek/ Valley View Dr. | 04-78-029-010-03 | IM-NHS-080-1(448)5--03-78 | Bridge Replacement-Steel Girder |  | 10800
|  | In Council Bluffs On I-80 EB Madison Ave. Ramp "D" Bridge Over BN/SF R.R./Mosquito Creek/Valley View Dr. | 04-78-029-010-03 | IM-NHS-080-1(449)5--03-78 | Bridge New-Steel Girder |  | 2900
|  | In Council Bluffs On I-80 WB Madison Ave. Ramp "A" Bridge Over BN/SF R.R./Mosquito Creek/Valley View Dr. | 04-78-029-010-03 | IM-NHS-080-1(450)5--03-78 | Bridge New-Steel Girder |  | 2882
|  | In Council Bluffs On I-80 WB Over Madison Ave. | 04-78-029-010-03 | IM-NHS-080-1(451)5--03-78 | Bridge Replacement-PPCB |  | 2765
[5 empty] | Grade and Pave | 114057 | 41575 | 337
|  | In Council Bluffs from N of UP RR to the 25th St Interchange (NB) | 04-78-029-010-04 | IM-029-3(190)53--13-78 | PCC Pavement - Grade and New | 89057
|  | On Nebraska Ave from SB Ramp Terminal to 35th St | 04-78-029-010-02 | IM-029-3(238)53--13-78 | HMA Resurfacing |  |  | 337
|  | In Council Bluffs At The Nebraska Ave. Interchange | 04-78-029-010-02 | IM-NHS-029-3(141)53--03-78 | PCC Pavement - Grade and New | 25000
|  | In Council Bluffs At The Madison Ave. Interchange | 04-78-029-010-03 | IM-NHS-080-1(447)5--03-78 | PCC Pavement - Grade and New |  | 41575
[5 empty] | Grading |  | 500
|  | CBIS Sec 2 and Sec 3 - Utility Relocation | 04-78-029-010-02 | IMN-029-3(185)52--0E-78 | Grading |  | 500
[5 empty] | Landscaping | 1950 | 916 | 1431 | 1783
|  | W I-29/80 Systems Interchange in Council Bluffs | 04-78-029-010-02 | IMN-029-3(235)52--0E-78 | Landscaping | 1950
|  | Nebraska Ave Interchange in Council Bluffs | 04-78-029-010-02 | IMN-029-3(236)53--0E-78 | Landscaping |  |  | 813
|  | I-29/I-480/W Broadway Interchange in Council Bluffs | 04-78-029-010-04 | IMN-029-3(237)53--0E-78 | Landscaping |  |  |  | 1000
|  | E I-29/80 Interchange to Madison Ave in Council Bluffs | 04-78-029-010-03 | IMN-080-1(501)4--0E-78 | Landscaping |  | 916
|  | South Expressway Interchange in Council Bluffs | 04-78-029-010-03 | IMN-080-1(503)3--0E-78 | Landscaping |  |  | 618
|  | Madison Ave Interchange in Council Bluffs | 04-78-029-010-03 | IMN-080-1(504)5--0E-78 | Landscaping |  |  |  | 430
|  | E of Madison Ave Interchange in Council Bluffs | 04-78-029-010-03 | IMN-080-1(505)5--0E-78 | Landscaping |  |  |  | 138
|  | W I-29/80 Interchange to Indian Creek in Council Bluffs | 04-78-029-010-02 | IMN-080-1(506)1--0E-78 | Landscaping |  |  |  | 215
[5 empty] | Lighting | 2206 | 6240
|  | In Council Bluffs at the Nebraska Ave Interchange | 04-78-029-010-02 | IM-029-3(184)53--13-78 | Lighting | 2206
|  | I-29/I-480/W Broadway Interchange and Frontage Roads in Council Bluffs | 04-78-029-010-04 | IM-029-3(220)53--13-78 | Lighting |  | 4613
|  | In Council Bluffs at the Madison Ave Interchange | 04-78-029-010-03 | IM-NHS-080-1(469)5--03-78 | Lighting |  | 1627
[5 empty] | Noise Wall |  | 966
|  | In Council Bluffs at the Madison Ave Interchange | 04-78-029-010-03 | IM-NHS-080-1(467)5--03-78 | Noise Wall |  | 966
[5 empty] | Pavement Markings | 440 | 715 | 175 | 1025
|  | S of US 275 to E or IA 192/S Expressway Interchange (NB) | 04-78-029-010 | IMN-029-2(92)47--0E-78 | Pavement Markings | 240
|  | Various Interstate Routes in Council Bluffs | 04-78-029-010 | IMN-029-3(204)52--0E-78 | Pavement Markings | 200
|  | Various Interstate Routes in Council Bluffs | 04-78-029-010 | IMN-029-3(205)52--0E-78 | Pavement Markings |  | 200
|  | Various Interstate Routes in Council Bluffs | 04-78-029-010 | IMN-029-3(227)52--0E-78 | Pavement Markings |  |  | 175
|  | S of Nebraska Ave to N of Ave G (NB/SB) and I-480 | 04-78-029-010 | IMN-029-3(249)52--0E-78 | Pavement Markings |  |  |  | 1025
|  | W I-29/80 Interchange to E of E I-29/80 Interchange (EB) and I-29 S of US 275 to E I-29/80 Interchange (SB) | 04-78-029-010 | IMN-080-1(513)1--0E-78 | Pavement Markings |  | 515
[5 empty] | Traffic Signals | 480 | 3293
|  | I-29/I-480/W Broadway Interchange and Frontage Roads in Council Bluffs | 04-78-029-010-04 | IM-029-3(219)53--13-78 | Traffic Signals |  | 1841
|  | Nebraska Ave Interchange | 04-78-029-010-02 | IM-029-3(232)53--13-78 | Traffic Signals | 480
|  | Madison Ave Interchange | 04-78-029-010-03 | IM-NHS-080-1(511)5--03-78 | Traffic Signals |  | 1452
[5 empty] | Traffic Signs | 5490 | 2345 | 1950 | 1130
|  | In Council Bluffs at the Nebraska Ave Interchange | 04-78-029-010-02 | IM-029-3(183)53--13-78 | Traffic Signs | 1273
|  | I-29/I-480/W Broadway Interchange and Frontage Roads in Council Bluffs | 04-78-029-010-04 | IM-029-3(218)53--13-78 | Traffic Signs | 3117
|  | In Council Bluffs at the Madison Ave Interchange | 04-78-029-010-03 | IM-NHS-080-1(468)5--03-78 | Traffic Signs |  | 870
|  | CBIS - ITS Fiber (FY 2021) | 04-78-029-010 | IMN-029-3(177)54--0E-78 | ITS Integration | 125
|  | CBIS - ITS Devices (FY 2021) | 04-78-029-010 | IMN-029-3(178)54--0E-78 | ITS Integration | 250
|  | CBIS - ITS Intelligent Work Zone Deployment (FY 2021) | 04-78-029-010 | IMN-029-3(179)54--0E-78 | Intelligent Work Zone (IWZ) | 125
|  | CBIS - ITS Fiber (FY 2022) | 04-78-029-010 | IMN-029-3(180)54--0E-78 | ITS Integration |  | 250
|  | CBIS - ITS Devices (FY 2022) | 04-78-029-010 | IMN-029-3(181)54--0E-78 | ITS Equipment |  | 500
|  | CBIS - ITS Intelligent Work Zone Deployment (FY 2022) | 04-78-029-010 | IMN-029-3(182)54--0E-78 | Intelligent Work Zone (IWZ) |  | 125
|  | CBIS - Highway Helper (FY 2021) | 04-78-029-010 | IMN-029-3(209)52--0E-78 | Traffic Operations (other) | 600
|  | CBIS - Highway Helper (FY 2022) | 04-78-029-010 | IMN-029-3(210)52--0E-78 | Traffic Operations (other) |  | 600
|  | CBIS - ITS Fiber (FY 2023) | 04-78-029-010 | IMN-029-3(212)54--0E-78 | ITS Integration |  |  | 225
|  | CBIS - ITS Fiber (FY 2023) | 04-78-029-010 | IMN-029-3(213)54--0E-78 | ITS Equipment |  |  | 1000
|  | CBIS - Intelligent Work Zone Deployment (FY 2023) | 04-78-029-010 | IMN-029-3(225)54--0E-78 | Intelligent Work Zone (IWZ) |  |  | 125
|  | CBIS - Highway Helper (FY 2023) | 04-78-029-010 | IMN-029-3(226)52--0E-78 | Traffic Operations (other) |  |  | 600
|  | CBIS - Highway Helper (FY 2024) | 04-78-029-010 | IMN-029-3(247)52--0E-78 | Traffic Operations (other) |  |  |  | 600
|  | CBIS - ITS Fiber (FY 2024) | 04-78-029-010 | IMN-029-3(259)54--0E-78 | ITS Integration |  |  |  | 130
|  | CBIS - ITS Devices (FY 2024) | 04-78-029-010 | IMN-029-3(260)54--0E-78 | ITS Equipment |  |  |  | 300
|  | CBIS - Intelligent Work Zone Deployment (FY 2024) | 04-78-029-010 | IMN-029-3(261)54--0E-78 | Intelligent Work Zone (IWZ) |  |  |  | 100
Pottawattamie | 80 | I-880 Interchange (WB) |  |  | Bridge Deck Overlay | 774
|  | I-880 Interchange (WB) | 16-78-080-050 | IMN-080-1(476)27--0E-78 | Bridge Deck Overlay | 774
Pottawattamie | 80 | Idlewood Rd 4.6 mi E of US 6 (EB & WB) |  |  | Bridge Deck Overlay |  |  |  | 1600
|  | Idlewood Rd 4.6 mi E of US 6 (EB & WB) | 19-78-080-020 | IMN-080-1(514)13--0E-78 | Bridge Deck Overlay |  |  |  | 1600
Pottawattamie | 80 | Keg Creek 0.8 mi E of Co Rd L66 (EB & WB) |  |  | Bridge Rehabilitation |  |  |  |  | 2540
|  | Keg Creek 0.8 mi E of Co Rd L66 (EB/WB) | 18-78-080-030 | IMN-080-1(496)30--0E-78 | Bridge Rehabilitation |  |  |  |  | 2540
Pottawattamie | 80 | McPherson Ave 1.6 mi W of US 6 (WB) |  |  | Bridge Deck Overlay |  |  |  |  | 660
|  | McPherson Ave 1.6 mi W of US 6 (WB) | 20-78-080-040 | IMN-080-1(519)7--0E-78 | Bridge Deck Overlay |  |  |  |  | 660
Pottawattamie | 80 | Missouri River in Council Bluffs (EB & WB) (State Share) |  |  | Bridge Cleaning | 42 | 42 | 42 | 42 | 42
|  | Missouri River in Council Bluffs (EB/WB) | 16-78-080-020 | IMN-080-1(466)0--0E-78 | Bridge Cleaning | 42
|  | Missouri River in Council Bluffs (EB/WB) | 16-78-080-020 | IMN-080-1(477)0--0E-78 | Bridge Cleaning |  | 42
|  | Missouri River in Council Bluffs (EB/WB) | 16-78-080-020 | IMN-080-1(490)0--0E-78 | Bridge Cleaning |  |  | 42
|  | Missouri River in Council Bluffs (EB/WB) | 16-78-080-020 | IMN-080-1(509)0--0E-78 | Bridge Cleaning |  |  |  | 42
|  | Missouri River in Council Bluffs (EB/WB) | 16-78-080-020 | IMN-080-1(515)0--0E-78 | Bridge Cleaning |  |  |  |  | 42
Pottawattamie | 80 | W Nishnabotna River to 1.0 mi E of Rest Area (WB) |  |  | Pavement Rehab |  | 1406
|  | W Nishnabotna River to 1 mi E of the Rest Area (WB) | 18-78-080-040 | IMN-080-1(507)40--0E-78 | HMA Resurfacing |  | 1406
Pottawattamie | 80 | WB Rest Area 1.0 Mi N of Co Rd G30 N of Underwood |  |  | Rest Area Improvement |  |  |  |  | 4336
|  | WB Rest Area 1 mi N of Co Rd G30 N of Underwood | 94-78-080-370 | IMN-080-1(252)19--0E-78 | Rest Area Building - New |  |  |  |  | 4336
Pottawattamie | 92 | Graybill Creek 1.2 mi E of E Jct US 59 |  |  | Bridge Deck Overlay |  |  | 573
|  | Graybill Creek 1.2 mi E of E Jct US 59 | 18-78-092-010 | BRFN-092-1(73)--39-78 | Bridge Deck Overlay |  |  | 573
Pottawattamie | 92 | Harry Langdon Blvd in Council Bluffs to 0.3 mi E of State Orchard Rd |  |  | Pavement Rehab | 2861
|  | Harry Langdon Blvd in Council Bluffs to 0.3 mi E of State Orchard Rd | 17-78-092-020 | STP-092-1(72)--2C-78 | HMA Resurfacing with Milling | 2861
Pottawattamie | 92 | Indian Creek 0.7 mi W of Co Rd M47 |  |  | Bridge Replacement |  |  |  |  | 760
|  | Indian Creek 0.7 mi W of Co Rd M47 | 20-78-092-010 | BRFN-092-1(75)--39-78 | Bridge-Unspecified |  |  |  |  | 760
Pottawattamie | 92 | Jordan Creek 3.5 mi E of US 59 |  |  | Bridge Deck Overlay |  | 371
|  | Jordan Creek 3.5 mi E of US 59 | 17-78-092-010 | BRFN-092-1(71)--39-78 | Bridge Deck Overlay |  | 371
Pottawattamie | 92 | Silver Creek 2.8 mi E of Treynor |  |  | Bridge Deck Overlay |  |  |  | 400
|  | Silver Creek 2.8 mi E of Treynor | 19-78-092-010 | BRFN-092-1(74)--39-78 | Bridge Deck Overlay |  |  |  | 400
Pottawattamie | 275 | Missouri River in Council Bluffs (State Share) |  |  | Bridge Cleaning | 57 | 57 | 57 | 57 | 57
|  | In Council Bluffs over the Missouri River | 12-78-275-010 | BRFN-275-3(65)--39-78 | Bridge Cleaning | 57
|  | In Council Bluffs over the Missouri River | 12-78-275-010 | BRFN-275-3(66)--39-78 | Bridge Cleaning |  | 57
|  | In Council Bluffs over the Missouri River | 12-78-275-010 | BRFN-275-3(67)--39-78 | Bridge Cleaning |  |  | 57
|  | In Council Bluffs over the Missouri River | 12-78-275-010 | BRFN-275-3(68)--39-78 | Bridge Cleaning |  |  |  | 57
|  | In Council Bluffs over the Missouri River | 12-78-275-010 | BRFN-275-3(69)--39-78 | Bridge Cleaning |  |  |  |  | 57
Pottawattamie | 480 | Missouri River in Council Bluffs (State Share) |  |  | Bridge Cleaning | 30 | 30 | 30 | 30 | 30
|  | Missouri River in Council Bluffs | 16-78-480-010 | IMN-480-1(161)0--0E-78 | Bridge Cleaning | 30
|  | Missouri River in Council Bluffs | 16-78-480-010 | IMN-480-1(163)0--0E-78 | Bridge Cleaning |  | 30
|  | Missouri River in Council Bluffs | 16-78-480-010 | IMN-480-1(165)0--0E-78 | Bridge Cleaning |  |  | 30
|  | Missouri River in Council Bluffs | 16-78-480-010 | IMN-480-1(168)0--0E-78 | Bridge Cleaning |  |  |  | 30
|  | Missouri River in Council Bluffs | 16-78-480-010 | IMN-480-1(171)0--0E-78 | Bridge Cleaning |  |  |  |  | 30
[5 empty] | Bridge Deck Overlay | 1186
|  | Missouri River Bridge in Council Bluffs | 14-78-480-010 | IMN-480-1(151)0--0E-78 | Bridge Deck Overlay | 1186
[5 empty] | Bridge Painting |  |  | 2372
|  | Missouri River Bridge in Council Bluffs | 19-78-480-020 | IMN-480-1(170)0--0E-78 | Bridge Painting |  |  | 2372
Pottawattamie | 680 | At W Jct I-29 (EB & WB) |  |  | Bridge Deck Overlay |  |  |  | 2000
|  | A W Jct I-29 (EB & WB) | 19-78-680-020 | IMN-680-1(185)3--0E-78 | Bridge Deck Overlay |  |  |  | 2000
Pottawattamie | 680 | Missouri River in Council Bluffs (EB & WB) (State Share) |  |  | Bridge Cleaning | 48 | 48 | 48 | 48 | 48
|  | Missouri River 3.1 mi W of I-29 | 16-78-680-010 | IMN-680-1(176)0--0E-78 | Bridge Cleaning | 48
|  | Missouri River 3.1 mi W of I-29 | 16-78-680-010 | IMN-680-1(179)0--0E-78 | Bridge Cleaning |  | 48
|  | Missouri River 3.1 mi W of I-29 | 16-78-680-010 | IMN-680-1(182)0--0E-78 | Bridge Cleaning |  |  | 48
|  | Missouri River 3.1 mi W of I-29 | 16-78-680-010 | IMN-680-1(184)0--0E-78 | Bridge Cleaning |  |  |  | 48
|  | Missouri River 3.1 mi W of I-29 | 16-78-680-010 | IMN-680-1(190)0--0E-78 | Bridge Cleaning |  |  |  |  | 48
Pottawattamie | 880 | Mosquito Creek 0.5 mi E of IA 191 (WB) |  |  | Bridge Rehabilitation |  |  | 1000
|  | Mosquito Creek 0.5 mi E of IA 191 (WB) | 18-78-680-010 | IMN-880-1(2)16--0E-78 | Bridge Rehabilitation |  |  | 1000
Pottawattamie | 880 | Potato Creek 0.8 mi E of Co Rd L34 (EB & WB) |  |  | Bridge Deck Overlay | 1330
|  | Potato Creek 0.8 mi E of Co Rd L34 (EB / WB) | 16-78-680-050 | IMN-880-1(1)9--0E-78 | Bridge Rehabilitation | 1330
Ringgold | 169 | Middle Fork Grand River 5.3 mi S of IA 2 |  |  | Bridge Replacement | 1551
|  | Middle Fork Grand River 5.3 mi S of IA 2 | 15-80-169-010 | BRF-169-1(43)--38-80 | Bridge Replacement-PPCB | 1551
Ringgold | 169 | Stream 0.1 mi N of Missouri |  |  | Bridge Replacement |  |  | 920
|  | Stream 0.1 mi N of Missouri | 18-80-169-010 | BRFN-169-1(46)--39-80 | Bridge-Unspecified |  |  | 920
Shelby | 44 | Mosquito Creek 0.3 mi E of IA 191 |  |  | Bridge Deck Overlay |  |  | 1102
|  | Mosquito Creek 0.3 mi E of IA 191 | 18-83-044-010 | BRFN-044-2(48)--39-83 | Bridge Deck Overlay |  |  | 1102
Taylor | 148 | Middle Branch 102 River 2.8 mi S of Co Rd J20 |  |  | Bridge Deck Overlay |  |  |  | 300
|  | Middle Branch 102 River 2.8 mi S of Co Rd J20 | 19-87-148-010 | BRFN-148-1(37)--39-87 | Bridge Deck Overlay |  |  |  | 300
Union | 34 | W Jct US 169 in Afton |  |  | Grade and Pave | 376
|  | W Jct US 169 in Afton | 20-88-034-010 | HSIPX-034-4(47)--3L-88 | HMA Pavement - Grade and New | 376
Union | 169 | Abandoned RR 2.8 mi N of N Jct US 34 (REMOVE BRIDGE) |  |  | Grade and Pave |  |  | 1000
|  | Abandoned RR 2.8 mi N of N Jct US 34 | 18-88-169-010 | BRFN-169-2(25)--39-88 | PCC Pavement - Grade and Replace |  |  | 1000

## Line Items
PROJECT ESTIMATED COSTS X $1000
COUNTY | LOCATION | TYPE OF WORK | 2021 | 2022 | 2023 | 2024 | 2025
STATEWIDE | STATEWIDE INTERSTATE GUARDRAIL REPAIR | GUARDRAIL REPAIR | 865 | 865 | 865 | 865 | 865
STATEWIDE | STATEWIDE INTERSTATE LIGHTING | LIGHTING | 500 | 500 | 500 | 500 | 500
STATEWIDE | STATEWIDE INTERSTATE REST AREA MAINTENANCE | REST AREA IMPROVEMENT | 6000 | 6000 | 6000 | 6000 | 6000
STATEWIDE | STATEWIDE INTERSTATE SIGNING | TRAFFIC SIGNS | 1000 | 1000 | 1000 | 1000 | 1000
STATEWIDE | NON-INTERSTATE PAVEMENT MODERNIZATION | PAVEMENT REHAB |  | 115000 | 140000 | 145000 | 150000
STATEWIDE | STATEWIDE SAFETY SPECIFIC | PAVING | 1250 | 20166 | 25000 | 25000 | 25000
STATEWIDE | AMERICANS WITH DISABILITIES ACT | MISCELLANEOUS | 3000 | 3000 | 3000 | 3000 | 3000
STATEWIDE | CONSTRUCTION INDUSTRY TRAINING PROGRAM | MISCELLANEOUS | 1000 | 1000 | 1000 | 1000 | 1000
STATEWIDE | COOPERATIVE CITY/COUNTY/STATE HIGHWAY RESEARCH | MISCELLANEOUS | 1500 | 1500 | 1500 | 1500 | 1500
STATEWIDE | EMERGENCY & CONTINGENCY - U-STEP/C-STEP | MISCELLANEOUS | 6000 | 6000 | 6000 | 6000 | 6000
STATEWIDE | POST LETTING PROJECT COST | MISCELLANEOUS | 20000 | 20000 | 20000 | 20000 | 20000
STATEWIDE | PREVOCATIONAL TRAINING AND DBE SUPPORT SERVICES | MISCELLANEOUS | 360 | 360 | 360 | 360 | 360
STATEWIDE | SCENIC BYWAY PROGRAM | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
STATEWIDE | STATEWIDE CONSULTANT SERVICES | OUTSIDE SERVICES ENGINEERING | 85000 | 85000 | 85000 | 85000 | 85000
STATEWIDE | STATEWIDE CONTRACT MAINTENANCE | MISCELLANEOUS | 35350 | 35350 | 35350 | 35350 | 35350
STATEWIDE | STATEWIDE RAILROAD CROSSINGS | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
STATEWIDE | STATEWIDE ROADSIDE IMPROVEMENT | LANDSCAPING | 2500 | 2500 | 2500 | 2500 | 2500
STATEWIDE | STATEWIDE TRAFFIC CONTROL DEVICES | TRAFFIC SIGNS | 10000 | 10000 | 10000 | 10000 | 10000
STATEWIDE | STATEWIDE INTERSTATE PAVEMENT MAINTENANCE | PAVEMENT REHAB | 9500 | 9500 | 9500 | 9500 | 9500

## Legend
BLACK text - Five Year Program data
BLUE text - PSS data