## Five Year Program
2021 - 2025 Five Year Program
This information is valid for the date of Commission approval of 6/9/2020
PROJECT ESTIMATED COSTS X $1000
COUNTY | ROUTE | LOCATION | PSS PIN | PSS PROJECT NUMBER | TYPE OF WORK | 2021 | 2022 | 2023 | 2024 | 2025
Appanoose | 2 | Cooper Creek 1.5 mi W of IA 5 |  |  | Bridge Deck Overlay | 266
|  | Cooper Creek 1.5 mi W of IA 5 | 16-04-002-020 | BRFN-002-7(51)--39-04 | Bridge Deck Overlay | 266
Appanoose | 2 | Walnut Creek 0.8 mi E of Co Rd S70 |  |  | Bridge Deck Overlay |  | 253
|  | Walnut Creek 0.8 mi E of Co Rd S70 | 17-04-002-010 | BRFN-002-7(52)--39-04 | Bridge Deck Overlay |  | 253
Appanoose | 5 | Cooper Creek 1.5 mi N of IA 2 |  |  | Bridge Replacement |  |  | 2181
|  | Cooper Creek 1.5 mi N of IA 2 | 18-04-005-010 | BRF-005-1(74)--38-04 | Bridge-Unspecified |  |  | 2181
Appanoose | 5 | Ditch 0.6 mi S of Co Rd T30 |  |  | Bridge Replacement | 2452
|  | Ditch 0.6 mi S of Co Rd T30 | 16-04-005-020 | BRF-005-1(67)--38-04 | Bridge Replacement-CCS | 2452
[5 empty] | Right of Way | 5
|  | Ditch 0.6 mi S of Co Rd T30 | 16-04-005-020 | STPN-005-1(68)--2J-04 | Right Of Way | 5
Appanoose | 5 | N of N 18th St in Centerville to S of US 34 in Albia |  |  | Pavement Rehab | 8624
|  | N of N 18th St in Centerville to S of US 34 in Albia | 20-04-005-010 | NHSX-005-1(79)--3H-04 | HMA Resurfacing/Heater Scarification | 8624
Appanoose | 5 | North Creek 2.6 mi S of Co Rd T20 |  |  | Bridge Replacement |  |  | 4517
|  | North Creek 2.6 mi S of Co Rd T20 | 17-04-005-010 | BRF-005-1(71)--38-04 | RCB Culvert Replacement - Twin Box |  |  | 4517
Appanoose | 5 | Shoal Creek 2.8 mi N of Co Rd T20 |  |  | Bridge Replacement | 3959
|  | Shoal Creek 2.8 mi N of Co Rd T20 | 16-04-005-030 | BRF-005-1(69)--38-04 | Bridge Replacement-PPCB | 3959
[5 empty] | Right of Way | 5
|  | Shoal Creek 2.8 mi N of Co Rd T20 | 16-04-005-030 | STPN-005-1(70)--2J-04 | Right Of Way | 5
Clarke | 34 | I-35 to ECL of Osceola |  |  | Pavement Rehab | 2303
|  | I-35 to ECL of Osceola | 18-20-034-010 | NHSN-034-5(28)--2R-20 | HMA Resurfacing with Milling | 2303
Clarke | 35 | 0.5 mi N of US 34 to Warren Co (NB) |  |  | Pavement Rehab |  |  | 2746
|  | 0.5 mi N of US 34 to Warren County (NB) | 18-20-035-020 | IMN-035-2(470)34--0E-20 | HMA Resurfacing |  |  | 2746
Clarke | 35 | 0.5 mi N of US 34 to Warren Co (SB) |  |  | Pavement Rehab |  |  |  | 2204
|  | 0.5 mi N of US 34 to Warren County (SB) | 18-20-035-020 | IMN-035-2(471)34--0E-20 | HMA Resurfacing |  |  |  | 2204
Clarke | 69 | Pearl St to N of Shaw St in Osceola (state share) |  |  | Pavement Rehab | 399
|  | Pearl St to 300 ft N of Shaw St in Osceola | 18-20-069-010 | STPN-069-2(28)--2J-20 | HMA Resurfacing with Milling | 399
Clarke | 69 | White Breast Creek 4.9 mi S of US 34 |  |  | Bridge Deck Overlay | 384
|  | White Breast Creek 4.9 mi S of US 34 | 16-20-069-020 | BRFN-069-2(23)--39-20 | Bridge Deck Overlay | 384
Davis | 63 | Fox River 2.1 mi N of IA 2 |  |  | Bridge Replacement |  |  |  | 3335
|  | Fox River 2.1 mi N of IA 2 | 18-26-063-010 | BRF-063-1(91)--38-26 | Bridge-Unspecified |  |  |  | 3335
[5 empty] | Right of Way |  |  | 6
|  | Fox River 2.1 mi N of IA 2 | 18-26-063-010 | NHSN-063-1(92)--2R-26 | Right Of Way |  |  | 6
Davis | 63 | Middle Chequest Creek 0.2 mi N of 180th St |  |  | Bridge Widening |  |  |  |  | 950
|  | Middle Chequest Creek 0.2 mi N of 180th St | 20-26-063-010 | BRFN-063-1(94)--39-26 | Reconstruction - Bridge Deck Replacement |  |  |  |  | 950
Davis | 63 | N Fabius Creek 2.6 mi N of Missouri State Line |  |  | Traffic Signs |  |  | 20
|  | N Fabius Creek 2.6 mi N of Missouri State Line | 19-26-063-010 | ITS-063-1(93)--25-26 | ITS Equipment |  |  | 20
Davis | 63 | North Chequest Creek 2.6 mi N of Co Rd J3T |  |  | Culvert Repair |  |  |  |  | 950
|  | North Chequest Creek 2.6 mi N of Co Rd J3T | 20-26-063-020 | BRFN-063-1(96)--39-26 | RCB Culvert Replacement - Twin Box |  |  |  |  | 950
Davis | 63 | Soap Creek 0.9 mi S of Wapello Co |  |  | Bridge Replacement | 6824
|  | US 63 Over Soap Creek 0.9 Miles South Of The Wapello Co. Line | 08-26-063-010 | NHSX-063-1(68)--3H-26 | Bridge Replacement-PPCB | 6824
[5 empty] | Mitigation | 151
|  | Site (Wetland) Not Yet Identified | 08-26-063-010-01 | NHSN-063-1(90)--2R-26 | Wetland Bank Mitigation | 151
Davis | 202 | Missouri to IA 2 |  |  | Pipe Culverts | 590
|  | Missouri State Line to IA 2 | 20-26-202-010 | STPN-202-1(5)--2J-26 | Pipe Culverts | 590
[5 empty] | Right of Way | 6
|  | Missouri to IA 2 | 20-26-202-010 | STPN-202-1(6)--2J-26 | Right Of Way | 6
Decatur | 2 | McGruder Creek 1.5 mi E of E Jct US 69 |  |  | Bridge Deck Overlay |  |  |  |  | 190
|  | McGruder Creek 1.5 mi E of E Jct US 69 | 20-27-002-010 | BRFN-002-5(51)--39-27 | Bridge Deck Overlay |  |  |  |  | 190
Decatur | 35 | 310th St 2.5 mi S of US 69 (NB & SB) |  |  | Bridge Deck Overlay |  |  | 937
|  | 310th St 2.5 mi S of US 69 (NB & SB) | 18-27-035-010 | IMN-035-1(187)2--0E-27 | Bridge Deck Overlay |  |  | 937
Decatur | 35 | Co Rd R30 1.0 mi S of IA 2 |  |  | Bridge Deck Overlay |  |  |  |  | 684
|  | Co Rd R30 1.0 mi S of IA 2 | 20-27-035-030 | IMN-035-1(193)12--0E-27 | Bridge Deck Overlay |  |  |  |  | 684
Decatur | 35 | Missouri to Polk Co |  |  | Guardrail Repair | 100 | 100 | 100 | 100 | 100
|  | Missouri to Polk Co (On-Call) | 14-27-035-010 | IMN-035-1(178)0--0E-27 | Guardrail Repair | 100
|  | Missouri to Polk Co (On-Call) | 14-27-035-010 | IMN-035-1(180)0--0E-27 | Guardrail Repair |  | 100
|  | Missouri to Polk Co (On-Call) | 14-27-035-010 | IMN-035-1(184)0--0E-27 | Guardrail Repair |  |  | 100
|  | Missouri to Polk Co (On-Call) | 14-27-035-010 | IMN-035-1(188)0--0E-27 | Guardrail Repair |  |  |  | 100
|  | Missouri to Polk Co (On-Call) | 14-27-035-010 | IMN-035-1(190)0--0E-27 | Guardrail Repair |  |  |  |  | 100
Decatur | 35 | S of Rest Area to S of IA 2 (SB) |  |  | Erosion Control | 350
|  | Missouri to Clarke Co (NB/SB) | 12-27-035-010 | IMN-035-1(192)0--0E-27 | Erosion Control | 350
Decatur | 69 | 1.6 mi S of Co Rd J66 |  |  | Pipe Culverts | 408
|  | 1.6 mi S of Co Rd J66 | 19-27-069-010 | STPN-069-1(54)--2J-27 | Pipe Culverts | 408
[5 empty] | Right of Way | 5
|  | 1.6 mi S of Co Rd J66 | 19-27-069-010 | STPN-069-1(55)--2J-27 | Right Of Way | 5
Decatur | 69 | 1.8 mi S of Co Rd J66 |  |  | Ditch Improvement | 221
|  | 1.8 mi S of Co Rd J66 | 18-27-069-020 | STPN-069-1(52)--2J-27 | Ditch Improvement | 221
[5 empty] | Right of Way | 20
|  | 1.8 mi S of Co Rd J66 | 18-27-069-020 | STPN-069-1(53)--2J-27 | Right Of Way | 20
Decatur | 69 | Dickersons Branch 1.1 mi S of Co Rd J66 |  |  | Right of Way | 2
|  | Dickersons Branch 1.1 mi S of Co Rd J66 | 18-27-069-010 | STPN-069-1(51)--2J-27 | Right Of Way | 2
[5 empty] | Rip Rap | 36
|  | Dickersons Branch 1.1 mi S of Co Rd J66 | 18-27-069-010 | STPN-069-1(50)--2J-27 | Revetment | 36
Des Moines | 34 | 8th St 1.8 mi E of US 61 in Burlington |  |  | Bridge Deck Overlay |  |  |  | 400
|  | 8th St 1.8 mi E of US 61 in Burlington | 19-29-034-010 | BRFN-034-9(234)--39-29 | Bridge Deck Overlay |  |  |  | 400
Des Moines | 34 | Curran St 0.8 mi E of US 61 in Burlington |  |  | Bridge Rehabilitation |  |  |  | 500
|  | Curran St 0.8 mi E of US 61 in Burlington | 19-29-034-020 | BRFN-034-9(235)--39-29 | Bridge Rehabilitation |  |  |  | 500
Des Moines | 34 | Mississippi River in Burlington (State Share) |  |  | Bridge Cleaning | 35 | 35 | 35 | 35 | 35
|  | Mississippi River in Burlington (state share) | 16-29-034-010 | BRFN-034-9(223)--39-29 | Bridge Cleaning | 35
|  | Mississippi River in Burlington (state share) | 16-29-034-010 | BRFN-034-9(226)--39-29 | Bridge Cleaning |  | 35
|  | Mississippi River in Burlington (state share) | 16-29-034-010 | BRFN-034-9(229)--39-29 | Bridge Cleaning |  |  | 35
|  | Mississippi River in Burlington (state share) | 16-29-034-010 | BRFN-034-9(232)--39-29 | Bridge Cleaning |  |  |  | 35
|  | Mississippi River in Burlington | 16-29-034-010 | BRFN-034-9(237)--39-29 | Bridge Cleaning |  |  |  |  | 35
Des Moines | 34 | N Central Ave in Burlington |  |  | Bridge Deck Overlay |  |  | 1307
|  | N Central Ave in Burlington | 18-29-034-020 | BRFN-034-9(231)--39-29 | Bridge Deck Overlay |  |  | 1307
Des Moines | 34 | W Burlington Ave 0.5 mi W of US 61 (EB) |  |  | Bridge Deck Overlay |  |  |  |  | 640
|  | W Burlington Ave 0.5 mi W of US 61 (EB) | 20-29-034-010 | BRFN-034-9(238)--39-29 | Bridge Deck Overlay |  |  |  |  | 640
Des Moines | 34 | W Burlington Ave 0.5 mi W of US 61 (WB) |  |  | Bridge Rehabilitation |  |  |  |  | 320
|  | W Burlington Ave 0.5 mi W of US 61 (WB) | 20-29-034-020 | BRFN-034-9(239)--39-29 | Bridge Repair |  |  |  |  | 320
Des Moines | 34 | WB Ramp to US 34 0.4 mi W of IL in Burlington |  |  | Bridge Rehabilitation |  |  |  | 1000
|  | WB Ramp to US 34 0.4 mi W of IL in Burlington | 19-29-034-030 | BRFN-034-9(236)--39-29 | Bridge Rehabilitation |  |  |  | 1000
Des Moines | 61 | Memorial Park Rd in Burlington to S of 210th St |  |  | Bridge Replacement | 1924
|  | Flint Creek 0.6 mi N of Memorial Park Rd (NB) | 97-29-061-010-01 | NHSX-061-2(93)--3H-29 | Bridge Replacement-PPCB | 1924
[5 empty] | Erosion Control |  | 1709
|  | Memorial Park Rd in Burlington to S of 210th St | 97-29-061-010-01 | NHSN-061-2(74)--2R-29 | Erosion Control |  | 1709
[5 empty] | Grade and Pave | 25016
|  | Memorial Park Rd in Burlington to S of 210th St | 97-29-061-010-01 | NHSX-061-2(69)--3H-29 | PCC Pavement - Grade and Replace | 25016
[5 empty] | Pavement Rehab |  | 960
|  | Memorial Park Rd in Burlington to S of 210th St (TJ to Des Moines Co) | 97-29-061-010-01 | TJ-061-2(120)--2M-29 | HMA Resurfacing |  | 960
[5 empty] | Traffic Signs | 300
|  | Memorial Park Rd in Burlington to S of 210th St | 97-29-061-010-01 | NHSX-061-2(73)--3H-29 | Traffic Signs | 300
Des Moines | 61 | N of Mediapolis to 0.5 mi N of IA 78 |  |  | Bridge New |  |  |  |  | 2833
|  | IA 78 5.6 mi N of Mediapolis | 97-29-061-010-03 | NHSX-061-3(79)--3H-58 | Bridge New-PPCB |  |  |  |  | 2833
[5 empty] | Culvert New |  |  |  | 3117
|  | 0.46 mi N of N Jct Co Rd H28 / 260th St | 97-29-061-010-03 | NHSX-061-2(119)--3H-29 | RCB Culvert New - Triple Box |  |  |  | 2551
|  | N of Mediapolis to 0.5 mi N of IA 78 | 97-29-061-010-03 | NHSX-061-2(63)--3H-29 | RCB Culvert New - Single Box |  |  |  | 566
[5 empty] | Grading |  |  |  | 12802
|  | N of Mediapolis to 0.5 mi N of IA 78 | 97-29-061-010-03 | NHSX-061-2(66)--3H-29 | Grading |  |  |  | 12802
[5 empty] | Mitigation |  |  |  | 2245
|  | Woodland Mitigation Site for Section 3 Not Yet Identified | 97-29-061-010-05 | NHSN-061-2(101)--2R-29 | Woodland Mitigation |  |  |  | 1250
|  | Stream Mitigation Site for Section 3 Not Yet Identified | 97-29-061-010-05 | NHSN-061-2(102)--2R-29 | Stream Mitigation |  |  |  | 335
|  | Wetland Mitigation Site for Section 3 Not Yet Identified | 97-29-061-010-05 | NHSN-061-2(103)--2R-29 | Wetland Mitigation |  |  |  | 660
[5 empty] | Right of Way |  |  | 2400
|  | N of Mediapolis to 1 mi N of IA 78 | 97-29-061-010-03 | NHSN-061-2(92)--2R-29 | Right Of Way |  |  | 2400
Des Moines | 61 | S of 210th St to N of Mediapolis |  |  | Bridge New |  | 3574
|  | Co Rd H38 N of Mediapolis | 97-29-061-010-02 | NHSX-061-2(72)--3H-29 | Bridge New-PPCB |  | 3574
[5 empty] | Erosion Control |  |  |  |  | 187
|  | S of 210th St to N of Mediapolis | 97-29-061-010-02 | NHSN-061-2(109)--2R-29 | Erosion Control |  |  |  |  | 187
[5 empty] | Grading |  | 13341
|  | S of 210th St to N of Mediapolis | 97-29-061-010-02 | NHSX-061-2(65)--3H-29 | Grading |  | 13341
[5 empty] | Lighting |  |  |  | 75
|  | S of 210th St to N of Mediapolis | 97-29-061-010-02 | NHSX-061-2(108)--3H-29 | Lighting |  |  |  | 75
[5 empty] | Paving |  |  |  | 26553
|  | S of 210th St to N of Mediapolis | 97-29-061-010-02 | NHSX-061-2(106)--3H-29 | Unknown Pavement - New |  |  |  | 26553
[5 empty] | Right of Way | 2200
|  | S of 210th St to N of Mediapolis | 97-29-061-010-02 | NHSN-061-2(91)--2R-29 | Right Of Way | 2200
[5 empty] | Traffic Signs |  |  |  | 225
|  | S of 210th St to N of Mediapolis | 97-29-061-010-02 | NHSX-061-2(107)--3H-29 | Traffic Signs |  |  |  | 225
Des Moines | 61 | US 34 in Burlington |  |  | Bridge Deck Overlay |  |  |  |  | 1270
|  | US 34 in Burlington | 20-29-061-020 | BRFN-061-2(129)--39-29 | Bridge Deck Overlay |  |  |  |  | 1270
Henry | 34 | E of Grand Ave at N Jct US 218 (WB) |  |  | Slope Improvement | 27
|  | E of Grand Ave at N Jct US 218 (WB) | 19-44-034-020 | NHSN-034-9(233)--2R-44 | Slide Repair | 27
Henry | 78 | Stream 0.3 mi W of E Jct Co Rd W66 |  |  | Bridge Replacement |  |  |  |  | 950
|  | Stream 0.3 mi W of E Jct Co Rd W66 | 20-44-078-010 | BRFN-078-4(25)--39-44 | Bridge-Unspecified |  |  |  |  | 950
Henry | 218 | 1.0 mi N of Co Rd J20 (NB) |  |  | Right of Way | 1
|  | 0.97 mi N of Co Rd J20 (NB) | 19-44-218-010 | NHSN-218-2(153)--2R-44 | Right Of Way | 1
[5 empty] | Slope Improvement | 216
|  | 0.97 mi N of Co Rd J20 (NB) | 19-44-218-010 | NHSN-218-2(151)--2R-44 | Slide Repair | 216
Henry | 218 | 3.1 mi N of Co Rd J20 (NB) |  |  | Right of Way | 6
|  | 3.1 mi N of Co Rd J20 (NB) | 19-44-218-020 | NHSN-218-2(154)--2R-44 | Right Of Way | 6
[5 empty] | Slope Improvement | 42
|  | 3.1 mi N of Co Rd J20 (NB) | 19-44-218-020 | NHSN-218-2(152)--2R-44 | Slide Repair | 42
Henry | 218 | North Fish Creek 1.1 mi N of Co Rd J20 (NB) |  |  | Bridge Replacement |  |  |  | 1000
|  | North Fish Creek 1.1 mi N of Co Rd J20 (NB) | 19-44-218-030 | BRFN-218-2(155)--39-44 | Bridge-Unspecified |  |  |  | 1000
Henry | 218 | South Fish Creek 0.7 mi N of Co Rd J20 (NB) |  |  | Bridge Replacement |  |  |  |  | 2030
|  | South Fish Creek 0.7 mi N of Co Rd J20 (NB) | 20-44-218-020 | BRF-218-2(158)--38-44 | Bridge-Unspecified |  |  |  |  | 2030
Jefferson | 1 | Big Cedar Creek 2.8 mi S of US 34 |  |  | Bridge Rehabilitation |  |  | 960
|  | Big Cedar Creek 2.8 mi S of US 34 | 18-51-001-010 | BRFN-001-2(37)--39-51 | Bridge Rehabilitation |  |  | 960
Jefferson | 1 | Middle Walnut Creek 3.1 mi S of S Jct IA 78 |  |  | Bridge Deck Overlay |  | 330
|  | Middle Walnut Creek 3.1 mi S of S Jct IA 78 | 17-51-001-010 | BRFN-001-2(34)--39-51 | Bridge Deck Overlay |  | 330
Jefferson | 1 | S of Libertyville Rd to Fillmore Ave in Fairfield |  |  | Grade and Pave |  |  | 3658
|  | S of Libertyville Rd to Fillmore Ave in Fairfield | 17-51-001-020 | STBG-SWAP-2465(35)--SG-51 | PCC Pavement Widening |  |  | 3658
[5 empty] | Right of Way |  |  | 5
|  | S of Libertyville Rd to Fillmore Ave in Fairfield | 17-51-001-020 | NHSN-001-2(36)--2R-51 | Right Of Way |  |  | 5
Keokuk | 21 | IA 92 to NCL of What Cheer |  |  | Pavement Rehab | 3002
|  | IA 92 to NCL of What Cheer | 20-54-021-010 | STP-021-1(42)--2C-54 | HMA Resurfacing/Cold-in-Place Recycling | 3002
[5 empty] | Right of Way | 5
|  | IA 92 to NCL of What Cheer | 20-54-021-010 | STPN-021-1(43)--2J-54 | Right Of Way | 5
Keokuk | 78 | DME RR 8.8 mi E of IA 149 |  |  | Bridge Replacement |  | 8448
|  | DME RR 8.8 mi E of IA 149 | 17-54-078-010 | BRF-078-1(20)--38-54 | Bridge and Approaches-Steel Girder |  | 8448
[5 empty] | Right of Way |  | 10
|  | DME RR 8.8 mi E of IA 149 | 17-54-078-010 | STPN-078-1(21)--2J-54 | Right Of Way |  | 10
Keokuk | 78 | Richland Creek 5.8 mi E of IA 149 |  |  | Bridge Replacement |  |  | 1038
|  | Richland Creek 5.8 mi E of IA 149 | 18-54-078-010 | BRFN-078-1(22)--39-54 | Bridge-Unspecified |  |  | 1038
Keokuk | 92 | Clear Creek 2.5 mi W of Co Rd W15 |  |  | Bridge Deck Overlay | 338
|  | Clear Creek 2.5 mi W of Co Rd W15 | 16-54-092-040 | BRFN-092-8(35)--39-54 | Bridge Deck Overlay | 338
Keokuk | 92 | E Jct IA 149 to Co Rd V67 |  |  | Pavement Rehab | 3586
|  | E Jct IA 149 to Co Rd V67 | 20-54-092-010 | NHSX-092-8(40)--3H-54 | HMA Resurfacing | 3586
Keokuk | 92 | German Creek 3.0 mi E of E Jct IA 149 |  |  | Bridge Deck Overlay |  |  |  |  | 260
|  | German Creek 3.0 mi E of E Jct IA 149 | 20-54-092-020 | BRFN-092-8(41)--39-54 | Bridge Deck Overlay |  |  |  |  | 260
Keokuk | 92 | IA 21 and Co Rd V33 Intersections |  |  | Grade and Pave |  |  | 6285
|  | IA 21 and Co Rd V33 Intersections | 16-54-092-030 | NHSN-092-8(36)--2R-54 | PCC Pavement - Grade and Replace |  |  | 6285
[5 empty] | Right of Way |  |  | 5
|  | IA 21 and Co Rd V33 Intersections | 16-54-092-030 | NHSN-092-8(39)--2R-54 | Right Of Way |  |  | 5
Lee | 2 | 3.5 mi E of Co Rd J56 |  |  | Right of Way |  |  | 10
|  | 3.5 mi E of Co Rd J56 | 19-56-002-020 | STPN-002-9(42)--2J-56 | Right Of Way |  |  | 10
[5 empty] | Slope Improvement |  |  | 118
|  | 3.5 mi E of Co Rd J56 | 19-56-002-020 | STPN-002-9(41)--2J-56 | Slide Repair |  |  | 118
Lee | 2 | Lick Creek 4.3 mi E of IA 81 |  |  | Bridge Replacement | 1631
|  | Lick Creek 4.3 mi E of IA 81 | 17-56-002-010 | BRFN-002-9(34)--39-56 | Bridge New-PPCB | 1631
Lee | 2 | Sugar Creek 1.8 mi W of US 218 |  |  | Bridge Replacement | 2964
|  | Sugar Creek 1.8 mi W of US 218 | 16-56-002-010 | BRF-002-9(32)--38-56 | Bridge Replacement-PPCB | 2964
[5 empty] | Right of Way | 10
|  | Sugar Creek 1.8 mi W of US 218 | 16-56-002-010 | STPN-002-9(33)--2J-56 | Right Of Way | 10
Lee | 136 | Mississippi River in Keokuk (State Share) |  |  | Bridge Cleaning | 20 | 20 | 20 | 20 | 20
|  | Mississippi River in Keokuk | 16-56-019-010 | BRFN-019-1(43)--39-56 | Bridge Cleaning | 20
|  | Mississippi River in Keokuk | 16-56-019-010 | BRFN-019-1(44)--39-56 | Bridge Cleaning |  | 20
|  | Mississippi River in Keokuk | 16-56-019-010 | BRFN-019-1(46)--39-56 | Bridge Cleaning |  |  | 20
|  | Mississippi River in Keokuk | 16-56-019-010 | BRFN-019-1(47)--39-56 | Bridge Cleaning |  |  |  | 20
|  | Mississippi River in Keokuk | 16-56-019-010 | BRFN-019-1(51)--39-56 | Bridge Cleaning |  |  |  |  | 20
Lee | 136 | Mississippi River in Keokuk (State Share) |  |  | Bridge Deck Overlay |  |  |  | 5000
|  | Mississippi River in Keokuk | 15-56-019-020 | BRFN-019-1(41)--39-56 | Bridge Deck Overlay |  |  |  | 5000
Lee | 136 | Soap Creek and BNSF RR 1.8 mi E of US 61 in Keokuk |  |  | Bridge Deck Overlay |  |  |  | 1000
|  | Soap Creek and BNSF RR 1.8 mi E of US 61 in Keokuk | 19-56-019-020 | BRFN-019-1(50)--39-56 | Bridge Deck Overlay |  |  |  | 1000
Lee | 218 | NB ON RAMP TO IA 27 |  |  | Grade and Pave |  | 300
|  | US 218 NB to IA 27 On Ramp | 20-56-218-010 | NHSN-218-1(80)--2R-56 | PCC Pavement - Grade and New |  | 300
[5 empty] | Right of Way |  | 5
|  | US 218 NB to IA 27 On Ramp | 20-56-218-010 | NHSN-218-1(81)--2R-56 | Right Of Way |  | 5
Louisa | 61 | 0.5 mi N of IA 78 to 2.0 mi S of IA 92 |  |  | Right of Way |  |  |  |  | 5800
|  | 0.5 mi N of IA 78 to 130th St 2 mi S of IA 92 | 11-58-061-010 | NHSN-061-3(62)--2R-58 | Right Of Way |  |  |  |  | 5800
Louisa | 78 | Honey Creek 1.8 mi W of US 61 |  |  | Bridge Replacement |  | 2436
|  | Honey Creek 1.8 mi W of US 61 | 17-58-078-010 | BRFN-078-5(5)--39-58 | RCB Culvert Replacement - Triple Box |  | 2436
[5 empty] | Right of Way |  | 10
|  | Honey Creek 1.8 mi W of US 61 | 17-58-078-010 | STPN-078-5(6)--2J-58 | Right Of Way |  | 10
Louisa | 92 | Little Indian Creek 1.9 mi W of S Jct US 61 |  |  | Bridge Deck Overlay |  | 425
|  | Little Indian Creek 1.9 mi W of S Jct US 61 | 17-58-092-010 | BRFN-092-9(152)--39-58 | Bridge Deck Overlay |  | 425
Lucas | 14 | 1.2 mi N of N Jct Co Rd H50 |  |  | Culvert Replacement | 563
|  | 1.2 mi N of N Jct Co Rd H50 (MP 14.6) | 18-59-014-010 | STPN-014-2(40)--2J-59 | RCB Culvert Replacement - Single Box | 563
[5 empty] | Right of Way | 2
|  | 1.2 mi N of N Jct Co Rd H50 (MP 14.6) | 18-59-014-010 | STPN-014-2(41)--2J-59 | Right Of Way | 2
Lucas | 34 | Little White Breast Creek 2.5 mi W of Co Rd S56 |  |  | Bridge Deck Overlay |  |  | 312
|  | Little White Breast Creek 2.5 mi W of Co Rd S56 | 18-59-034-010 | BRFN-034-6(98)--39-59 | Bridge Deck Overlay |  |  | 312
Lucas | 34 | Stream 2.1 mi E of E Jct US 65 |  |  | Bridge Replacement |  | 2046
|  | Stream 2.1 mi E of E Jct US 65 | 17-59-034-010 | BRFN-034-6(95)--39-59 | Bridge and Approaches-CCS |  | 2046
[5 empty] | Right of Way |  | 10
|  | Stream 2.1 mi E of E Jct US 65 | 17-59-034-010 | NHSN-034-6(96)--2R-59 | Right Of Way |  | 10
Mahaska | 23 | Tributary of Cedar Creek 0.8 mi N of Co Rd T67 |  |  | Bridge Replacement |  |  | 1057
|  | Tributary of Cedar Creek 0.8 mi N of Co Rd T67 | 18-62-023-010 | BRFN-023-1(48)--39-62 | Bridge-Unspecified |  |  | 1057
Mahaska | 63 | NW Bypass of Oskaloosa |  |  | Bridge New |  |  |  |  | 3162
|  | NW Bypass of Oskaloosa | 13-62-063-020 | NHSX-063-3(96)--3H-62 | Bridge New-PPCB |  |  |  |  | 3162
[5 empty] | Culvert New |  |  |  | 2037
|  | NW Bypass of Oskaloosa | 13-62-063-020 | NHSX-063-3(97)--3H-62 | RCB Culvert-Unspecified |  |  |  | 2037
[5 empty] | Grading |  |  |  | 14152
|  | NW Bypass of Oskaloosa | 13-62-063-020 | NHSX-063-3(95)--3H-62 | Grading |  |  |  | 14152
[5 empty] | Mitigation |  |  |  | 500
|  | Site (Wetland) Not Yet Identified | 13-62-063-020-01 | NHSN-063-3(102)--2R-62 | Wetland Mitigation |  |  |  | 250
|  | Site (Stream) Not Yet Identified | 13-62-063-020-01 | NHSN-063-3(103)--2R-62 | Stream Mitigation |  |  |  | 250
[5 empty] | Right of Way |  |  | 5900
|  | NW Bypass of Oskaloosa | 13-62-063-020 | NHSN-063-3(94)--2R-62 | Right Of Way |  |  | 5900
Mahaska | 92 | Muchakinock Creek 1.3 mi W of IA 163 |  |  | Bridge Replacement | 3899
|  | Muchakinock Creek 1.3 mi W of IA 163 | 13-62-092-010 | BRF-092-7(45)--38-62 | Bridge Replacement-Steel Girder | 3899
[5 empty] | Mitigation | 26
|  | C&W Hunter Wetland Mitigation Bank for Mahaska Co IA 92 Muchakinock Cr Bridge Replacement BRFN-092-7(45)--39-6 | 13-62-092-010-01 | NHSN-092-7(54)--2R-62 | Wetland Bank Mitigation | 26
Mahaska | 92 | North Skunk River 2.6 mi E of E Jct Co Rd V13 |  |  | Bridge Replacement |  | 6363
|  | North Skunk River 2.2 mi E of E Jct Co Rd V13 | 17-62-092-010 | BRF-092-7(52)--38-62 | Bridge and Approaches-PPCB |  | 6363
[5 empty] | Right of Way |  | 10
|  | North Skunk River 2.6 mi E of E Jct Co Rd V13 | 17-62-092-010 | NHSN-092-7(53)--2R-62 | Right Of Way |  | 10
Marion | 5 | S Jct IA 92 |  |  | Bridge Deck Overlay |  |  | 1674
|  | S Jct IA 92 | 18-63-005-010 | BRFN-005-3(68)--39-63 | Bridge Deck Overlay |  |  | 1674
Marion | 5 | Walnut Creek 0.9 mi N of Co Rd G76 |  |  | Bridge Replacement |  |  |  |  | 2394
|  | Walnut Creek 0.9 mi N of Co Rd G76 | 18-63-005-020 | BRFN-005-3(69)--39-63 | Bridge-Unspecified |  |  |  |  | 2394
Marion | 5 | White Breast Creek 2.7 mi N of IA 14 (NB) |  |  | Bridge Deck Overlay |  |  |  |  | 1140
|  | White Breast Creek 2.7 mi N of IA 14 (NB) | 20-63-005-020 | BRFN-005-3(71)--39-63 | Bridge Deck Overlay |  |  |  |  | 1140
Marion | 14 | 0.6 mi S of Co Rd G18 |  |  | Pipe Culverts | 70
|  | 0.6 mi S of Co Rd G18 | 19-63-014-010 | NHSN-014-3(54)--2R-63 | Pipe Culverts | 70
[5 empty] | Right of Way | 5
|  | 0.6 mi S of Co Rd G18 | 19-63-014-010 | NHSN-014-3(55)--2R-63 | Right Of Way | 5
Marion | 14 | Brush Creek 0.2 mi S of Co Rd G28 |  |  | Bridge Replacement |  |  |  | 3500
|  | Brush Creek 0.2 mi S of Co Rd G28 | 19-63-014-030 | BRF-014-3(56)--38-63 | Bridge-Unspecified |  |  |  | 3500
Marion | 14 | Des Moines River 1.2 mi N of Co Rd G40 |  |  | Bridge Deck Overlay |  |  |  |  | 8860
|  | Des Moines River 1.2 mi N of Co Rd G40 | 20-63-014-010 | BRF-014-3(60)--38-63 | Bridge Deck Overlay |  |  |  |  | 8860
Marion | 92 | Old Highway 92 3.9 mi E of E Jct IA 5 |  |  | Bridge Deck Overlay |  |  |  | 1000
|  | Old Highway 92 3.9 mi E of E Jct IA 5 | 19-63-092-010 | BRFN-092-6(38)--39-63 | Bridge Deck Overlay |  |  |  | 1000
Monroe | 5 | 0.1 mi S of Co Rd T19 |  |  | Pipe Culverts | 273
|  | 0.1 mi S of Co Rd T19 | 19-68-005-010 | NHSN-005-2(44)--2R-68 | Pipe Culverts | 273
[5 empty] | Right of Way | 6
|  | 0.1 mi S of Co Rd T19 | 19-68-005-010 | NHSN-005-2(45)--2R-68 | Right Of Way | 6
Monroe | 34 | BNSF RR 4.5 mi W of IA 5 |  |  | Bridge Deck Overlay |  |  | 443
|  | BNSF RR 4.5 mi W of IA 5 | 18-68-034-010 | BRFN-034-6(99)--39-68 | Bridge Deck Overlay |  |  | 443
Muscatine | 6 | 1.2 mi E of Co Rd X46 to 1.1 mi W of IA 38 |  |  | Right of Way | 3
|  | 1.2 mi E of Co Rd X46 to 1.1 mi W of IA 38 (3 Locations) | 19-70-006-010 | STPN-006-8(42)--2J-70 | Right Of Way | 3
[5 empty] | Slope Improvement | 268
|  | 1.2 mi E of Co Rd X46 to 1.1 mi W of IA 38 (3 Locations) | 19-70-006-010 | STPN-006-8(41)--2J-70 | Slide Repair | 268
Muscatine | 6 | IAIS RR 1.2 mi E of IA 38 |  |  | Bridge Deck Overlay |  |  | 513
|  | IAIS RR 1.2 mi E of IA 38 | 18-70-006-010 | BRFN-006-8(39)--39-70 | Bridge Deck Overlay |  |  | 513
Muscatine | 6 | Sugar Creek 1.7 mi W of W Jct IA 38 |  |  | Bridge Deck Overlay |  |  | 855
|  | Sugar Creek 1.7 mi W of W Jct IA 38 | 18-70-006-020 | BRFN-006-8(40)--39-70 | Bridge Deck Overlay |  |  | 855
Muscatine | 6 | Sugar Creek 2.3 mi W of IA 38 |  |  | Bridge Deck Overlay |  | 184
|  | Mud Creek 2.3 mi W of IA 38 | 17-70-006-010 | BRFN-006-8(38)--39-70 | Bridge Deck Overlay |  | 184
Muscatine | 22 | Wapsinonoc Creek 1.6 mi E of W Jct IA 70 |  |  | Bridge Deck Overlay |  |  |  | 600
|  | Wapsinonoc Creek 1.6 mi E of W Jct IA 70 | 19-70-022-010 | BRFN-022-4(79)--39-70 | Bridge Deck Overlay |  |  |  | 600
Muscatine | 92 | Mississippi River in Muscatine (State Share) |  |  | Bridge Cleaning | 25 | 25 | 25 | 25 | 25
|  | Mississippi River in Muscatine | 16-70-092-010 | BRFN-092-9(149)--39-70 | Bridge Cleaning | 25
|  | Mississippi River in Muscatine | 16-70-092-010 | BRFN-092-9(151)--39-70 | Bridge Cleaning |  | 25
|  | Mississippi River in Muscatine | 16-70-092-010 | BRFN-092-9(155)--39-70 | Bridge Cleaning |  |  | 25
|  | Mississippi River in Muscatine | 16-70-092-010 | BRFN-092-9(156)--39-70 | Bridge Cleaning |  |  |  | 25
|  | Mississippi River in Muscatine | 16-70-092-010 | BRFN-092-9(159)--39-70 | Bridge Cleaning |  |  |  |  | 25
Muscatine | 92 | Mississippi River in Muscatine (State share) |  |  | Bridge Rehabilitation |  |  |  | 200
|  | Mississippi River in Muscatine | 19-70-092-010 | BRFN-092-9(157)--39-70 | Bridge Repair |  |  |  | 200
Union | 34 | Four Mile Creek 2.0 mi E of E Jct US 169 |  |  | Bridge Deck Overlay |  |  |  | 600
|  | Four Mile Creek 2 mi E of E Jct US 169 | 19-88-034-010 | BRFN-034-4(46)--39-88 | Bridge Deck Overlay |  |  |  | 600
Van Buren | 1 | 0.1 mi N of Franklin St in Keosauqua |  |  | Culvert Replacement | 730
|  | 0.1 mi N of Franklin St in Keosauqua | 18-89-001-010 | STPN-001-1(32)--2J-89 | Structures - Miscellaneous | 730
[5 empty] | Right of Way | 3
|  | 0.1 mi N of Franklin St in Keosauqua | 18-89-001-010 | STPN-001-1(33)--2J-89 | Right Of Way | 3
Van Buren | 1 | Little Lick Creek 1.2 mi N of S Jct IA 16 |  |  | Bridge Replacement |  |  | 4408
|  | Little Lick Creek 1.2 mi N of S Jct IA 16 | 18-89-001-020 | BRF-001-1(34)--38-89 | Structures - Miscellaneous |  |  | 4408
Van Buren | 2 | Co Rd W40 to Park St in Donnellson |  |  | Pave Shoulder | 1000
|  | Co Rd W40 to Park St in Donnellson | 20-89-002-010 | HSIPX-002-9(44)--3L-89 | HMA Paved Shoulder - New | 1000
[5 empty] | Pavement Rehab | 1711
|  | Co Rd W40 to Park St in Donnellson | 20-89-002-010 | STP-002-9(43)--2C-89 | Microsurfacing | 1711
[5 empty] | Right of Way | 10
|  | Co Rd W40 to Park St in Donnellson | 20-89-002-010 | STPN-002-9(45)--2J-89 | Right Of Way | 10
Van Buren | 2 | Fox River 1.5 mi E of Co Rd V64 |  |  | Bridge Rehabilitation |  |  |  | 1214
|  | Fox River 1.5 mi E of Co Rd V64 | 19-89-002-010 | BRFN-002-9(40)--39-89 | Reconstruction - Bridge Deck Replacement |  |  |  | 1214
Van Buren | 81 | Missouri to 0.3 mi S of IA 2 |  |  | Pavement Rehab | 126
|  | Missouri State Line to 0.3 mi S of IA 2 | 20-89-081-010 | STPN-081-0(7)--2J-89 | Microsurfacing | 126
Wapello | 34 | BNSF RR 1.2 E of W Jct US 63 in Ottumwa (EB & WB) |  |  | Bridge Rehabilitation |  |  |  | 2994
|  | BNSF RR 1.2 E of W Jct US 63 in Ottumwa (EB/WB) | 19-90-034-010 | BRFN-034-7(150)--39-90 | Reconstruction - Bridge Deck Replacement |  |  |  | 2994
Wapello | 34 | Bardell St 0.5 mi E of IA 149 in Ottumwa (WB) |  |  | Bridge Deck Overlay |  | 262
|  | Bardell St 0.5 mi E of IA 149 in Ottumwa (WB) | 17-90-034-030 | BRFN-034-7(145)--39-90 | Bridge Deck Overlay |  | 262
Wapello | 34 | Bear Creek 1.2 mi W of Co Rd H35 |  |  | Bridge Deck Overlay |  | 489
|  | Bear Creek 1.2 mi W of Co Rd H35 | 17-90-034-020 | BRFN-034-7(144)--39-90 | Bridge Deck Overlay |  | 489
Wapello | 34 | E Main St 1.4 mi E of W Jct US 63 in Ottumwa |  |  | Bridge Deck Overlay | 252
|  | E Main St 1.4 mi E of W Jct US 63 in Ottumwa | 16-90-034-010 | BRFN-034-7(142)--39-90 | Bridge Deck Overlay | 252
Wapello | 34 | South Avery Creek 0.7 mi E of Co Rd T61 |  |  | Bridge Deck Overlay |  |  | 645
|  | South Avery Creek 0.7 mi E of Co Rd T61 | 18-90-034-020 | BRFN-034-7(148)--39-90 | Bridge Deck Overlay |  |  | 645
Wapello | 63 | Little Soap Creek 1.9 miles N of Davis Co |  |  | Bridge Rehabilitation |  |  | 1777
|  | Little Soap Creek 1.9 miles N of Davis Co | 10-90-063-010 | NHSX-063-2(137)--3H-90 | Reconstruction - Bridge Deck Replacement |  |  | 1777
Wapello | 63 | Village Creek 3.1 mi S of US 34 |  |  | Bridge Widening |  |  | 1902
|  | Village Creek 3.1 mi S of US 34 | 15-90-063-010 | BRF-063-2(161)--38-90 | Reconstruction - Bridge Widening |  |  | 1902
Warren | 35 | 1.8 miles S of Co Rd G14 to 0.25 mi N of Adams St (NB) |  |  | Grade and Pave |  |  |  |  | 23465
|  | 1.8 mi S of Co Rd G14 to 0.25 mi N of Adams St (NB) | 00-91-035-030-04 | IM-NHS-035-2(467)63--03-91 | Unknown Pavement - Grade and Replace |  |  |  |  | 23465
[5 empty] | Traffic Signs |  |  |  |  | 400
|  | 1.8 mi S of Co Rd G14 to 0.25 mi N of Adams St (NB) | 00-91-035-030-04 | IM-NHS-035-2(468)63--03-91 | Traffic Signs |  |  |  |  | 400
Warren | 35 | Clarke Co to Clanton Creek (NB & SB) |  |  | Pavement Rehab |  |  |  |  | 8688
|  | Clarke Co to Clanton Creek (NB & SB) | 20-91-035-030 | IMX-035-2(482)43--02-91 | HMA Resurfacing |  |  |  |  | 8688
Warren | 35 | Co Rd G50 Interchange 4.7 mi S of IA 92 |  |  | Bridge Deck Overlay |  | 385
|  | Co Rd G50 Interchange 4.7 mi S of IA 92 | 17-91-035-030 | IMN-035-2(460)52--0E-91 | Bridge Deck Overlay |  | 385
Warren | 35 | Co Rd G64 Interchange |  |  | Bridge Deck Overlay |  | 422
|  | Co Rd G64 Interchange | 17-91-035-020 | IMN-035-2(459)47--0E-91 | Bridge Deck Overlay |  | 422
Warren | 35 | N of IA 92 to S of North River (SB) |  |  | Bridge Replacement |  |  | 1843
|  | Co Rd G6R (Hoover St) 1.7 mi N of IA 92 | 00-91-035-030-05 | BRFIM-035-2(428)59--05-91 | Bridge Replacement-PPCB |  |  | 1843
[5 empty] | Grade and Pave |  |  | 19145
|  | N of IA 92 to S of North River (SB) | 00-91-035-030-05 | IM-NHS-035-2(427)57--03-91 | Unknown Pavement - Grade and New |  |  | 19145
[5 empty] | Right of Way |  |  | 200
|  | N of IA 92 to S of North River | 00-91-035-030-05 | IMN-035-2(431)61--0E-91 | Right Of Way |  |  | 200
[5 empty] | Traffic Signs |  |  | 50
|  | N of IA 92 to S of North River (SB) | 00-91-035-030-05 | IM-NHS-035-2(450)57--03-91 | Traffic Signs |  |  | 50
Warren | 35 | N of North River to S of Badger Creek (SB) |  |  | Bridge Replacement | 1615
|  | Fillmore St. Over I-35, 4.6 Miles N. Of Ia. 92(SBL) | 00-91-035-030-06 | BRFIM-035-2(430)61--05-91 | Bridge Replacement-PPCB | 1615
[5 empty] | Grade and Pave | 12466
|  | From Just N. Of North River N. To Just S. Of Badger Creek (SBL) | 00-91-035-030-06 | IM-NHS-035-2(429)61--03-91 | PCC Pavement - Grade and Replace | 12466
[5 empty] | Mitigation | 223
|  | McCorkle Bank for Warren Co IM-NHS-035-2(429)61--03-91 | 00-91-035-030-07 | IMN-035-2(475)61--0E-91 | Wetland Bank Mitigation | 223
[5 empty] | Traffic Signs | 35
|  | N of North River to S of Badger Creek (SB) | 00-91-035-030-06 | IM-NHS-035-2(451)61--03-91 | Traffic Signs | 35
Warren | 65 | Otter Creek 1.6 mi S of Co Rd G58 |  |  | Bridge Replacement |  |  |  | 2200
|  | Otter Creek 1.6 mi S of Co Rd G58 | 19-91-065-010 | BRF-065-3(83)--38-91 | Bridge-Unspecified |  |  |  | 2200
Warren | 69 | 120th AVE 0.75 MI N OF CO RD G64 |  |  | Right of Way | 10
|  | 120th Ave Intersection 0.75 mi N of Co Rd G64 | 20-91-069-010 | STPN-069-3(24)--2J-91 | Right-Of-Way Purchase | 10
Washington | 22 | 9th St in Kalona to E of Boise St in Riverside |  |  | Pave Shoulder | 2103
|  | 9th St in Kalona to E of Boise St in Riverside | 20-92-022-010 | HSIPX-022-2(82)--3L-92 | HMA Paved Shoulder - New | 2103
Washington | 22 | Bulgers Run 4.8 mi E of IA 1 |  |  | Culvert Replacement | 954
|  | Bulgers Run 4.8 mi E of IA 1 | 16-92-022-010 | BRFN-022-2(74)--39-92 | RCB Culvert Replacement - Twin Box | 954
[5 empty] | Right of Way | 10
|  | Bulgers Run 4.8 mi E of IA 1 | 16-92-022-010 | STPN-022-2(75)--2J-92 | Right Of Way | 10
Washington | 92 | E of US 218 to IA 70 in Columbus Junction |  |  | Culvert Replacement |  |  | 224
|  | E of US 218 to IA 70 in Columbus Junction | 85-92-092-010 | NHSX-092-9(108)--3H-58 | RCB Culvert New - Single Box |  |  | 224
[5 empty] | Erosion Control |  |  |  |  | 279
|  | E of US 218 to IA 70 in Columbus Junction | 85-92-092-010 | NHSN-092-9(110)--2R-92 | Erosion Control |  |  |  |  | 279
[5 empty] | Grade and Pave |  |  | 23935
|  | E of US 218 to IA 70 in Columbus Junction | 85-92-092-010 | NHSX-092-9(57)--3H-92 | Unknown Pavement - Grade and Replace |  |  | 23935
[5 empty] | Mitigation |  |  | 1000
|  | River Product #1 or Cedar River Crossing Bank for Washington 92 (57) | 85-92-092-010-01 | NHSN-092-9(153)--2R-92 | Wetland Bank Mitigation |  |  | 500
|  | Site (Stream) Not Yet Identified | 85-92-092-010-01 | NHSN-092-9(154)--2R-92 | Stream Mitigation |  |  | 500
[5 empty] | Right of Way |  |  | 426
|  | E of US 218 to IA 70 in Columbus Junction | 85-92-092-010 | NHSN-092-9(70)--2R-92 | Right Of Way |  |  | 213
|  | E of US 218 to IA 70 in Columbus Junction | 85-92-092-010 | NHSN-092-9(71)--2R-58 | Right Of Way |  |  | 213
[5 empty] | Traffic Signs |  |  | 60
|  | E of US 218 to IA 70 in Columbus Junction | 85-92-092-010 | NHSX-092-9(150)--3H-92 | Traffic Signs |  |  | 60
Washington | 218 | N Fork Long Creek 1.0 mi S of IA 92 (NB) |  |  | Bridge Deck Overlay |  | 337
|  | N Fork Long Creek 1.0 mi S of IA 92 (NB) | 17-92-218-010 | BRFN-218-3(87)--39-92 | Bridge Deck Overlay |  | 337
Wayne | 2 | Jackson Creek 3.8 mi W of Co Rd S56 |  |  | Bridge Deck Overlay |  |  |  | 350
|  | Jackson Creek 3.8 mi W of Co Rd S56 | 19-93-002-010 | BRFN-002-6(47)--39-93 | Bridge Deck Overlay |  |  |  | 350
Wayne | 2 | Steel Creek 2.0 mi E of Co Rd R69 |  |  | Bridge Deck Overlay | 628
|  | Steel Creek 2.0 mi E of Co Rd R69 | 15-93-002-030 | BRFN-002-6(35)--39-93 | Bridge Deck Overlay | 628
Wayne | 65 | CALEB CREEK 2.0 MI S OF CO RD J46 |  |  | Bridge Replacement |  |  | 2557
|  | North Caleb Creek 2.0 mi S of Co Rd J46 | 18-93-065-010 | BRF-065-1(32)--38-93 | Bridge Replacement-PPCB |  |  | 2557
Wayne | 65 | Stream 0.3 mi N of Co Rd J54 |  |  | Culvert Repair |  | 260
|  | Stream 0.3 mi N of Co Rd J54 | 20-93-065-010 | NHSN-065-1(34)--2R-93 | RCB Culvert - Repair |  | 260
[5 empty] | Right of Way |  | 2
|  | Stream 0.3 mi N of Co Rd J54 | 20-93-065-010 | NHSN-065-1(35)--2R-93 | Right Of Way |  | 2

## Line Items
PROJECT ESTIMATED COSTS X $1000
COUNTY | LOCATION | TYPE OF WORK | 2021 | 2022 | 2023 | 2024 | 2025
STATEWIDE | STATEWIDE INTERSTATE GUARDRAIL REPAIR | GUARDRAIL REPAIR | 865 | 865 | 865 | 865 | 865
STATEWIDE | STATEWIDE INTERSTATE LIGHTING | LIGHTING | 500 | 500 | 500 | 500 | 500
STATEWIDE | STATEWIDE INTERSTATE REST AREA MAINTENANCE | REST AREA IMPROVEMENT | 6000 | 6000 | 6000 | 6000 | 6000
STATEWIDE | STATEWIDE INTERSTATE SIGNING | TRAFFIC SIGNS | 1000 | 1000 | 1000 | 1000 | 1000
STATEWIDE | NON-INTERSTATE PAVEMENT MODERNIZATION | PAVEMENT REHAB |  | 115000 | 140000 | 145000 | 150000
STATEWIDE | STATEWIDE SAFETY SPECIFIC | PAVING | 1250 | 20166 | 25000 | 25000 | 25000
STATEWIDE | AMERICANS WITH DISABILITIES ACT | MISCELLANEOUS | 3000 | 3000 | 3000 | 3000 | 3000
STATEWIDE | CONSTRUCTION INDUSTRY TRAINING PROGRAM | MISCELLANEOUS | 1000 | 1000 | 1000 | 1000 | 1000
STATEWIDE | COOPERATIVE CITY/COUNTY/STATE HIGHWAY RESEARCH | MISCELLANEOUS | 1500 | 1500 | 1500 | 1500 | 1500
STATEWIDE | EMERGENCY & CONTINGENCY - U-STEP/C-STEP | MISCELLANEOUS | 6000 | 6000 | 6000 | 6000 | 6000
STATEWIDE | POST LETTING PROJECT COST | MISCELLANEOUS | 20000 | 20000 | 20000 | 20000 | 20000
STATEWIDE | PREVOCATIONAL TRAINING AND DBE SUPPORT SERVICES | MISCELLANEOUS | 360 | 360 | 360 | 360 | 360
STATEWIDE | SCENIC BYWAY PROGRAM | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
STATEWIDE | STATEWIDE CONSULTANT SERVICES | OUTSIDE SERVICES ENGINEERING | 85000 | 85000 | 85000 | 85000 | 85000
STATEWIDE | STATEWIDE CONTRACT MAINTENANCE | MISCELLANEOUS | 35350 | 35350 | 35350 | 35350 | 35350
STATEWIDE | STATEWIDE RAILROAD CROSSINGS | MISCELLANEOUS | 500 | 500 | 500 | 500 | 500
STATEWIDE | STATEWIDE ROADSIDE IMPROVEMENT | LANDSCAPING | 2500 | 2500 | 2500 | 2500 | 2500
STATEWIDE | STATEWIDE TRAFFIC CONTROL DEVICES | TRAFFIC SIGNS | 10000 | 10000 | 10000 | 10000 | 10000
STATEWIDE | STATEWIDE INTERSTATE PAVEMENT MAINTENANCE | PAVEMENT REHAB | 9500 | 9500 | 9500 | 9500 | 9500

## Legend
BLACK text - Five Year Program data
BLUE text - PSS data