## Sheet1
2025 - 2029 IOWA HIGHWAY PROGRAM
S.F 257 Only: No |  |  |  |  | Project Estimated Costs X $1000
Route | Project Code | Location | Miles | Type Of Work | 2025 | 2026 | 2027 | 2028 | 2029
Boone
30 | 24-08-030-010 | Greene Co Line to Co Rd E41/G Ave | 6.1 | Right of Way
|  |  |  | Pavement Rehab | 3500000
169 | 22-08-169-020 | US 30 Interchange | 0.0 | Bridge Deck Overlay |  |  | 823000
210 | 17-08-210-010 | Des Moines River 0.3 mi E of Co Rd E62 | 0.2 | Bridge Rehabilitation |  | 5000000
Dallas
141 | 20-25-141-010 | Granger to IA 44 | 18.2 | Right of Way
|  |  |  | Pavement Rehab | 7100000
Greene
30 | 21-37-030-010 | Buttrick Creek 2.8 mi W of IA 144 | 0.0 | Bridge Replacement |  |  | 2576000
|  |  |  | Right of Way |  | 5000
Grundy
14 | 18-38-014-020-90 | Black Hawk Creek 1.5 mi S of S Jct Co Rd D35 in Grundy | 0.0 | Mitigation | 250000
14 | 18-38-014-020 | Black Hawk Creek 1.5 mi S of S Jct Co Rd D35 | 0.1 | Bridge Replacement | 3575000
|  |  |  | Right of Way | 17000
14 | 20-38-014-010 | Wolf Creek 0.8 mi N fo Co Rd D67 | 0.0 | Bridge Replacement | 1635000
|  |  |  | Right of Way | 11000
175 | 20-38-175-010-90 | Munns Creek 0.8 mi E of Co Rd T47 | 0.0 | Mitigation |  | 75000
175 | 20-38-175-010 | Munns Creek 0.8 mi E of Co Rd T47 | 0.0 | Culvert Replacement |  | 1315000
|  |  |  | Right of Way | 134000
175 | 24-38-175-010 | Branch Blackhawk Creek 0.8 mi W of Co Rd T69 | 0.0 | Bridge Deck Overlay |  |  |  |  | 455000
Hamilton
20 | 21-40-020-010 | Co Rd R38 Interchange | 0.0 | Bridge Deck Overlay |  | 749000
35 | 24-40-035-030 | Co Rd D25/220th St to 0.1 mi S of Co Rd R75 | 7.1 | Pavement Rehab |  |  |  | 5472000
35 | 24-40-035-020 | 1 mi N of IA 175 to 1 mi N of Co Rd D41 (SB) | 6.1 | Pavement Rehab |  |  |  | 1188000
35 | 20-40-035-020 | IA 175 Interchange (NB/SB) | 0.0 | Bridge Rehabilitation | 3168000
Hardin
65 | 20-42-065-010 | UP RR 2.1 mi W of IA 57 | 0.0 | Bridge Deck Overlay | 657000
175 | 21-42-175-020 | Iowa River 0.1 mi W of Co Rd S56 in Eldora | 0.1 | Bridge Deck Overlay |  | 1424000
Humboldt
169 | 22-46-169-010 | W Fork Des Moines River 0.6 mi S of IA 3 in Humboldt | 0.0 | Bridge Rehabilitation |  |  | 2058000
Jasper
6 | 23-50-006-020 | North Skunk River 1.3 mi E of IA 224 | 0.0 | Bridge New |  |  |  | 5610000
|  |  |  | Right of Way |  |  |  | 10000
14 | 24-50-014-020 | In Newton, N of 4th Ave to N of 23rd Ave | 1.5 | Grade & Pave |  |  | 5098000
14 | 24-50-014-030 | In Newton, I-80 to 0.25 mi N of 4th Ave | 1.7 | Grade & Pave |  |  |  | 4025000
65 | 23-50-065-010 | Indian Creek 0.2 mi S of IA 117 (NB) |  | Bridge Deck Overlay |  |  |  | 880000
117 | 22-50-117-010 | At the I-80 Interchange | 0.0 | Bridge Deck Overlay |  |  | 511000
Marion
316 | 20-63-316-010 | NS and BNSF RR 2.5 mi N of IA 5 | 0.0 | Bridge Deck Overlay | 320000
Marshall
14 | 23-64-014-020 | N Jct Co Rd E63 | 0.0 | Grading | 300000
330 | 22-64-330-010 | Clear Creek 1.8 mi S of Co Rd S52 | 0.0 | Bridge Deck Overlay |  |  | 477000
330 | 23-64-330-030 | N of US 30 | 0.0 | Grading | 100000
Polk
35 | 10-77-035-010-03 | I-80/235 Interchange NE Of Des Moines | 1.5 | Grading
Bridge New
Grade & Pave
Traffic Signs
Lighting
Bridge Widening
|  |  |  | Erosion Control | 465082
Right of Way
Salvage & Removal
35 | 15-77-035-040-01 | N of NE 36th St in Ankeny to N of 315th St | 25.4 | Bridge Replacement
|  |  |  | Traffic Signs |  | 1092000
|  |  |  | Lighting |  | 216000
Right of Way
|  |  |  | Erosion Control |  |  | 1246000
Salvage & Removal
|  |  |  | Grade & Pave |  | 51590000
Grading
Culvert New
|  |  |  | Culvert Extension |  | 601102
35 | 10-77-035-010-05 | I-35/235 Interchange NE of Des Moines to US 65 |  | Bridge Replacement | 4945000 |  | 3113000
|  |  |  | Lighting | 68000
|  |  |  | Traffic Signs | 1116000 | 1775000 | 2551000
|  |  |  | Erosion Control |  |  |  | 314000
Right of Way
|  |  |  | Pavement Rehab |  | 14294000
|  |  |  | Grade & Pave | 20940000 | 1029000 | 20393000
|  |  |  | Bridge Widening |  | 6048000
35 | 16-77-035-050 | SW I-35/80/235 Interchange in West Des Moines | 2.7 | Miscellaneous
|  |  |  | Grade & Pave |  |  | 32008000 | 4100000
|  |  |  | Bridge New |  |  | 74384000
|  |  |  | Traffic Signs |  |  | 2000000 | 1000000
|  |  |  | Right of Way |  | 500000
|  |  |  | Erosion Control |  |  |  |  | 400000
35 | 15-77-035-040-90 | Mitigation for Polk - Story I-35 | 17.8 | Mitigation | 131000
65 | 21-77-065-020 | US 6 Interchange 1.0 mi S of I-80 | 0.1 | Bridge Deck Overlay |  | 1813000
65 | 24-77-065-020 | At N IA 5 Interchange (NB/SB) | 0.0 | Bridge Deck Overlay |  |  |  |  | 2475000
65 | 24-77-065-030 | NE 46th Ave 1.2 mi S of I-80 (NB/SB) | 0.0 | Bridge Deck Overlay |  |  |  |  | 2340000
69 | 22-77-069-050 | 1st Street to NE 18th Street in Ankeny | 1.0 | Right of Way
|  |  |  | Paving | 1750000
69 | 17-77-069-010 | DM River to N of Maury Ave in Des Moines (State Share) | 0.5 | Pavement Widening |  |  | 1075000
|  |  |  | Traffic Signals |  |  | 685000
|  |  |  | Right of Way |  | 47000
69 | 20-77-069-030 | Des Moines River 1.4 mi S of I-235 in Des Moines | 0.1 | Bridge Replacement |  |  | 20645000
|  |  |  | Right of Way |  |  | 36000
69 | 19-77-069-010 | Fourmile Creek 0.3 mi N of Co Rd F22 | 0.1 | Bridge Replacement |  | 2156000
Right of Way
80 | 15-77-080-060 | University Ave to N of Douglas Ave | 5.3 | Grade & Pave | 45597000 | 18155000
|  |  |  | Traffic Signs | 3873000 | 2010000
|  |  |  | Culvert Extension | 1289000
|  |  |  | Bridge Widening | 9677000 | 652000
|  |  |  | Lighting |  | 274000
|  |  |  | Traffic Signals |  | 2785000
|  |  |  | Bridge Replacement | 19626000 | 7398000
Miscellaneous
|  |  |  | Erosion Control |  | 200000
Right of Way
80 | 20-77-080-020-01 | EB I-80 Aux Lanes at W I-35/235 Interchange | 0.7 | Grade & Pave | 2402000
80 | 22-77-080-080 | Mitchellville Rest Area 1.4 mi W of Co Rd S27 (EB) | 0.6 | Right of Way |  |  |  | 382000
|  |  |  | Grade & Pave |  |  |  |  | 7899000
|  |  |  | Traffic Signs |  |  |  |  | 499000
|  |  |  | Lighting |  |  |  |  | 269000
80 | 20-77-080-020 | WB I-80 Ramp at W I-35/235 Interchange |  | Right of Way
|  |  |  | Grade & Pave |  | 835000
80 | 24-77-080-050 | Mitchellville Rest Area 1.4 mi W of Co Rd S27 (EB) | 0.0 | Rest Area Improvement |  |  |  | 5125000
141 | 17-77-141-020 | NW 121st St Intersection incl Local Rd Connections | 0.3 | Right of Way
Miscellaneous
|  |  |  | Grade & Pave | 6477000
|  |  |  | Traffic Signs | 218000
|  |  |  | Lighting | 98000
235 | 20-77-235-030 | E 6th St, E 9th St, E 12th St, and US 69 in Des Moines |  | Bridge Painting | 2140000
235 | 19-77-235-030 | SW I-35/80 Interchange to NE I-35/80 Interchange | 14.6 | Landscaping | 125000 |  | 137000 | 249604 | 285000
415 | 24-77-415-020 | NW Beaver Drive Intersection | 0.0 | Grade & Pave | 2400000
Traffic Signs
Lighting
Right of Way
415 | 24-77-415-010 | Over Small Saylorville Dam | 0.8 | Grade & Pave |  |  |  |  | 2348000
415 | 24-77-415-030 | Rock Creek 1.9 mi N of IA 160 | 0.0 | Bridge Deck Overlay |  |  |  |  | 1170000
Poweshiek
6 | 23-79-006-010 | Stony Creek 0.4 mi W of W Jct Co Rd V18 | 0.0 | Bridge New |  |  |  | 1250000
|  |  |  | Right of Way |  |  |  | 10000
21 | 18-79-021-010 | S of I-80 to US 6 | 11.6 | Pavement Rehab | 3500000
63 | 19-79-063-020 | W Jct US 6 to SCL Tama | 28.5 | Erosion Control | 357756
Right of Way
Miscellaneous
Traffic Signs
Pavement Rehab
63 | 22-79-063-010 | Stream 4.4 mi N of Co Rd G17 | 0.0 | Culvert New |  |  | 1558000
|  |  |  | Right of Way |  |  | 12000
80 | 21-79-080-010 | W of IA 21 to E of IA 21 | 2.0 | Miscellaneous
|  |  |  | Traffic Signs |  | 437000 | 371000 | 268000
|  |  |  | Lighting |  |  | 62000 | 64000
|  |  |  | Erosion Control |  |  |  |  | 300000
Right of Way
|  |  |  | Grading |  | 6936000
|  |  |  | Bridge Replacement |  | 2598000 |  | 3160000
|  |  |  | Paving |  |  | 8380000
|  |  |  | Grade & Pave |  |  |  | 16545000
80 | 23-79-080-010 | At US 63 Interchange (EB/WB) | 0.0 | Right of Way |  |  |  |  | 636000
Miscellaneous
|  |  |  | Bridge New |  |  |  |  | 13999000
80 | 24-79-080-010 | 1 mi E of IA 146 to 1 mi E of US 63 (EB/WB) | 9.3 | Pavement Rehab | 9400000
80 | 22-79-080-010 | 50th St 2.1 mi E of IA 146 (EB/WB) | 0.0 | Bridge Deck Overlay |  |  | 3543000
146 | 24-79-146-010 | North Skunk River 2.7 mi N of US 63 | 0.0 | Bridge New |  |  |  |  | 5200000
|  |  |  | Right of Way |  |  |  |  | 10000
146 | 20-79-146-010 | 0.3 mi N of I-80 to US 6 in Grinnell | 3.1 | Pavement Rehab | 3222000
Story
30 | 13-85-030-010-02 | 0.5 mi E of I-35 to E of 590th Ave | 9.1 | Erosion Control | 357756
Right of Way
Salvage & Removal
Grading
Bridge New
Paving
Traffic Signs
Lighting
30 | 13-85-030-010-01 | 610th Ave Interchange at Nevada | 1.7 | Right of Way |  | 18603000
|  |  |  | Erosion Control |  |  |  |  | 358000
|  |  |  | Grading |  |  | 7500000
|  |  |  | Bridge New |  |  | 6565000
|  |  |  | Paving |  |  |  | 15000000
|  |  |  | Traffic Signs |  | 501000 | 58000 | 361000
|  |  |  | Lighting |  |  |  | 129000
Miscellaneous
30 | 19-85-030-020 | South Skunk River 1.2 mi W of I-35 (EB/WB) | 15.8 | Bridge Widening | 1885000
|  |  |  | Bridge Replacement |  | 6779000 | 6633000
|  |  |  | Right of Way | 380000
|  |  |  | Erosion Control |  |  |  | 436000
|  |  |  | Grade & Pave | 2053000 | 6911000 | 4771000
|  |  |  | Lighting |  | 360000 | 310000
|  |  |  | Culvert New |  | 1466000 | 1921000
|  |  |  | Traffic Signs | 425000 | 683000 | 417000
35 | 11-85-035-020-04 | 0.5 mi N of Co Rd E57/260th St to 0.6 mi N of US 30 | 1.9 | Miscellaneous
|  |  |  | Right of Way |  |  | 6900000
Erosion Control
|  |  |  | Lighting |  |  |  |  | 312000
|  |  |  | Traffic Signs |  |  |  | 1246000 | 1685000
|  |  |  | Bridge New |  |  |  |  | 5400000
|  |  |  | Grade & Pave |  |  |  | 10400000 | 24500000
35 | 24-85-035-020 | 0.5 mi N of Co Rd E29 to 1.5 mi S of Co Rd E18 (NB) | 3.6 | Pavement Rehab | 2400000
Tama
8 | 20-86-008-010 | WCL of Dysart to US 218 | 6.2 | Pavement Rehab | 3442000
30 | 23-86-030-010 | WB Off Ramp at L Ave Interchange | 0.2 | Slope Improvement | 100000
63 | 24-86-063-010 | Business US 30 Intersection in Toledo | 0.0 | Grade & Pave | 2200000
Traffic Signs
Lighting
Right of Way
63 | 20-86-063-010 | NCL Toledo to 0.5 mi S of IA 96 | 23.5 | Erosion Control
|  |  |  | Right of Way | 1050000
Miscellaneous
|  |  |  | Grade & Pave |  | 15103000
|  |  |  | Traffic Signs |  | 191000
63 | 19-86-063-020 | NCL Traer to Hudson | 42.4 | Erosion Control
|  |  |  | Right of Way | 639000
Miscellaneous
|  |  |  | Grade & Pave |  |  | 11823000
|  |  |  | Traffic Signs |  |  | 228000
63 | 21-86-063-030 | Iowa River 1.3 mi N of Co Rd E64 | 0.1 | Bridge Deck Overlay |  |  |  | 2853000
96 | 23-86-096-020 | 0.8 mi E of Co Rd T53 | 0.0 | Grading | 600000
|  |  |  | Right of Way | 2000
Warren
5 | 19-91-005-030-90 | Mitigation - South River Bridge | 0.0 | Mitigation |  | 110000
5 | 19-91-005-030 | South River 0.2 mi N of Co Rd S31 (NB) | 0.2 | Bridge Replacement |  | 5297000
Right of Way
65 | 22-91-065-010 | Stream 0.2 mi N fo Co Rd G24 (NB) | 0.0 | Bridge New |  |  | 1408000
|  |  |  | Right of Way |  |  | 7478
Webster
0 | 20-94-926-010 | DM River and B Ave 1.3 mi N of S Jct US 169 in Fort Dodge (EB) |  | Bridge Deck Overlay | 1140000
0 | 20-94-926-020 | CN RR and 7th St 1.5 mi N of S Jct US 169 in Fort Dodge (EB) |  | Bridge Rehabilitation | 601000
144 | 22-94-144-010 | East Buttrick Creek 2.2 mi S of IA 175 | 0.0 | Bridge New |  |  | 1172000
|  |  |  | Right of Way |  |  | 12000
169 | 22-94-169-020 | Bass Creek 0.6 mi S of Co Rd C56 | 0.0 | Bridge New |  |  |  | 742000
Right of Way
175 | 20-94-175-020 | Des Moines River 1.8 mi E of Co Rd P70 | 0.0 | Bridge New |  |  | 13064000
|  |  |  | Right of Way |  |  | 114000
175 | 20-94-175-030 | Ditch #52 0.8 mi E of Co Rd P29 | 0.0 | Culvert Replacement |  | 750000
|  |  |  | Right of Way | 20000
Wright
35 | 24-99-035-010 | 0.1 mi S of Co Rd R75 to 0.6 mi N of Co Rd C47 (NB/SB) | 9.8 | Pavement Rehab |  |  |  |  | 7750000

## Sheet2
2025 - 2029 Five Year Program
This information is valid for the date of Commission approval of None
Line Items
Project Estimated Costs X $1000
County | Location | Type Of Work | 2025 | 2026 | 2027 | 2028 | 2029
Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
Statewide | Statewide Interstate Lighting | Lighting | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
Statewide | Statewide Interstate Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 9800000 | 9900000 | 10000000 | 10100000 | 10200000
Statewide | Statewide Interstate Signing | Traffic Signs | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
Statewide | Statewide Interstate Pavement Maintenance | Pavement Rehab | 9500000 | 9500000 | 14500000 | 14500000 | 14500000
Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 15000000 | 15000000 | 15000000 | 15000000
Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 155000000 | 200000000 | 210000000 | 220000000
Statewide | Statewide Safety Specific | Paving | 0 | 34000000 | 35000000 | 36000000 | 37000000
Statewide | American with Disabilities Act | Miscellaneous | 4500000 | 5000000 | 5500000 | 6000000 | 6500000
Statewide | Construction Industry Training Program | Miscellaneous | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
Statewide | Cooperative City/County/State Highway Research | Miscellaneous | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Statewide | Emergency & Contingency (U-STEP/C-STEP) | Miscellaneous | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
Statewide | Post Letting Project Cost | Miscellaneous | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
Statewide | Prevocational Training and DBE Support Services | Miscellaneous | 360000 | 360000 | 360000 | 360000 | 360000
Statewide | Scenic Byway Program | Miscellaneous | 500000 | 500000 | 500000 | 500000 | 500000
Statewide | Statewide Consultant Services | Outside Services Engineering | 64000000 | 64000000 | 64000000 | 64000000 | 64000000
Statewide | Statewide Contract Maintenance | Miscellaneous | 37350000 | 37850000 | 38350000 | 43500000 | 44000000
Statewide | Statewide Railroad Crossings | Miscellaneous | 500000 | 500000 | 500000 | 500000 | 500000
Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Statewide | Statewide Traffic Control Devices/Signs | Traffic Signs | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Statewide | Statewide Operations | Outside Services Engineering | 12450000 | 12450000 | 12450000 | 12450000 | 12450000
Statewide | Statewide ITS | Miscellaneous | 5750000 | 5750000 | 5750000 | 5750000 | 5750000
Statewide | Winter Operations Materials | Miscellaneous | 15000000 | 15000000 | 15000000 | 15000000 | 15000000
Statewide | Summer Infrastructure Rehabilitation Materials | Miscellaneous | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
Statewide | Pavement Marking Materials | Miscellaneous | 5700000 | 7700000 | 7700000 | 7700000 | 7700000