## Sheet1
2025 - 2029 IOWA HIGHWAY PROGRAM
S.F 257 Only: No |  |  |  |  | Project Estimated Costs X $1000
Route | Project Code | Location | Miles | Type Of Work | 2025 | 2026 | 2027 | 2028 | 2029
Buena Vista
10 | 24-11-010-010 | US 71 to IA 4 | 24.4 | Pavement Rehab | 1082000
71 | 22-11-071-010 | Little Sioux River 2.0 mi S of N Jct IA 10 | 0.0 | Bridge Rehabilitation |  |  | 2757000
Calhoun
175 | 20-13-175-010 | Prairie Creek 3.0 mi E of Co Rd N28 | 0.0 | Bridge Deck Overlay | 648000
175 | 20-13-175-020 | Lake Creek 2.0 mi W of Co Rd N37 | 0.0 | Bridge Deck Overlay | 666000
Carroll
30 | 20-14-030-010 | Storm Creek 2.5 mi W of Co Rd N41 | 0.0 | Bridge Replacement | 2055000
|  |  |  | Right of Way | 11000
71 | 24-14-071-020 | 0.5 mi S of Co Rd E25 to Sac Co | 7.6 | Grade & Pave
71 | 24-14-071-010 | 0.2 mi N of 180th St to E Jct IA 175 in Auburn | 10.6 | Pavement Rehab | 628000
71 | 22-14-071-010 | UP RR and Local Streets 0.2 mi S of US 30 in Carroll | 0.0 | Bridge Deck Overlay |  |  |  | 2009000
Cherokee
3 | 20-18-003-030 | 1.3 mi E of US 59 to 1.8 mi E of US 59 | 0.0 | Erosion Control
|  |  |  | Right of Way | 631000
|  |  |  | Grade & Pave |  | 4168000
|  |  |  | Bridge Replacement |  | 7148847
|  |  |  | Bridge New |  | 1495418
3 | 24-18-003-010 | Fork Little Sioux River 2.5 mi E of IA 143 | 0.0 | Bridge Deck Overlay |  |  |  |  | 650000
31 | 24-18-031-010 | Stratton Creek 0.1 mi N of Co Rd C66 | 0.0 | Bridge New |  |  |  |  | 975000
Right of Way
31 | 20-18-031-010 | Silver Creek 1.0 mi W of US 59 | 0.0 | Bridge Replacement |  | 1990000
|  |  |  | Right of Way |  | 5000
59 | 24-18-059-010 | Grey Creek 2.1 mi N of Co Rd C16 | 0.0 | Bridge Deck Overlay |  |  |  |  | 455000
143 | 24-18-143-010 | IA 3 to E Section St in Marcus | 1.0 | Pavement Rehab | 996000
Clay
18 | 23-21-018-010 | Little Sioux River 2.1 mi W of W Jct US 71 | 0.0 | Bridge New |  |  |  | 2500000
|  |  |  | Right of Way |  |  |  | 10000
18 | 21-21-018-020 | Stony Creek 5.3 mi W of W Jct US 71 | 0.0 | Bridge Replacement |  |  | 3736000
|  |  |  | Right of Way |  |  | 5000
71 | 21-21-071-020 | Willow Creek 3.4 mi N of N Jct IA 10 | 0.0 | Bridge Replacement |  | 2447000
|  |  |  | Right of Way |  | 23853
71 | 21-21-071-010 | Branch of Little Meadow Creek 0.8 mi N of N Jct US 18 | 0.0 | Bridge Deck Overlay |  | 196000
Crawford
30 | 20-24-030-010 | Boyer River 2.7 mi W of US 59 | 0.1 | Bridge Replacement |  |  |  | 3810000
|  |  |  | Right of Way |  |  |  | 5000
30 | 20-24-030-020 | Boyer River 0.8 mi E of Co Rd M14 | 0.1 | Bridge Rehabilitation | 1415000
|  |  |  | Right of Way | 5000
30 | 22-24-030-010 | UP RR 0.4 mi E of W Jct US 59 in Denison (EB/WB) | 0.0 | Bridge New |  |  |  |  | 16988000
|  |  |  | Right of Way |  |  |  |  | 14000
39 | 20-24-039-010 | East Otter Creek 0.4 mi E of Co Rd M35 | 0.0 | Bridge Replacement |  | 2038000
|  |  |  | Right of Way |  | 1000
59 | 20-24-059-010-90 | Mitigation - East Soldier River RCB Culvert Project | 0.0 | Mitigation | 70000
59 | 20-24-059-010 | East Soldier River 2.9 mi S of Co Rd E16 | 0.0 | Culvert Replacement | 923000
|  |  |  | Right of Way | 16000
59 | 24-24-059-010 | Crestview Ave in Denison to N Jct IA 141 | 3.9 | Pavement Rehab | 853000
59 | 22-24-059-020 | Boyer River 0.1 mi S of IA 39 in Denison (SB) | 0.0 | Bridge Deck Overlay |  |  | 1068000
141 | 21-24-141-010 | Monona Co Line to N Jct US 59 | 15.0 | Pavement Rehab | 4396000
141 | 24-24-141-020 | Charter Oak to US 59 | 10.2 | Paved Shoulders | 1883000
|  |  |  | Paved Shoulders | 345000
Dickinson
9 | 21-30-009-020 | W Fork Little Sioux River 4.9 mi W of IA 86 | 0.0 | Bridge Replacement |  | 2069000
|  |  |  | Right of Way |  | 6000
71 | 20-30-071-010 | East Okoboji Lake 1.7 mi N of S Jct IA 9 | 0.0 | Bridge Deck Overlay | 468000
Emmet
4 | 22-32-004-020 | Drainage Ditch 1.5 mi N of N Jct Co Rd A34 | 0.0 | Bridge Deck Overlay |  |  | 737000
9 | 24-32-009-010 | In Estherville, Des Moines River Bridge to S 28th St | 1.8 | Right of Way
|  |  |  | Grade & Pave |  |  |  | 5451000
Harrison
37 | 21-43-037-010 | Boyer River 0.1 mi W of US 30 | 0.1 | Bridge New |  |  |  | 4870000
|  |  |  | Right of Way |  |  |  | 5000
Ida
31 | 24-47-031-010 | Ashton Creek 1.0 mi N of Co Rd D15 | 0.0 | Bridge Deck Overlay |  |  |  |  | 520000
59 | 24-47-059-010 | Susan Lawrence Dr to Father Dailey Dr in Ida Grove | 0.8 | Pavement Rehab | 614000
59 | 24-47-059-020 | Crawford Co Line to S Jct IA 175 | 8.4 | Pavement Rehab | 942000
175 | 21-47-175-010 | Morehead Creek 2.6 mi W of W Jct Co Rd L51 | 0.0 | Bridge Deck Overlay |  | 410000
Lyon
9 | 18-60-009-010 | South Dakota east 0.5 mi | 0.0 | Grade & Pave |  | 535000
Right of Way
9 | 24-60-009-030 | Approx 1.4 mi W of Co Rd K60 | 0.0 | Culvert Replacement |  |  | 400000
|  |  |  | Right of Way |  |  | 10000
9 | 24-60-009-040 | Little Rock River 1.0 mi W of Co Rd L26 | 0.0 | Bridge Deck Overlay |  |  |  |  | 975000
18 | 20-60-018-010 | Big Sioux River at South Dakota (State Share) | 0.1 | Bridge Deck Overlay | 2014000
75 | 21-60-075-010 | Little Rock River 0.4 mi S of Co Rd A44 | 0.0 | Bridge Rehabilitation |  | 759000
Monona
29 | 24-67-029-050 | Onawa Rest Area 2.6 mi S of IA 175 (NB) | 0.7 | Right of Way | 205000
|  |  |  | Grade & Pave |  | 7050000
|  |  |  | Traffic Signs |  | 164000
|  |  |  | Lighting |  | 171000
29 | 22-67-029-040 | N of Co Rd E60 to IA 175 (SB) | 7.7 | Paving |  |  |  | 25037000
29 | 24-67-029-040 | Harrison County to Woodbury County | 25.4 | Pavement Markings | 810000
29 | 22-67-029-020 | Onawa Rest Area 2.6 mi S of IA 175 (SB | 0.0 | Rest Area Improvement |  |  |  |  | 4500000
29 | 24-67-029-060 | Onawa Rest Area 2.6 mi S of IA 175 (NB) | 0.0 | Rest Area Improvement |  |  | 5125000
29 | 20-67-029-010 | N of IA 175 to Woodbury Co (NB) | 0.0 | Pavement Rehab | 3823000
29 | 20-67-029-020 | 1.5 mi N of IA 175 to Woodbury Co (SB) | 0.0 | Pavement Rehab | 3636000
29 | 20-67-029-030 | Co Rd E24 Interchange |  | Bridge Deck Overlay |  | 1084000
37 | 24-67-037-010 | Beaver Creek 4.4 mi E of IA 175 | 0.0 | Bridge New |  |  |  |  | 3250000
Right of Way
37 | 22-67-037-010 | Norway Creek 2.6 mi E of IA 183 | 0.0 | Bridge Deck Overlay |  |  | 750000
141 | 23-67-141-010 | Maple River 0.1 mi E of W Jct IA 175 in Mapleton | 0.0 | Bridge New |  |  |  | 4370000
|  |  |  | Right of Way |  |  |  | 10000
141 | 24-67-141-030 | Soldier River 3.9 mi W of IA 183 | 0.0 | Bridge New |  |  |  |  | 3575000
Right of Way
141 | 24-67-141-020 | ECL Ute to Crawford Co Line | 1.5 | Pavement Rehab | 519000
175 | 21-67-175-020 | I-29 Interchange | 0.0 | Grade & Pave |  | 19623000
|  |  |  | Bridge Replacement |  | 4375000
|  |  |  | Traffic Signs |  | 819000
|  |  |  | Lighting |  | 118000
|  |  |  | Right of Way | 26000
|  |  |  | Erosion Control |  |  | 200000
175 | 20-67-175-020 | Little Sioux River 1.5 mi W of IA 37 | 0.0 | Bridge New |  | 4343000
|  |  |  | Right of Way |  | 11000
175 | 16-67-175-010 | Missouri River E of Decatur Nebraska (State Share) | 0.0 | Bridge Rehabilitation | 133000 | 133000 | 133000 | 133000 | 133000
175 | 23-67-175-020 | Missouri River E of Decatur, Nebraska | 0.0 | Bridge Rehabilitation | 736000
183 | 24-67-183-020 | Jordan Creek 0.8 mi S of Co Rd E54 | 0.0 | Bridge Deck Overlay |  |  |  |  | 520000
O'Brien
10 | 21-71-010-010 | Dry Run 0.2 mi W of W Jct US 59 | 0.0 | Bridge Deck Overlay |  | 653000
18 | 24-71-018-030 | Stream 0.2 mi W of Co Rd M22 | 0.0 | Culvert New |  |  |  |  | 1300000
Right of Way
18 | 23-71-018-010 | In Sheldon, from B St to 0.3 mi E of IA 60 | 1.4 | Pavement Rehab | 1821000
59 | 20-71-059-020 | Branch Floyd River 1.9 mi N of N Jct US 18 | 0.0 | Bridge Deck Overlay | 542000
Osceola
9 | 24-72-009-030 | Polly Creek 0.9 mi W of IA 60 | 0.0 | Bridge New |  |  |  |  | 650000
Right of Way
9 | 24-72-009-020 | Otter Creek 2.5 mi W of Co Rd L40 | 0.0 | Bridge Deck Overlay |  |  |  |  | 130000
59 | 24-72-059-020 | Approx 0.9 mi n of Co Rd A22 | 0.0 | Culvert Replacement |  |  | 800000
|  |  |  | Right of Way |  |  | 10000
59 | 24-72-059-010 | Approx 0.2 mi S of 250th St | 0.0 | Culvert Replacement |  |  | 500000
|  |  |  | Right of Way |  |  | 10000
59 | 21-72-059-010 | Drainage Ditch 1.1 mi N of Co Rd A46 | 0.0 | Bridge Deck Overlay |  | 604000
60 | 23-72-060-030 | Drainage Ditch 2.6 mi N of Co Rd B14 (SB) | 0.0 | Bridge New |  |  |  | 1250000
|  |  |  | Right of Way |  |  |  | 10000
60 | 21-72-060-010 | Drainage Ditch 1.1 mi S of Co Rd L36 (SB) |  | Culvert Replacement |  | 1971000
|  |  |  | Right of Way |  | 5000
Palo Alto
4 | 21-74-004-020 | W Fork Des Moines River 3.2 mi S of S Jct US 18 | 0.1 | Bridge New |  |  |  | 4494000
|  |  |  | Right of Way |  |  |  | 13000
4 | 22-74-004-010 | Drainage Ditch 1.3 mi S of Co Rd B57 | 0.0 | Bridge New |  |  |  | 1224000
|  |  |  | Right of Way |  |  |  | 13000
18 | 19-74-018-010 | Prairie Creek 2.8 mi W of W Jct IA 15 | 0.0 | Culvert Replacement | 1525000
Right of Way
Plymouth
3 | 24-75-003-010 | In Remsen, W of Country Club St to 0.1 mi E of S Lincoln St | 1.4 | Pavement Rehab | 925000
Right of Way
3 | 24-75-003-030 | Big Sioux Overflow 1.0 mi W of IA 12 | 0.0 | Bridge Deck Overlay |  |  |  |  | 650000
3 | 23-75-003-030 | Floyd River 1.0 mi E of US 75 in Le Mars | 0.0 | Bridge Deck Overlay |  |  |  | 940000
12 | 22-75-012-030 | Broken Kettle Creek 0.1 mi N of S Jct Co Rd K18 | 0.0 | Bridge Replacement |  |  | 2804000
|  |  |  | Right of Way |  |  | 12000
12 | 22-75-012-010 | Beaver Creek 0.5 mi N of Co Rd C16 | 0.0 | Bridge Deck Overlay |  |  | 770000
75 | 16-75-075-030 | N of Maple St in Hinton to S of 2nd St in Merrill | 6.4 | Erosion Control |  | 358000
Right of Way
|  |  |  | Grade & Pave | 26364000
Culvert New
|  |  |  | Culvert Repair | 3659000
75 | 21-75-075-010 | S of W Grover St to N of Maple St in Hinton | 0.7 | Right of Way |  | 4174318
Salvage & Removal
|  |  |  | Grade & Pave |  |  |  | 7911000
|  |  |  | Traffic Signals |  |  |  | 2028000
|  |  |  | Bridge Replacement |  |  |  | 1973000
75 | 24-75-075-030 | Stream 0.6 mi S of Co Rd C60 (NB) | 0.0 | Bridge New |  |  |  |  | 1950000
Right of Way
75 | 22-75-075-020 | W Fork Floyd River 2.4 mi N of Co Rd R38 | 0.0 | Bridge Deck Overlay |  |  | 1131000
404 | 24-75-404-010 | Floyd River 0.4 mi N of IA 3 in Le Mars (NB) | 0.0 | Bridge Rehabilitation |  |  |  |  | 2600000
Pocahontas
3 | 21-76-003-050 | Drainage Ditch 5.0 mi W of IA 4 | 0.0 | Culvert Replacement |  | 1260000
|  |  |  | Right of Way |  | 3000
3 | 24-76-003-010 | North Lizard Creek 0.8 mi W of IA 15 | 0.0 | Bridge Deck Overlay |  |  |  |  | 520000
3 | 21-76-003-030 | Lizard Creek 0.9 mi E of IA 4 in Pocahontas | 0.0 | Bridge Deck Overlay |  | 626000
3 | 21-76-003-040 | Little Cedar Creek 4.4 mi E of Co Rd N14 | 0.0 | Bridge Deck Overlay |  | 275000
4 | 24-76-004-010 | IA 3 In Pocahontas to Co Rd B63 in Mallard | 13.9 | Paved Shoulders | 2127000
|  |  |  | Pavement Rehab | 4167000
4 | 23-76-004-030 | North Lizard Creek 5.6 mi N of IA 3 | 0.0 | Bridge Deck Overlay |  |  |  | 500000
10 | 23-76-010-010 | Little Cedar Creek 3.7 mi W of Co Rd N28 | 0.0 | Bridge Deck Overlay |  |  |  | 500000
15 | 22-76-015-010 | Pilot Creek at the N Jct Co Rd C26 | 0.0 | Bridge Replacement |  |  | 2493000
|  |  |  | Right of Way |  |  | 12000
Sac
20 | 23-81-020-010 | North Raccoon River 1.0 mi W of Co Rd M54 (EB/WB) | 0.0 | Bridge Deck Overlay |  |  |  | 640000
71 | 24-81-071-010 | Carroll Co to Jct IA 175 in Auburn | 2.8 | Grade & Pave |  |  |  |  | 4611000
110 | 21-81-110-010 | First St in Schaller to Storm Lake | 12.5 | Pavement Rehab | 8546000
175 | 24-81-175-010 | High St 1.9 mi E of Co Rd M64 | 0.0 | Bridge New |  |  |  |  | 3900000
Right of Way
471 | 20-81-471-010 | Ditch 0.2 mi N of Co Rd D36 | 0.0 | Culvert Repair | 196000
Right of Way
Shelby
59 | 24-83-059-010 | Lyon Creek 2.6 mi S of IA 37 | 0.0 | Bridge Deck Overlay |  |  |  |  | 780000
Sioux
10 | 24-84-010-020 | Dry Creek 0.4 mi W of IA 12 in Hawarden | 0.0 | Bridge New |  |  |  |  | 1950000
Right of Way
10 | 20-84-010-010 | Orange City Slough 4.5 mi E of US 75 | 0.0 | Bridge Deck Overlay | 730000
10 | 24-84-010-010 | UP RR 1.0 mi W of IA 60 | 0.0 | Bridge Deck Overlay |  |  |  |  | 1300000
18 | 24-84-018-030 | US 75 to Hull | 2.0 | Paving | 1080000
60 | 21-84-060-010 | Floyd River Tributary 0.5 mi S of Co Rd K64 (NB) | 0.0 | Bridge Replacement |  |  | 2134000
|  |  |  | Right of Way |  |  | 5000
60 | 23-84-060-010 | Floyd River Tributary 0.5 mi S of Co Rd K64 (SB) | 0.0 | Bridge Deck Overlay |  |  |  | 440000
75 | 17-84-075-010 | S of 12th St NE in Sioux Center to S Jct US 18 | 6.1 | Right of Way | 470000
|  |  |  | Traffic Signals |  |  | 300000
|  |  |  | Grade & Pave |  |  | 23841000
75 | 24-84-075-020 | W Fork Floyd River 0.1 mi N of IA 10 | 0.0 | Bridge Deck Overlay |  |  |  |  | 110000
Statewide
0 | 24-00-000-070 | Various Counties and Routes in District 3 |  | Pavement Rehab | 2100000
Woodbury
12 | 19-97-012-010 | Gordon Dr Viaduct, Rustin St to Virginia St in Sioux City | 1.2 | Miscellaneous
|  |  |  | Right of Way |  |  | 26400000
|  |  |  | Grade & Pave |  |  |  | 40000000
|  |  |  | Bridge New |  |  |  |  | 100000000
20 | 17-97-020-020 | Abandoned RR 0.1 mi E of Co Rd D25 (Remove Bridge) | 0.0 | Grade & Pave | 7853000
Right of Way
20 | 24-97-020-020 | 0.4 mi E of Franklin Ave to E of Humboldt Ave near Moville | 3.6 | Paved Shoulders |  |  | 0
|  |  |  | Grade & Pave |  |  | 5746000
|  |  |  | Grade & Pave |  |  | 0
20 | 98-97-020-010-08 | Mitigation - Woodbury Ida and Sac Counties US 20 | 0.0 | Mitigation
|  |  |  | Wetland Mitigation | 179000
20 | 19-97-020-040 | Proposed Rd 0.5 mi W of IA 12 (EB/WB) | 0.0 | Bridge Deck Overlay | 601000
20 | 21-97-020-050 | WB Ramp over IA 376 and RR |  | Bridge Deck Overlay |  | 2583000
20 | 22-97-020-040 | Sunnybrook Dr 1.7 mi W of IA 12 in Sioux City (EB/WB) | 0.0 | Bridge Deck Overlay |  |  | 903000
20 | 21-97-020-070 | US 20 Ramp G over I-29 |  | Bridge Deck Overlay |  | 1265000
29 | 20-97-029-070 | SB Weigh Station 0.6 mi N of Co Rd K35 |  | Paving |  | 4915000
29 | 18-97-029-010 | IA 141 Interchange | 0.0 | Erosion Control | 238233
Right of Way
Grade & Pave
Bridge Replacement
Traffic Signs
Lighting
29 | 24-97-029-030 | Monona County to Sergeant Bluff | 12.3 | Pavement Markings | 410000
29 | 24-97-029-040 | Sergeant Bluff to South Dakota Border | 12.9 | Pavement Markings | 600000
29 | 06-97-029-010 | Southbridge Interchange 2.5 mi south of Sergeant Bluff | 0.0 | Miscellaneous
|  |  |  | Right of Way |  | 125000
|  |  |  | Traffic Signals |  | 819000
|  |  |  | Bridge New |  | 500000
29 | 23-97-029-070 | Sergeant Bluff Rest Area (SB) (Remove Ramps) | 0.0 | Grading |  | 655000
29 | 22-97-029-030 | Sergeant Bluff Rest Area (NB) (Remove) | 0.0 | Grading |  | 892000
31 | 17-97-031-010-01 | Co Rd C66 in Washta to US 59 | 9.9 | Pavement Rehab
Right of Way
|  |  |  | Culvert Extension |  | 1674000
75 | 24-97-075-010 | US 20 Interchange to N of Co Rd C80 | 6.9 | Pavement Rehab | 1263000
77 | 23-97-077-020 | Wesley Pkwy over Tri View Ave and BNSF RR in Sioux City | 0.0 | Bridge Deck Overlay |  |  |  | 1630000
77 | 16-97-077-010 | Missouri River in Sioux City (State Share) | 0.1 | Bridge Washing | 36000 | 36000 | 35780 | 36000 | 36000
129 | 21-97-129-010 | Missouri River in Sioux City (State Share) | 0.0 | Bridge Rehabilitation | 9500000
129 | 16-97-129-010 | Missouri River in Sioux City (State Share) | 0.2 | Bridge Washing |  | 50000 | 50000 | 50243 | 50000
|  |  |  | Bridge Washing | 50000
141 | 23-97-141-030 | W Branch Little Sioux River 0.8 mi E of Co Rd K64 | 0.0 | Bridge New |  |  |  |  | 2613000
|  |  |  | Right of Way |  |  |  |  | 10000
141 | 24-97-141-010 | Fork Little Sioux River 0.3 mi W of Co Rd K64 | 0.0 | Bridge New |  |  |  |  | 975000
Right of Way
141 | 24-97-141-020 | Smokey Hollow Creek 0.2 mi E of IA 31 | 0.0 | Bridge New |  |  |  |  | 2275000
Right of Way
175 | 20-97-175-010 | Reynolds Creek 1.6 mi W of Co Rd L37 | 0.0 | Bridge New |  |  | 1717000
|  |  |  | Right of Way |  |  | 12000
376 | 21-97-376-030 | Tributary to Floyd River 0.1 mi N of Co Rd D12 in Sioux City (SB) |  | Bridge New |  | 875000
Right of Way
376 | 21-97-376-010 | Singing Hills Dr to Lincoln Way in Sioux City | 1.7 | Pavement Rehab | 1224000

## Sheet2
2025 - 2029 Five Year Program
This information is valid for the date of Commission approval of None
Line Items
Project Estimated Costs X $1000
County | Location | Type Of Work | 2025 | 2026 | 2027 | 2028 | 2029
Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
Statewide | Statewide Interstate Lighting | Lighting | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
Statewide | Statewide Interstate Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 9800000 | 9900000 | 10000000 | 10100000 | 10200000
Statewide | Statewide Interstate Signing | Traffic Signs | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
Statewide | Statewide Interstate Pavement Maintenance | Pavement Rehab | 9500000 | 9500000 | 14500000 | 14500000 | 14500000
Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 15000000 | 15000000 | 15000000 | 15000000
Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 155000000 | 200000000 | 210000000 | 220000000
Statewide | Statewide Safety Specific | Paving | 0 | 34000000 | 35000000 | 36000000 | 37000000
Statewide | American with Disabilities Act | Miscellaneous | 4500000 | 5000000 | 5500000 | 6000000 | 6500000
Statewide | Construction Industry Training Program | Miscellaneous | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
Statewide | Cooperative City/County/State Highway Research | Miscellaneous | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Statewide | Emergency & Contingency (U-STEP/C-STEP) | Miscellaneous | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
Statewide | Post Letting Project Cost | Miscellaneous | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
Statewide | Prevocational Training and DBE Support Services | Miscellaneous | 360000 | 360000 | 360000 | 360000 | 360000
Statewide | Scenic Byway Program | Miscellaneous | 500000 | 500000 | 500000 | 500000 | 500000
Statewide | Statewide Consultant Services | Outside Services Engineering | 64000000 | 64000000 | 64000000 | 64000000 | 64000000
Statewide | Statewide Contract Maintenance | Miscellaneous | 37350000 | 37850000 | 38350000 | 43500000 | 44000000
Statewide | Statewide Railroad Crossings | Miscellaneous | 500000 | 500000 | 500000 | 500000 | 500000
Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Statewide | Statewide Traffic Control Devices/Signs | Traffic Signs | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Statewide | Statewide Operations | Outside Services Engineering | 12450000 | 12450000 | 12450000 | 12450000 | 12450000
Statewide | Statewide ITS | Miscellaneous | 5750000 | 5750000 | 5750000 | 5750000 | 5750000
Statewide | Winter Operations Materials | Miscellaneous | 15000000 | 15000000 | 15000000 | 15000000 | 15000000
Statewide | Summer Infrastructure Rehabilitation Materials | Miscellaneous | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
Statewide | Pavement Marking Materials | Miscellaneous | 5700000 | 7700000 | 7700000 | 7700000 | 7700000