## Sheet1
2025 - 2029 IOWA HIGHWAY PROGRAM
S.F 257 Only: No |  |  |  |  | Project Estimated Costs X $1000
Route | Project Code | Location | Miles | Type Of Work | 2025 | 2026 | 2027 | 2028 | 2029
Appanoose
5 | 23-04-005-010 | Drainage Ditch 0.4 mi N of Co Rd T30 | 0.0 | Bridge New |  |  |  | 630000
|  |  |  | Right of Way |  |  |  | 10000
Clarke
35 | 18-20-035-020 | 0.5 mi N of US 34 to Warren Co | 9.1 | Pavement Rehab
|  |  |  | Pavement Rehab | 3402000
35 | 22-20-035-010 | White Breast Creek 1.3 mi S of US 34 (NB/SB) | 0.0 | Bridge Rehabilitation |  |  | 2286000
69 | 24-20-069-010 | S of Co Rd R35 to N of Warren Co Line | 11.4 | Pavement Rehab | 9163000
Davis
63 | 18-26-063-010 | Fox River 2.1 mi N of IA 2 | 0.1 | Bridge Replacement | 3330000
Right of Way
63 | 20-26-063-010 | Middle Chequest Creek 0.2 mi N of 180th St | 0.1 | Bridge Replacement | 2604000
|  |  |  | Right of Way | 11000
63 | 20-26-063-020 | North Chequest Creek 2.6 mi N of Co Rd J3T | 0.0 | Culvert Repair | 1001716
|  |  |  | Right of Way | 5000
Decatur
35 | 14-27-035-010 | Missouri to Polk Co | 0.0 | Guardrail | 100000 | 100000 | 100000 | 100000 | 100000
35 | 22-27-035-020 | At the Co Rd J20 Interchange | 0.0 | Bridge Deck Overlay |  |  | 838000
35 | 20-27-035-030 | Co Rd R30 1.0 mi S of IA 2 |  | Bridge Deck Overlay | 720000
69 | 21-27-069-030 | I-35 Interchange | 0.1 | Bridge Deck Overlay |  | 524000
69 | 21-27-069-020 | Dickersons Branch 1.1 mi S of Co Rd J66 | 0.0 | Bridge Deck Overlay |  | 839000
Des Moines
34 | 20-29-034-020 | W Burlington Ave 0.5 mi W of US 61 (WB) | 0.0 | Bridge Rehabilitation | 228000
Right of Way
34 | 22-29-034-030 | Broadway Ave 1.0 mi W of US 61 in Burlington (WB) | 0.0 | Bridge Deck Overlay |  |  | 1080000
34 | 19-29-034-030 | WB Ramp to US 34 0.4 mi W of IL in Burlington |  | Bridge Deck Overlay | 1392000
34 | 20-29-034-010 | W Burlington Ave 0.5 mi W of US 61 (EB) | 0.0 | Bridge Deck Overlay | 766000
34 | 22-29-034-010 | BNSF RR and City Streets 1.4 mi E of US 61 in Burlington | 0.1 | Bridge Rehabilitation |  |  | 2109000
34 | 22-29-034-020 | BNSF RR and City Streets 1.5 mi E of US 61 in Burlington | 0.1 | Bridge Rehabilitation |  |  | 4959000
34 | 23-29-034-020 | Broadway Ave 1.0 mi W of US 61 in West Burlington (EB) | 0.0 | Bridge Rehabilitation |  |  |  | 250000
34 | 23-29-034-030 | BNSF RR 0.3 mi W of US 61 in West Burlington (EB/WB) | 0.0 | Bridge Rehabilitation |  |  |  | 500000
34 | 23-29-034-040 | Gear Ave 1.6 mi W of US 61 in West Burlington | 0.0 | Bridge Rehabilitation |  |  |  | 250000
34 | 23-29-034-050 | 4th St 2.1 mi E of US 61 in Burlington | 0.0 | Bridge Rehabilitation |  |  |  | 250000
34 | 23-29-034-060 | 5th St 2.0 mi E of US 61 in Burlington | 0.0 | Bridge Rehabilitation |  |  |  | 250000
34 | 24-29-034-010 | Mississippi River in Burlington | 0.0 | Bridge Painting |  |  |  |  | 1000000
34 | 16-29-034-010 | Mississippi River in Burlington (State Share) | 0.4 | Bridge Washing | 50000 | 50000 | 49633 | 50000 | 50000
61 | 97-29-061-010-02 | S of 210th St to N of Mediapolis | 8.4 | Erosion Control |  | 233000
|  |  |  | Grade & Pave | 24363000
|  |  |  | Traffic Signs | 366000
|  |  |  | Lighting | 188000
Grading
Bridge New
Culvert Replacement
|  |  |  | Pavement Rehab |  | 1228000
61 | 97-29-061-010-03 | N of Mediapolis to 0.5 mi N of IA 78 | 16.3 | Erosion Control |  |  | 373855
Right of Way
|  |  |  | Paving |  | 32909000
|  |  |  | Traffic Signs |  | 457000
|  |  |  | Lighting |  | 171000
|  |  |  | Culvert Replacement |  | 322000
Culvert New
Grading
|  |  |  | Bridge New | 3514000
61 | 15-29-061-010 | Branch Smith Creek 1.0 mi S of Louisa Co | 0.1 | Culvert Replacement |  | 1401000
|  |  |  | Right of Way | 4201000
61 | 21-29-061-010 | Skunk River 0.5 mi N of IA 16 (SB) |  | Bridge Deck Overlay |  |  | 1588000
61 | 20-29-061-020 | US 34 in Burlington | 0.1 | Bridge Deck Overlay | 1937000
Henry
34 | 24-44-034-010 | E US 218 Interchange to E of Nebraska Ave (WB) | 3.4 | Pavement Rehab | 2250000
78 | 23-44-078-020 | Stream 2.0 mi W of W Jct Co Rd W66 | 0.0 | Bridge New |  |  |  | 1250000
|  |  |  | Right of Way |  |  |  | 10000
78 | 20-44-078-010 | Stream 0.3 mi W of E Jct Co Rd W66 | 0.0 | Culvert Replacement | 994000
|  |  |  | Right of Way | 5000
218 | 19-44-218-030 | North Fish Creek 1.1 mi N of Co Rd J20 (NB) | 0.1 | Bridge Replacement | 4897000
Right of Way
218 | 20-44-218-020 | South Fish Creek 0.7 mi N of Co Rd J20 (NB) | 0.0 | Bridge Replacement | 2420000
|  |  |  | Right of Way | 5000
218 | 23-44-218-020 | US 218 Ramp G 3.3 mi N of S Jct US 34 | 0.0 | Bridge Deck Overlay |  |  |  | 820000
218 | 24-44-218-010 | US 34 Interchange (NB/SB) | 0.0 | Bridge Deck Overlay |  |  |  |  | 2600000
Keokuk
21 | 21-54-021-020 | Cedar Creek 1.1 mi N of IA 92 | 0.0 | Bridge Replacement |  | 3484000
|  |  |  | Right of Way |  | 2283000
78 | 23-54-078-010 | Stream 3.9 mi E of IA 149 | 0.0 | Culvert New |  |  |  | 940000
|  |  |  | Right of Way |  |  |  | 10000
78 | 21-54-078-010 | Stream 3.4 mi W of IA 1 | 0.0 | Bridge Replacement |  | 1920000
|  |  |  | Right of Way |  | 10000
92 | 20-54-092-020 | German Creek 3.0 mi E of E Jct IA 149 | 0.0 | Bridge Deck Overlay | 712000
92 | 21-54-092-010 | Rock Creek 0.4 mi W of Co Rd V45 | 0.0 | Bridge Deck Overlay |  | 531000
149 | 16-54-149-010 | IA 78 to 0.25 mi S of W Kelly St in Sigourney | 10.2 | Pavement Rehab | 6113000
149 | 22-54-149-010 | North Skunk River 2.5 mi S of W Jct IA 92 | 0.1 | Bridge Deck Overlay |  |  | 1487000
Lee
2 | 21-56-002-010 | Big Sugar Creek 3.4 mi W of W Jct US 61 | 0.1 | Bridge Deck Overlay |  | 1028000
16 | 22-56-016-010 | Sugar Creek 0.3 mi W of US 218 | 0.0 | Bridge New |  |  |  | 3256000
|  |  |  | Right of Way |  |  |  | 13000
16 | 21-56-016-010 | Little Cedar Creek 1.7 mi E of Co Rd W46 | 0.0 | Bridge Deck Overlay |  | 596000
61 | 24-56-061-010 | In Keokuk, Des Moines River Bridge to US 218 | 3.7 | Grade & Pave |  |  |  |  | 7940000
61 | 21-56-061-020 | Lost Creek 2.4 mi S of IA 16 (NB) | 0.0 | Bridge Replacement |  |  |  | 3708000
|  |  |  | Right of Way |  |  |  | 0
136 | 23-56-019-010 | Mississippi River in Keokuk | 0.0 | Bridge Rehabilitation |  |  |  | 50000
136 | 16-56-019-010 | Mississippi River in Keokuk (State Share) | 0.1 | Bridge Washing | 20000 | 20000 | 19853 | 20000 | 20000
218 | 21-56-218-010 | BNSF RR 4.4 mi S of US 61 | 0.0 | Bridge Deck Overlay |  | 807000
218 | 24-56-218-010 | Approx 0.3 mi S of Co Rd J38 to Big Creek Bridge (SB) | 10.9 | Paved Shoulders | 3360000
Louisa
61 | 11-58-061-010 | 0.5 mi N of IA 78 to 2.0 mi S of IA 92 | 30.8 | Erosion Control
|  |  |  | Right of Way |  | 8110000
|  |  |  | Grading |  |  | 56011000
Bridge New
Bridge Replacement
Paving
|  |  |  | Grade & Pave |  |  |  |  | 91131000
Traffic Signals
Culvert Extension
|  |  |  | Culvert New |  |  | 42892000
|  |  |  | Traffic Signs |  |  |  |  | 623000
|  |  |  | Lighting |  |  |  |  | 224000
61 | 21-58-061-010 | DME RR 3.4 mi N of W Jct IA 92 (NB) | 0.1 | Bridge Deck Overlay |  | 418000
61 | 23-58-061-020 | Drainage Ditch 2.7 mi S of Co Rd X99 | 0.0 | Bridge Deck Overlay |  |  |  | 500000
61 | 24-58-061-010 | Iowa River 4.2 mi S of IA 92 | 0.0 | Bridge Deck Overlay |  |  |  |  | 3900000
61 | 23-58-061-030 | Iowa River 4.2 mi S of IA 92 | 0.0 | Bridge Painting |  |  |  | 1190000
70 | 24-58-070-010 | Iowa River 0.9 mi N of IA 92 | 0.0 | Bridge Deck Overlay |  |  |  |  | 1950000
92 | 23-58-092-010 | Monkey Run Creek 0.6 mi W of IA 70 in Columbus Jct | 0.0 | Bridge Deck Overlay |  |  |  | 440000
92 | 23-58-092-020 | Iowa River 0.5 mi E of IA 70 | 0.0 | Bridge Deck Overlay |  |  |  | 3740000
92 | 21-58-092-010 | Main St and Collins Rd 0.3 mi W of IA 70 in Columbus Jct | 0.1 | Bridge Deck Overlay |  | 614000
Lucas
14 | 23-59-014-010 | At the Jct US 34 in Chariton | 0.0 | Bridge New |  |  |  | 4370000
|  |  |  | Right of Way |  |  |  | 10000
34 | 22-59-034-020 | BNSF RR 0.1 mi E of W Jct US 65 in Lucas | 0.0 | Bridge Deck Overlay |  |  |  | 1593000
34 | 22-59-034-030 | Russell Blvd, BNSF RR, and UP RR E of IA 14 in Chariton | 0.1 | Bridge Deck Overlay |  |  |  | 2465000
65 | 24-59-065-010 | Chariton River 2.2 mi N of Co Rd H50 | 0.0 | Bridge Deck Overlay |  |  |  |  | 650000
Mahaska
63 | 13-62-063-020 | NW Bypass of Oskaloosa | 17.3 | Erosion Control |  |  |  | 199000
Salvage & Removal
Right of Way
|  |  |  | Lighting |  |  | 185000
|  |  |  | Grading | 40746000
|  |  |  | Bridge New |  | 3239000
|  |  |  | Culvert New | 954000
|  |  |  | Paving |  |  | 21656000
|  |  |  | Traffic Signs |  |  | 399000
63 | 13-62-063-020-01 | Mitigation for NW Oskaloosa Bypass | 0.0 | Mitigation | 480000
Marion
5 | 18-63-005-020 | Walnut Creek 0.9 mi N of Co Rd G76 | 0.1 | Bridge Replacement | 1554000
|  |  |  | Right of Way | 5000
5 | 23-63-005-030 | English Creek 1.3 mi S of S Jct IA 92 | 0.0 | Bridge Deck Overlay |  |  |  | 630000
5 | 24-63-005-020 | At IA 14 Interchange in Knoxville (NB/SB) | 0.0 | Bridge Deck Overlay |  |  |  |  | 1820000
5 | 20-63-005-020 | White Breast Creek 2.7 mi N of IA 14 (NB) | 0.1 | Bridge Deck Overlay | 2010000
14 | 24-63-014-010 | N of Kermit Dr in Knoxville to Hayes Dr | 3.9 | Grade & Pave |  |  | 6894000
14 | 24-63-014-020 | Hayes Dr to N of Co Rd G28 | 3.4 | Grade & Pave |  |  |  | 5947000
14 | 19-63-014-030 | Brush Creek 0.2 mi S of Co Rd G28 | 0.2 | Bridge Replacement | 3751000
Right of Way
14 | 20-63-014-010 | Des Moines River 1.2 mi N of Co Rd G40 | 1.1 | Bridge Deck Overlay | 12020000
14 | 21-63-014-010 | White Breast Creek 2.1 mi S of Co Rd G40 | 0.1 | Bridge Deck Overlay |  | 1946000
14 | 21-63-014-020 | Teter Creek 0.2 mi S of Co Rd G40 | 0.1 | Bridge Deck Overlay |  | 746000
Monroe
34 | 21-68-034-030 | Coal Creek 2.0 mi W of IA 5 | 0.0 | Bridge Replacement |  |  | 3130000
|  |  |  | Right of Way |  | 0
34 | 22-68-034-010 | Cedar Creek 4.4 mi W of IA 5 | 0.0 | Bridge Rehabilitation |  |  | 1139000
137 | 23-68-137-010 | IA 5 to Heartland Dr near Eddyville | 13.1 | Pavement Rehab | 7451000
Muscatine
6 | 21-70-006-030 | E Branch Wapsinonoc Creek 0.5 mi E of IA 70 | 0.0 | Bridge Replacement |  | 1710000
|  |  |  | Right of Way |  | 5000
22 | 23-70-022-020 | Stream 0.2 mi E of Co Rd Y36 | 0.0 | Bridge New |  |  |  | 1250000
|  |  |  | Right of Way |  |  |  | 10000
22 | 22-70-022-010 | Pike Run Creek 1.2 mi E of IA 70 | 0.0 | Bridge Deck Overlay |  |  | 828000
22 | 24-70-022-010 | Pine Cree 0.1 mi E of Co Rd Y26 | 0.0 | Bridge Deck Overlay |  |  |  |  | 715000
38 | 22-70-038-010 | Mad Creek 0.6 mi N of US 61 | 0.0 | Bridge Rehabilitation |  |  | 1211000
38 | 24-70-038-020 | Mosquito Creek 2.2 mi S of US 6 | 0.0 | Bridge Deck Overlay |  |  |  |  | 650000
70 | 23-70-070-020 | Wapsinonoc Creek 1.1 mi S of US 6 | 0.0 | Bridge Deck Overlay |  |  |  | 570000
92 | 22-70-092-010 | Mississippi River in Muscatine |  | Bridge Rehabilitation |  |  | 3077000
92 | 16-70-092-010 | Mississippi River in Muscatine (State Share) | 0.6 | Bridge Washing | 50000 | 50000 | 49633 | 50000 | 50000
Statewide
0 | 24-00-000-080 | Various Counties and Routes in District 5 |  | Pavement Rehab | 708000
Van Buren
2 | 19-89-002-010 | Fox River 1.5 mi E of Co Rd V64 | 0.0 | Bridge Rehabilitation | 1524000
16 | 24-89-016-010 | W of Co Rd V64 to IA 1 | 7.5 | Pavement Rehab | 3629000
16 | 22-89-016-010 | Stump Creek 3.3 mi W of Co Rd V64 | 0.0 | Bridge Deck Overlay |  |  | 590000
Wapello
34 | 24-90-034-010 | In Ottumwa, Des Moines River Bridge to RR Bridge | 1.2 | Grade & Pave |  |  |  |  | 2339000
34 | 18-90-034-020 | South Avery Creek 0.7 mi E of Co Rd T61 | 0.1 | Bridge Replacement | 3207000
Right of Way
34 | 23-90-034-010 | Bear Creek and ICE RR 4.2 mi W of Co Rd H35 | 0.0 | Bridge New |  |  |  | 4990000
|  |  |  | Right of Way |  |  |  | 10000
63 | 21-90-063-010 | Abandoned RR 4.8 mi N of Co Rd J15 (Bridge Removal) | 0.0 | Grade & Pave |  | 1174000
|  |  |  | Right of Way |  | 5000
63 | 23-90-063-020 | Fudge Creek 4.3 mi S of IA 137 (NB/SB) | 0.0 | Bridge Deck Overlay |  |  |  | 640000
149 | 20-90-149-010 | Des Moines River Bridge to W Woodland Ave in Ottumwa | 0.7 | Grade & Pave |  |  | 5634000
Right of Way
149 | 22-90-149-030 | DME RR 3.9 mi N of US 34 (NB/SB) | 0.0 | Bridge New |  |  |  | 8127000
|  |  |  | Right of Way |  |  |  | 13000
149 | 22-90-149-010 | Des Moines River and BNSF RR N of US 34 in Ottumwa | 0.4 | Bridge Rehabilitation |  |  |  |  | 33798000
149 | 22-90-149-020 | Approx 0.24 mi S of N Court St in Ottumwa | 0.0 | Slope Improvement | 159783
Warren
35 | 00-91-035-030-05 | N of IA 92 to S of North River | 6.4 | Bridge Replacement
|  |  |  | Traffic Signs |  |  |  | 36000
Right of Way
|  |  |  | Grade & Pave |  |  |  | 11163000
35 | 00-91-035-030-06 | N of North River to S of Badger Creek | 4.8 | Bridge Replacement
|  |  |  | Traffic Signs |  | 19000
Right of Way
|  |  |  | Grade & Pave |  | 21290000
35 | 00-91-035-030-04 | 1.8 miles S of Co Rd G14 to 0.25 mi N of Adams St (NB) | 0.0 | Right of Way
|  |  |  | Grade & Pave |  |  | 32552000
|  |  |  | Traffic Signs |  |  | 1427000
35 | 24-91-035-020 | Clarke Co to Clanton Creek Bridge (NB/SB) | 11.3 | Pavement Rehab |  | 8000000
65 | 19-91-065-010 | Otter Creek 1.6 mi S of Co Rd G58 | 0.1 | Bridge Replacement | 2681000
Right of Way
92 | 23-91-092-010 | Stream 1.9 mi E of IA 28 | 0.0 | Culvert New |  |  |  | 940000
|  |  |  | Right of Way |  |  |  | 10000
Washington
22 | 23-92-022-010 | Smith Creek 3.6 mi W of IA 1 | 0.0 | Bridge Deck Overlay |  |  |  | 570000
22 | 24-92-022-020 | Iowa River Overflow 1.7 mi E of US 218 | 0.0 | Bridge Deck Overlay |  |  |  |  | 520000
22 | 22-92-022-010 | English River Overflow 2.5 mi W of IA 1 | 0.0 | Bridge Rehabilitation |  |  | 849000
92 | 85-92-092-010 | E of US 218 to IA 70 in Columbus Junction | 9.4 | Erosion Control | 270000
Right of Way
Culvert Replacement
Traffic Signs
Grade & Pave
218 | 22-92-218-010 | At the IA 22 Interchange (SB) | 0.0 | Bridge Deck Overlay |  |  | 1567000
Wayne
65 | 22-93-065-010 | Drainage Ditch 2.8 mi N of IA 2 | 0.0 | Culvert Repair |  |  | 167000

## Sheet2
2025 - 2029 Five Year Program
This information is valid for the date of Commission approval of None
Line Items
Project Estimated Costs X $1000
County | Location | Type Of Work | 2025 | 2026 | 2027 | 2028 | 2029
Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
Statewide | Statewide Interstate Lighting | Lighting | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
Statewide | Statewide Interstate Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 9800000 | 9900000 | 10000000 | 10100000 | 10200000
Statewide | Statewide Interstate Signing | Traffic Signs | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
Statewide | Statewide Interstate Pavement Maintenance | Pavement Rehab | 9500000 | 9500000 | 14500000 | 14500000 | 14500000
Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 15000000 | 15000000 | 15000000 | 15000000
Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 155000000 | 200000000 | 210000000 | 220000000
Statewide | Statewide Safety Specific | Paving | 0 | 34000000 | 35000000 | 36000000 | 37000000
Statewide | American with Disabilities Act | Miscellaneous | 4500000 | 5000000 | 5500000 | 6000000 | 6500000
Statewide | Construction Industry Training Program | Miscellaneous | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
Statewide | Cooperative City/County/State Highway Research | Miscellaneous | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Statewide | Emergency & Contingency (U-STEP/C-STEP) | Miscellaneous | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
Statewide | Post Letting Project Cost | Miscellaneous | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
Statewide | Prevocational Training and DBE Support Services | Miscellaneous | 360000 | 360000 | 360000 | 360000 | 360000
Statewide | Scenic Byway Program | Miscellaneous | 500000 | 500000 | 500000 | 500000 | 500000
Statewide | Statewide Consultant Services | Outside Services Engineering | 64000000 | 64000000 | 64000000 | 64000000 | 64000000
Statewide | Statewide Contract Maintenance | Miscellaneous | 37350000 | 37850000 | 38350000 | 43500000 | 44000000
Statewide | Statewide Railroad Crossings | Miscellaneous | 500000 | 500000 | 500000 | 500000 | 500000
Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Statewide | Statewide Traffic Control Devices/Signs | Traffic Signs | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Statewide | Statewide Operations | Outside Services Engineering | 12450000 | 12450000 | 12450000 | 12450000 | 12450000
Statewide | Statewide ITS | Miscellaneous | 5750000 | 5750000 | 5750000 | 5750000 | 5750000
Statewide | Winter Operations Materials | Miscellaneous | 15000000 | 15000000 | 15000000 | 15000000 | 15000000
Statewide | Summer Infrastructure Rehabilitation Materials | Miscellaneous | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
Statewide | Pavement Marking Materials | Miscellaneous | 5700000 | 7700000 | 7700000 | 7700000 | 7700000