## Sheet1
2026 - 2030 IOWA HIGHWAY PROGRAM
S.F 257 Only: No |  |  |  |  | Project Estimated Costs X $1000
Route | Project Code | Location | Miles | Type of Work | 2026 | 2027 | 2028 | 2029 | 2030
(08) Boone
30 | 25-08-030-010 | Co Rd R27/Corporal Roger Snedden Dr Intersection in Boone |  | Right of Way |  | 10000
|  |  |  | Mitigation |  | 1000000
|  |  |  | Grade & Pave |  | 1990000
169 | 22-08-169-020 | US 30 Interchange |  | Bridge Deck Overlay |  | 622000
210 | 17-08-210-010 | Des Moines River 0.3 mi E of Co Rd E62 | 0.2 | Bridge Rehabilitation | 3446000
930 | 25-08-930-010 | X Ave to Y Ave | 1.1 | Pavement Rehab | 1300000 | 1300000
(37) Greene
4 | 25-37-004-010 | Hardin Creek 1.2 mi N of US 30 |  | Bridge Deck Overlay |  |  |  |  | 1055000
30 | 21-37-030-010 | Buttrick Creek 2.8 mi W of IA 144 |  | Bridge Replacement |  | 1805000
(38) Grundy
175 | 24-38-175-010 | Branch Blackhawk Creek 0.8 mi W of Co Rd T69 |  | Bridge Deck Overlay |  |  |  | 455000
175 | 20-38-175-010 | Munns Creek 0.8 mi E of Co Rd T47 |  | Culvert Replacement | 1645000
(40) Hamilton
17 | 25-40-017-020 | Boone River 1.3 mi S of US 20 |  | Bridge Deck Overlay |  |  |  |  | 2605000
20 | 21-40-020-010 | Co Rd R38 Interchange |  | Bridge Deck Overlay | 749000
20 | 25-40-020-010 | US 69 to I-35 (WB) | 4 | Paving |  |  |  | 9794000
35 | 24-40-035-020 | 1 mi N of IA 175 to 1 mi N of Co Rd D41 (SB) | 6.1 | Pavement Rehab |  |  | 1440000
35 | 24-40-035-030 | Co Rd D25/220th St to 0.1 mi S of Co Rd R75 | 7.1 | Pavement Rehab |  |  | 9822000
(42) Hardin
175 | 21-42-175-020 | Iowa River 0.1 mi W of Co Rd S56 in Eldora | 0.1 | Bridge Deck Overlay | 1424000
(46) Humboldt
169 | 22-46-169-010 | W Fork Des Moines River 0.6 mi S of IA 3 in Humboldt |  | Bridge Rehabilitation |  | 2058000
(50) Jasper
6 | 23-50-006-020 | North Skunk River 1.3 mi E of IA 224 |  | Bridge Replacement |  |  | 6333000
|  |  |  | Right of Way |  |  | 60000
6 | 25-50-006-020 | IAIS RR 1.5 mi E of IA 224 |  | Bridge New |  |  |  |  | 4298000
|  |  |  | Right of Way |  |  |  |  | 5000
6 | 25-50-006-010 | 0.25 mi E of E 60th St |  | Culvert New |  |  | 995000
|  |  |  | Right of Way |  |  | 5000
14 | 24-50-014-030 | In Newton, I-80 to 0.25 mi N of 4th Ave | 1.7 | Grade & Pave |  |  |  | 9794000
14 | 24-50-014-020 | In Newton, N of 4th Ave to N of 23rd Ave | 1.5 | Grade & Pave |  |  | 5500000
65 | 23-50-065-010 | Indian Creek 0.2 mi S of IA 117 (NB) |  | Bridge Deck Overlay |  | 910000
80 | 25-50-080-030 | IAIS RR 0.4 mi W of IA 14 (EB/WB) |  | Bridge Rehabilitation |  |  |  | 4238000
80 | 25-50-080-040 | IA 14 Interchange - Ramps | 0.4 | Pavement Rehab |  |  |  |  | 1371000
117 | 22-50-117-010 | At the I-80 Interchange |  | Bridge Deck Overlay |  | 511000
(64) Marshall
30 | 25-64-030-020 | Durham Ave Intersection at State Center |  | Grade & Pave | 1500000
30 | 25-64-030-030 | Binford Ave Intersection approx. 2.5 mi W of State Center |  | Grade & Pave | 250000
330 | 22-64-330-010 | Clear Creek 1.8 mi S of Co Rd S52 |  | Bridge Deck Overlay |  | 486000
330 | 20-64-330-010 | Story Co Line to US 30 (Various Locations) | 29.5 | Pavement Rehab | 6300000
(77) Polk
6 | 19-77-006-020 | E of MLK Jr Pkwy to E of US 69/NE 14th St in Des Moines | 9.9 | Pavement Rehab | 1908000
28 | 25-77-028-030 | Raccoon River to I-235 | 2 | Pavement Rehab | 3220000
35 | 10-77-035-010-05 | I-35/235 Interchange NE of Des Moines to US 65 |  | Traffic Signs | 1695000 | 2290000
|  |  |  | Paving | 1300000
|  |  |  | Erosion Control |  |  | 300000
|  |  |  | Grade & Pave | 15890000 | 19000000
|  |  |  | Bridge Replacement | 4475000 | 7585000
|  |  |  | Bridge Widening | 3160000
35 | 16-77-035-050 | SW I-35/80/235 Interchange in West Des Moines | 4.4 | Right of Way | 80000
|  |  |  | Erosion Control |  |  |  | 400000
|  |  |  | Grade & Pave |  | 32000000 | 4400000
|  |  |  | Bridge New |  | 74390000
|  |  |  | Traffic Signs | 1105000 | 2450000 | 1000000
35 | 15-77-035-040-01 | N of NE 36th St in Ankeny to N of 315th St | 25.4 | Traffic Signs | 1000000
|  |  |  | Lighting | 420000
|  |  |  | Erosion Control |  | 1200000
|  |  |  | Grade & Pave | 49400000
|  |  |  | Culvert Extension | 601101.86
35 | 25-77-035-070 | SW I-80/I-235 Interchange - Various Ramps | 0.6 | Pavement Rehab |  |  |  |  | 997000
65 | 21-77-065-020 | US 6 Interchange 1.0 mi S of I-80 | 0.1 | Bridge Deck Overlay |  |  |  | 1813000
65 | 24-77-065-020 | At N IA 5 Interchange (NB/SB) |  | Bridge Deck Overlay |  |  |  | 2475000
65 | 24-77-065-030 | NE 46th Ave 1.2 mi S of I-80 (NB/SB) |  | Bridge Deck Overlay |  |  |  | 3515000
69 | 17-77-069-010 | DM River to N of Maury Ave in Des Moines (State Share) | 0.5 | Pavement Widening |  | 2900000
|  |  |  | Traffic Signals |  | 307000
|  |  |  | Right of Way | 110000
69 | 19-77-069-010 | Fourmile Creek 0.3 mi N of Co Rd F22 | 0.1 | Bridge Replacement | 2255000
69 | 20-77-069-030 | Des Moines River 1.4 mi S of I-235 in Des Moines | 0.1 | Bridge Replacement |  |  |  | 22616000
|  |  |  | Right of Way |  |  |  | 10000
69 | 24-77-069-010 | In Des Moines, from E Vine St to E Ovid Ave | 2.8 | Pavement Rehab | 3000000
69 | 20-77-069-010-01 | SE Peterson to 1st St in Ankeny | 0.8 | Grade & Pave | 4640000
|  |  |  | Right of Way | 1500000
|  |  |  | Grade & Pave | 2200000
69 | 25-77-069-030 | BN RR, Scott Ave, and MLK Pkwy 0.7 mi S of I-235 |  | Bridge New |  |  |  |  | 52091000
|  |  |  | Right of Way |  |  |  |  | 5000
80 | 20-77-080-020 | WB I-80 Ramp at W I-35/235 Interchange |  | Grade & Pave | 835000
80 | 24-77-080-050 | Mitchellville Rest Area 1.4 mi W of Co Rd S27 (EB) |  | Rest Area Improvement |  |  | 5125000
80 | 22-77-080-080 | Mitchellville Rest Area 1.4 mi W of Co Rd S27 (EB) | 0.6 | Right of Way |  |  | 382000
|  |  |  | Grade & Pave |  |  |  | 7899000
|  |  |  | Traffic Signs |  |  |  | 499000
|  |  |  | Lighting |  |  |  | 269000
80 | 15-77-080-060 | University Ave to N of Douglas Ave | 7 | Grade & Pave | 7096000 | 7418000
|  |  |  | Traffic Signs | 2187000 | 300000
|  |  |  | Bridge Widening | 644000
|  |  |  | Bridge Replacement | 9246000
|  |  |  | Lighting |  | 2870000
|  |  |  | Traffic Signals |  | 2499000
|  |  |  | Erosion Control |  |  | 200000
80 | 25-77-080-010 | 0.7 mi E of Co Rd S27 and 1.4 mi W of IA 117 | 4.2 | Grading | 186000
80 | 19-77-080-010 | Integrated Corridor Management Study for I-80, I-35, and I-235 in the Des Moines Metro Area | 268.2 | Guardrail |  | 500000
235 | 19-77-235-030 | SW I-35/80 Interchange to NE I-35/80 Interchange | 14.6 | Landscaping | 131000 | 137000 |  | 285000
235 | 25-77-235-020 | 0.1 mi E of 31st St to Hull Ave (EB/WB) | 5.4 | Pavement Rehab | 3180000
235 | 25-77-235-070 | 0.3 mi W of 73rd Street to 31st Street (WB) | 3 | Pavement Rehab |  |  |  |  | 4204000
235 | 25-77-235-080 | 0.3 mi W of 73rd Street to 31st Street (EB) | 3 | Pavement Rehab |  |  |  |  | 4204000
235 | 25-77-235-090 | 50th Street to 0.3 mi W of 73rd Street (EB/WB) | 3.4 | Pavement Rehab |  |  |  |  | 8270000
415 | 24-77-415-030 | Rock Creek 1.9 mi N of IA 160 |  | Bridge Deck Overlay |  |  |  | 1170000
(79) Poweshiek
6 | 23-79-006-010 | Stony Creek 0.4 mi W of W Jct Co Rd V18 |  | Bridge New |  |  | 2203000
|  |  |  | Right of Way |  |  | 10000
63 | 22-79-063-010 | Stream 4.4 mi N of Co Rd G17 |  | Culvert Replacement |  | 1558000
|  |  |  | Right of Way |  | 12000
63 | 19-79-063-020 | W Jct US 6 to SCL Tama | 28.5 | Erosion Control | 374000
80 | 22-79-080-010 | 50th St 2.1 mi E of IA 146 (EB/WB) |  | Bridge Deck Overlay |  | 3544000
80 | 23-79-080-010 | At US 63 Interchange (EB/WB) |  | Right of Way |  |  |  | 700000
|  |  |  | Bridge Replacement |  |  |  | 14000000 | 14000000
80 | 21-79-080-010 | W of IA 21 to E of IA 21 | 2 | Traffic Signs | 500000 | 357000 | 260000
|  |  |  | Lighting |  | 65000 | 65000
|  |  |  | Erosion Control |  |  |  | 300000
|  |  |  | Grade & Pave | 7461000 |  | 16935000
|  |  |  | Bridge Replacement | 2598000 |  | 3160000
|  |  |  | Paving | 8019000
80 | 25-79-080-020 | Co Rd V18 and Co Rd V38 Interchanges - Ramps | 9.2 | Pavement Rehab |  |  |  |  | 1122000
146 | 24-79-146-010 | North Skunk River 2.7 mi N of US 63 |  | Bridge New |  |  |  | 5200000
|  |  |  | Right of Way |  |  |  | 10000
(85) Story
30 | 23-85-030-010 | W Branch Indian Creek 0.5 mi E of Co Rd S14 (WB) |  | Bridge Deck Overlay |  | 898000
30 | 19-85-030-020 | South Skunk River from Duff Ave to Dayton Ave in Ames (EB/WB) | 15.8 | Bridge Replacement | 4783000 | 5605000
|  |  |  | Erosion Control |  |  | 350000
|  |  |  | Grade & Pave | 4980000 | 2771000
|  |  |  | Traffic Signs | 750000 | 200000
|  |  |  | Culvert New | 1374000 | 1820000
|  |  |  | Lighting | 250000 | 216000
30 | 13-85-030-010-01 | 610th Ave Interchange at Nevada | 1.7 | Right of Way |  | 9750000
|  |  |  | Erosion Control |  |  |  |  | 366000
|  |  |  | Grading |  |  |  | 7219000
|  |  |  | Bridge New |  |  |  | 3614000
|  |  |  | Paving |  |  |  |  | 9502000
|  |  |  | Traffic Signs |  |  | 300000 | 125000 | 375000
|  |  |  | Lighting |  |  |  |  | 180000
35 | 11-85-035-020-04 | 0.5 mi N of Co Rd E57/260th St to 0.6 mi N of US 30 | 1.9 | Right of Way |  |  | 5900000
|  |  |  | Lighting |  |  |  |  | 450000
|  |  |  | Bridge Replacement |  |  |  |  | 6113000
|  |  |  | Grade & Pave |  |  |  | 12886000 | 15247000
|  |  |  | Traffic Signs |  |  |  | 600000 | 750000
35 | 25-85-035-010 | N of IA 210 to Co Rd C47 | 55.9 | Pavement Markings | 400000
35 | 25-85-035-020 | 13th St Interchange 1.8 mi N of US 30 in Ames (NB/SB) |  | Bridge Deck Overlay |  |  |  |  | 2345000
65 | 25-85-065-010 | 0.2 mi S of 310th St in Collins |  | Culvert New |  |  | 245000
|  |  |  | Right of Way |  |  | 5000
65 | 25-85-065-020 | 0.2 mi S of Co Rd E41 in Colo |  | Culvert New |  |  | 245000
|  |  |  | Right of Way |  |  | 5000
(86) Tama
63 | 21-86-063-030 | Iowa River 1.3 mi N of Co Rd E64 | 0.1 | Bridge Deck Overlay |  | 2853000
63 | 20-86-063-010 | NCL Toledo to 0.5 mi S of IA 96 | 23.5 | Erosion Control |  | 250000
|  |  |  | Grade & Pave | 6700000
|  |  |  | Pavement Rehab | 8700000
|  |  |  | Traffic Signs | 50000
(91) Warren
5 | 19-91-005-030-90 | Mitigation - South River Bridge |  | Mitigation | 111000
5 | 19-91-005-030 | South River 0.2 mi N of Co Rd S31 (NB) | 0.2 | Bridge Replacement | 5755000
65 | 22-91-065-010 | Stream 0.2 mi N of Co Rd G24 (NB) |  | Bridge Replacement |  | 1956000
|  |  |  | Right of Way |  | 5000
(94) Webster
144 | 22-94-144-010 | East Buttrick Creek 2.2 mi S of IA 175 |  | Culvert Replacement |  | 960000
|  |  |  | Right of Way |  | 210000
|  |  |  | Mitigation |  | 94000
169 | 22-94-169-020 | Bass Creek 0.6 mi S of Co Rd C56 |  | Culvert Replacement |  |  | 742000
|  |  |  | Right of Way |  |  | 17000
169 | 20-94-169-010 | E Jct IA 175 to S of US 20 | 31.4 | Pavement Rehab | 8300000
175 | 20-94-175-030 | Ditch #52 0.8 mi E of Co Rd P29 |  | Culvert Replacement | 750000
175 | 20-94-175-020 | Des Moines River 1.8 mi E of Co Rd P70 |  | Bridge Replacement |  |  | 13651000
|  |  |  | Right of Way |  |  | 119000
(99) Wright
35 | 24-99-035-010 | 0.1 mi S of Co Rd R75 to 0.6 mi N of Co Rd C47 (NB/SB) | 9.8 | Pavement Rehab |  |  |  | 12680000

## Sheet2
2026 - 2030 Five Year Program
This information is valid for the date of Commission approval of 06/10/2025
Line Items
Project Estimated Costs X $1000
| County | Location | Type Of Work | 2026 | 2027 | 2028 | 2029 | 2030
| Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide Interstate Lighting | Lighting | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
| Statewide | Statewide Interstate Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 9900000 | 10000000 | 10100000 | 10200000 | 10300000
| Statewide | Statewide Interstate Signing | Traffic Signs | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
| Statewide | Statewide Interstate Pavement Maintenance | Pavement Rehab | 9500000 | 14500000 | 14500000 | 14500000 | 14500000
| Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 166700000 | 155900000 | 185500000 | 192500000
| Statewide | Statewide Safety Specific | Paving | 0 | 35000000 | 36000000 | 37000000 | 38000000
| Statewide | American with Disabilities Act | Pedestrian Improvement | 5000000 | 5500000 | 6000000 | 6500000 | 7000000
| Statewide | Construction Industry Training Program | Training | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
| Statewide | Cooperative City/County/State Highway Research | Research | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Emergency & Contingency (U-STEP/C-STEP) | Construction | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
| Statewide | Post Letting Project Cost | Construction | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
| Statewide | Prevocational Training and DBE Support Services | Training | 360000 | 360000 | 360000 | 360000 | 360000
| Statewide | Scenic Byway Program | Signs | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Consultant Services | Outside Services Engineering | 72000000 | 74000000 | 74000000 | 74000000 | 74000000
| Statewide | Statewide Contract Maintenance | Construction | 42850000 | 43350000 | 48500000 | 49000000 | 49500000
| Statewide | Statewide Railroad Crossings | Construction | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Statewide Traffic Control Devices/Signs/Lighting | Traffic Signs and Lighting | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
| Statewide | Statewide Operations | Outside Services Engineering | 16000000 | 16000000 | 16000000 | 16000000 | 16000000
| Statewide | Statewide ITS | Equipment | 8000000 | 8000000 | 8000000 | 8000000 | 8000000
| Statewide | Winter Operations Materials | Materials | 15000000 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Summer Infrastructure Rehabilitation Materials | Materials | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
| Statewide | Pavement Marking Materials | Paint | 7700000 | 7700000 | 7700000 | 7700000 | 7700000