## Sheet1
2026 - 2030 IOWA HIGHWAY PROGRAM
S.F 257 Only: No |  |  |  |  | Project Estimated Costs X $1000
Route | Project Code | Location | Miles | Type of Work | 2026 | 2027 | 2028 | 2029 | 2030
(03) Allamakee
9 | 16-03-009-020 | Mississippi River in Lansing (State Share) | 0.4 | Bridge Washing |  |  | 20000 | 19853.29 | 20000
9 | 24-03-009-020 | In Lansing, North 7th Street to near Hale Street | 0.8 | Grade & Pave |  | 3161000
9 | 16-03-009-010 | Mississippi River in Lansing (State Share) | 0.7 | Traffic Signs | 270000
76 | 21-03-076-020 | Yellow River 3.0 mi S of Co Rd X52 | 0.1 | Bridge Deck Overlay | 1107000
(07) Black Hawk
20 | 24-07-020-020 | At IA 27/IA 58 Interchange in Cedar Falls (EB/WB) |  | Bridge Deck Overlay |  | 1300000
20 | 17-07-020-010 | IA 21 to E I-380 Interchange |  | Traffic Signs | 1692000
20 | 24-07-020-030 | At W I-380/US 218 Interchange in Waterloo (EB/WB) |  | Bridge Deck Overlay |  | 2340000
20 | 16-07-020-030 | Hudson Rd to US 63 (EB/WB) | 3.1 | Traffic Signs | 1443000
|  |  |  | Paving | 24670000
27 | 12-07-058-010-01 | Greenhill Rd in Cedar Falls (State Share) | 1.3 | Erosion Control |  |  |  |  | 261000
|  |  |  | Mitigation |  |  | 314000
|  |  |  | Right of Way |  | 1747000
|  |  |  | Bridge New |  |  | 3628000
|  |  |  | Culvert Extension |  |  | 743000
|  |  |  | Traffic Signs |  |  | 205000
|  |  |  | Lighting |  |  | 434000
|  |  |  | Traffic Signals |  |  | 68000
|  |  |  | Culvert Replacement |  |  | 1644000
|  |  |  | Culvert New |  |  | 1090000
|  |  |  | Noise Wall |  |  | 4403000
|  |  |  | Grade & Pave |  |  | 44755000
57 | 24-07-057-010 | Union Rd Intersection in Cedar Falls |  | Grade & Pave | 750000
218 | 23-07-218-040 | NB 218 to SB IA 27/58 (Ramp J) N of IA 57 in Waterloo |  | Bridge Deck Overlay | 2362000
218 | 21-07-218-050 | Big Creek Overflow 0.3 mi N of Co Rd D48 in La Porte City |  | Bridge Replacement | 2243000
|  |  |  | Right of Way | 10000
|  |  |  | Mitigation | 20000
218 | 24-07-218-010 | Fletcher Ave 0.6 mi N of US 63 in Waterloo (NB/SB) |  | Bridge Deck Overlay |  |  | 2240000
218 | 22-07-218-030 | Cedar River and Trail 2.9 mi S of IA 57 in Waterloo |  | Bridge Deck Overlay |  | 5450000
218 | 25-07-218-010 | W US 63 Interchange to Cedar River Bridge in Waterloo (NB/SB) | 2.5 | Pavement Rehab | 3001000
218 | 25-07-218-020 | George Wythe State Park to the IA 27/IA 57/IA 58 Interchange (SB) | 1.3 | Paving | 1197000
281 | 22-07-281-010 | Elk Run Creek 0.3 mi E of Co Rd V43 |  | Bridge Replacement |  | 474000
|  |  |  | Right of Way |  | 11000
281 | 25-07-281-010 | Wapsie River Overflow 2.7 mi W of Co Rd V62 |  | Bridge New |  |  |  |  | 3061000
|  |  |  | Right of Way |  |  |  |  | 5000
380 | 22-07-380-040 | Southbound Flyover Ramp at N US 20 Interchange |  | Bridge Painting |  |  | 2190000
(09) Bremer
3 | 23-09-003-010 | Drainage Ditch 2.1 mi W of Co Rd V56 |  | Bridge Deck Overlay |  |  | 615000
3 | 25-09-003-010 | Crane Creek 3.4 mi E of US 63 |  | Bridge New |  |  |  |  | 4038000
|  |  |  | Right of Way |  |  |  |  | 5000
93 | 23-09-093-010 | Stream 0.7 mi W of Co Rd V62 in Sumner |  | Bridge Replacement |  |  | 1870000
|  |  |  | Right of Way |  |  | 10000
188 | 25-09-188-010 | Crane Creek 1.0 mi W of US 63 |  | Bridge New |  |  |  |  | 1693000
|  |  |  | Right of Way |  |  |  |  | 5000
218 | 06-07-218-010-02 | Cedar River in Janesville to IA 116 in Waverly | 7.7 | Erosion Control |  | 456000
|  |  |  | Grade & Pave | 19357000
|  |  |  | Traffic Signs | 355000
|  |  |  | Lighting | 118000
(12) Butler
3 | 23-12-003-010 | Boylan Creek 2.4 mi E of Co Rd T16 |  | Bridge New |  |  | 5509000
|  |  |  | Right of Way |  |  | 10000
|  |  |  | Mitigation |  |  | 165000
3 | 19-12-003-010 | Hartgraves Creek Overflow 0.5 mi W of Co Rd T16 | 0.2 | Culvert New | 4865000
57 | 24-12-057-020 | Beaver Creek 1.3 mi E of Co Rd T53 |  | Bridge New |  |  |  | 1300000
|  |  |  | Right of Way |  |  |  | 10000
57 | 24-12-057-010 | Co Rd T47 to New Hartford | 5.8 | Grade & Pave |  |  | 12599000
188 | 25-12-188-010 | Dry Run Creek 3.4 mi W of US 218 |  | Bridge Rehabilitation |  |  |  |  | 1954000
(17) Cerro Gordo
18 | 24-17-018-030 | Winnebago River & Road 0.7 mi Ee of Co Rd S56 |  | Bridge Deck Overlay |  |  |  | 1560000
35 | 23-17-035-010 | Bailey Creek 2.7 mi N of Co Rd C13 (NB/SB) |  | Bridge Deck Overlay |  |  | 1285000
35 | 23-17-035-020 | Co Rd B35 2.4 mi S of N Jct US 18 (NB/SB) |  | Bridge Deck Overlay |  |  | 1519000
35 | 22-17-035-040 | Winnebago River 2.3 mi S of IA 9 (NB/SB) |  | Bridge Deck Overlay |  | 1520000
35 | 24-17-035-010 | 3 mi N of Co Rd B60 to 1 mi N of Co Rd B35 (NB/SB) | 7.2 | Pavement Rehab |  |  | 14126000
35 | 24-17-035-020 | Franklin Co to 3 mi N of Co Rd B60 (NB/SB) | 8.1 | Pavement Rehab |  |  |  | 16540000
35 | 25-17-035-020 | NCL of Clear Lake to 0.7 mi S of Co Rd B20 (NB/SB) | 2.3 | Pavement Rehab |  |  |  |  | 5309000
65 | 23-17-065-010 | Willow Creek 0.1 mi N of WB IA 122 in Mason City |  | Bridge Deck Overlay |  | 1289000
65 | 20-17-065-010 | West Fork Cedar River 2.6 mi N of Co Rd C13 | 0.1 | Bridge Replacement | 3717000
|  |  |  | Right of Way | 44000
65 | 20-17-065-010-01 | Wetland Bank for Cerro Gordo Co US 65 Bridge | 0.1 | Mitigation | 66000
65 | 25-17-065-040 | Spring Creek 0.3 mi N of Co Rd B15 |  | Bridge New |  |  |  |  | 4884000
|  |  |  | Right of Way |  |  |  |  | 5000
122 | 22-17-122-010 | Ideal Creek 1.2 mi W of Co Rd S56 in Mason City |  | Bridge Deck Overlay |  | 322000
(19) Chickasaw
18 | 21-19-018-010 | Little Cedar River 1.0 mi. E. of Co Rd T74 | 0.1 | Bridge Replacement |  |  | 5792000
|  |  |  | Right of Way | 5000
24 | 25-19-024-010 | In New Hampton, from 400 ft E of Water Ave to the ECL | 2.1 | Pavement Rehab | 985000
63 | 21-19-063-010 | E Fork Wapsipinicon River 2.1 mi N of US 18 |  | Bridge Rehabilitation | 1060000
(22) Clayton
13 | 25-22-013-010 | NCL Strawberry Point to IA 56 near Elkader - Various | 13.1 | Grading | 273000
|  |  |  | Right of Way | 2000
18 | 16-22-018-010 | Mississippi River in Marquette (State Share) | 0.4 | Bridge Washing | 20000 | 19853.29 | 20000 | 20000 | 20000
52 | 25-22-052-020 | S of Weiland St in Guttenberg |  | Grading | 156000
|  |  |  | Right of Way | 2000
(32) Emmet
15 | 22-32-015-010 | Black Cat Creek 6.5 mi S of IA 9 |  | Bridge Deck Overlay |  | 794000
(33) Fayette
18 | 21-33-018-010 | Drainage Ditch 0.1 mi W of Co Rd W14 |  | Bridge Deck Overlay | 296000
93 | 21-33-093-010 | Coulee Creek 1.4 mi W of IA 150 |  | Bridge Deck Overlay | 668000
93 | 19-33-093-010 | Stream 0.7 mi W of Co Rd V68 |  | Culvert Replacement | 849000
150 | 22-33-150-020 | Otter Creek 0.2 mi N of IA 56 in West Union |  | Bridge Deck Overlay |  | 1148000
187 | 22-33-187-010 | Brush Creek 0.5 mi W of Co Rd W51 |  | Bridge Replacement |  | 1712000
|  |  |  | Right of Way |  | 11000
(34) Floyd
18 | 22-34-018-010 | Shell Rock River and Red Ball Rd 1.5 mi E of Co Rd S70 |  | Bridge Rail Retrofit |  | 1283000
18 | 25-34-018-010 | Near Co Rd B30 to Floyd Interchange (WB/EB) | 6.8 | Paved Shoulders | 2730000
|  |  |  | Paved Shoulders | 472000
18 | 25-34-018-020 | IA Northern RR and Stream 1.1 mi E of Co Rd S70 (EB/WB) |  | Bridge Rail Retrofit |  |  |  |  | 2084000
(35) Franklin
3 | 22-35-003-020 | Beeds Creek 0.4 mi W of Co Rd S56 |  | Bridge Replacement |  | 1172000
35 | 22-35-035-020 | At the Co Rd C25 Interchange |  | Bridge Deck Overlay |  | 892000
35 | 25-35-035-050 | Co Rd C47 to Minnesota State Line | 58.6 | Pavement Markings | 1010000
35 | 25-35-035-010 | 0.5 mi S of Co Rd C23 to Cerro Gordo Co Line (NB) | 5.6 | Paving | 15583000
65 | 24-35-065-010 | Maynes Creek 0.1 mi N of Co Rd C47 |  | Bridge Deck Overlay |  |  |  | 676000
(41) Hancock
18 | 23-41-018-020 | 0.4 mi W of Crane Ave |  | Culvert Replacement |  | 407000
18 | 25-41-018-010 | 2.17 mi E of Co Rd R35 to W Jct US 69 | 6.4 | Pavement Widening |  | 1500000
69 | 24-41-069-010 | Drainage Ditch 2.7 mi S of US 18 |  | Bridge New |  |  |  | 975000
|  |  |  | Right of Way |  |  |  | 10000
(45) Howard
63 | 24-45-063-010 | Turkey River 2.5 mi S of IA 9 |  | Bridge Deck Overlay |  |  |  | 520000
(55) Kossuth
169 | 21-55-169-020 | Blue Earth River 0.5 mi S of Co Rd A16 |  | Bridge Deck Overlay | 322000
169 | 24-55-169-020 | In Algona, S of E Maple Place to 0.6 miles north of US 18 | 0.6 | Grade & Pave |  |  |  |  | 6983000
(66) Mitchell
9 | 25-66-009-010 | 0.2 mi W of US 218 to Wapsipinicon River in Riceville | 13.4 | Pavement Rehab | 9569000
218 | 24-66-218-010 | Otter Creek 2.6 mi N of Co Rd A19 |  | Bridge Deck Overlay |  |  |  | 650000
(95) Winnebago
69 | 25-95-069-020 | Lime Creek 1.2 mi N of Co Rd R60 |  | Bridge Deck Overlay |  |  |  |  | 521000
(96) Winneshiek
9 | 23-96-009-020 | Division St 0.6 mi E of IA 52 in Decorah |  | Bridge Deck Overlay | 1131000
9 | 24-96-009-010 | In Decorah, from US 52 to near Pleasant Ave | 0.9 | Paving | 7474000
24 | 24-96-024-010 | Goddard Creek 1.8 mi W of Co Rd W14 |  | Bridge New |  |  |  | 1300000
|  |  |  | Right of Way |  |  |  | 10000
52 | 24-96-052-030 | Dry Run 0.3 mi N of IA 9 |  | Bridge Deck Overlay |  |  |  | 650000
(98) Worth
35 | 24-98-035-040 | 2 mi N of Co Rd 105 to Minnesota State Line (NB/SB) | 2 | Pavement Rehab |  |  | 549000
35 | 22-98-035-050 | At the Co Rd A38 Interchange |  | Bridge Deck Overlay |  | 824000
35 | 22-98-035-010 | SB Weigh Station 3.2 mi N of Co Rd A38 |  | Paving |  | 1446000
35 | 22-98-035-040 | 1.0 mi N of IA 9 to 0.15 mi N of 450th St | 8.3 | Pavement Rehab | 2456000
35 | 24-98-035-030 | UP RR Bridge to 1 mi N of IA 9 (NB/SB) | 2 | Pavement Rehab |  |  | 4112000
35 | 22-98-035-030 | 435th St to 2.0 mi N of Co Rd 105 | 5.3 | Pavement Rehab | 5994000
(99) Wright
3 | 21-99-003-010 | Eagle Creek 5.3 mi E of E Jct IA 17 |  | Bridge Replacement | 1352000
|  |  |  | Right of Way | 5000
3 | 23-99-003-020 | E Jct US 69 to Franklin Co Line | 11 | Pavement Rehab | 4931000
3 | 25-99-003-020 | Stream 2.7 mi E of E Jct US 69 |  | Bridge Deck Overlay |  |  |  |  | 1075000
3 | 25-99-003-030 | 0.5 mi W of Clarion |  | Right of Way |  |  | 5000
|  |  |  | Grading |  |  | 130000
69 | 21-99-069-010 | Iowa River 1.4 mi S of S Jct Co Rd C20 in Belmond |  | Bridge Replacement |  |  | 4875000

## Sheet2
2026 - 2030 Five Year Program
This information is valid for the date of Commission approval of 06/10/2025
Line Items
Project Estimated Costs X $1000
| County | Location | Type Of Work | 2026 | 2027 | 2028 | 2029 | 2030
| Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide Interstate Lighting | Lighting | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
| Statewide | Statewide Interstate Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 9900000 | 10000000 | 10100000 | 10200000 | 10300000
| Statewide | Statewide Interstate Signing | Traffic Signs | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
| Statewide | Statewide Interstate Pavement Maintenance | Pavement Rehab | 9500000 | 14500000 | 14500000 | 14500000 | 14500000
| Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 166700000 | 155900000 | 185500000 | 192500000
| Statewide | Statewide Safety Specific | Paving | 0 | 35000000 | 36000000 | 37000000 | 38000000
| Statewide | American with Disabilities Act | Pedestrian Improvement | 5000000 | 5500000 | 6000000 | 6500000 | 7000000
| Statewide | Construction Industry Training Program | Training | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
| Statewide | Cooperative City/County/State Highway Research | Research | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Emergency & Contingency (U-STEP/C-STEP) | Construction | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
| Statewide | Post Letting Project Cost | Construction | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
| Statewide | Prevocational Training and DBE Support Services | Training | 360000 | 360000 | 360000 | 360000 | 360000
| Statewide | Scenic Byway Program | Signs | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Consultant Services | Outside Services Engineering | 72000000 | 74000000 | 74000000 | 74000000 | 74000000
| Statewide | Statewide Contract Maintenance | Construction | 42850000 | 43350000 | 48500000 | 49000000 | 49500000
| Statewide | Statewide Railroad Crossings | Construction | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Statewide Traffic Control Devices/Signs/Lighting | Traffic Signs and Lighting | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
| Statewide | Statewide Operations | Outside Services Engineering | 16000000 | 16000000 | 16000000 | 16000000 | 16000000
| Statewide | Statewide ITS | Equipment | 8000000 | 8000000 | 8000000 | 8000000 | 8000000
| Statewide | Winter Operations Materials | Materials | 15000000 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Summer Infrastructure Rehabilitation Materials | Materials | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
| Statewide | Pavement Marking Materials | Paint | 7700000 | 7700000 | 7700000 | 7700000 | 7700000