## Sheet1
2026 - 2030 IOWA HIGHWAY PROGRAM
S.F 257 Only: No |  |  |  |  | Project Estimated Costs X $1000
Route | Project Code | Location | Miles | Type of Work | 2026 | 2027 | 2028 | 2029 | 2030
(11) Buena Vista
71 | 22-11-071-010 | Little Sioux River 2.0 mi S of N Jct IA 10 |  | Bridge Rehabilitation | 2757000
(14) Carroll
71 | 22-14-071-010 | UP RR and Local Streets 0.2 mi S of US 30 in Carroll |  | Bridge Deck Overlay |  |  | 2009000
71 | 24-14-071-030 | N of E Jct IA 141 to Middle Raccoon River in Carroll | 10.6 | Patching | 1524000
71 | 24-14-071-020 | 0.5 mi S of Co Rd E25 to Sac Co | 7.6 | Grade & Pave |  |  |  |  | 18109000
(18) Cherokee
3 | 24-18-003-010 | Fork Little Sioux River 2.5 mi E of IA 143 |  | Bridge Deck Overlay |  |  |  | 650000
3 | 22-18-003-010 | IA 143 Intersection in Marcus |  | Grade & Pave | 4230000
|  |  |  | Traffic Signs | 150000
|  |  |  | Lighting | 120000
|  |  |  | Right of Way | 50000
31 | 24-18-031-010 | Stratton Creek 0.1 mi N of Co Rd C66 |  | Bridge New |  |  |  | 975000
|  |  |  | Right of Way |  |  |  | 5000
31 | 20-18-031-010 | Silver Creek 1.0 mi W of US 59 |  | Bridge Replacement | 1990000
|  |  |  | Right of Way | 5000
59 | 24-18-059-010 | Grey Creek 2.1 mi N of Co Rd C16 |  | Bridge Deck Overlay |  |  |  | 455000
(21) Clay
18 | 23-21-018-010 | Little Sioux River 2.1 mi W of W Jct US 71 |  | Bridge Replacement |  |  | 2500000
|  |  |  | Right of Way |  |  | 10000
71 | 21-21-071-010 | Branch of Little Meadow Creek 0.8 mi N of N Jct US 18 |  | Bridge Deck Overlay | 196000
71 | 21-21-071-020 | Willow Creek 3.4 mi N of N Jct IA 10 |  | Bridge Replacement | 2479000
|  |  |  | Right of Way | 23853.25
(24) Crawford
30 | 20-24-030-010 | Boyer River 2.7 mi W of US 59 | 0.1 | Bridge Replacement |  |  | 3726000
30 | 22-24-030-010 | UP RR 0.4 mi E of W Jct US 59 in Denison (EB/WB) |  | Bridge Replacement |  |  |  | 17182000
|  |  |  | Right of Way |  |  |  | 12000
30 | 25-24-030-020 | Flasher Creek 5.6 mi N of IA 37 |  | Bridge Deck Overlay |  |  |  |  | 652000
39 | 20-24-039-010 | East Otter Creek 0.4 mi E of Co Rd M35 |  | Bridge Replacement | 1873000
|  |  |  | Right of Way | 1000
39 | 25-24-039-010 | Otter Creek 5.6 mi N of US 59 |  | Bridge New |  |  |  |  | 3256000
|  |  |  | Right of Way |  |  |  |  | 5000
59 | 22-24-059-020 | Boyer River 0.1 mi S of IA 39 in Denison (SB) |  | Bridge Deck Overlay |  | 1068000
59 | 25-24-059-020 | CC RR 0.4 mi S of IA 39 (NB/SB) |  | Right of Way |  |  |  |  | 5000
141 | 25-24-141-010 | Emigrant Creek 2.1 mi W of Co Rd M 14 |  | Bridge Deck Overlay |  |  |  |  | 977000
(30) Dickinson
9 | 21-30-009-020 | W Fork Little Sioux River 4.9 mi W of IA 86 |  | Bridge Replacement | 2121000
9 | 25-30-009-020 | Osceola Co to IA 86 | 10.2 | Pavement Rehab | 8212000
71 | 24-30-071-020 | E Jct IA 9 to Minnesota State Line | 4.9 | Pavement Rehab | 1213000
(32) Emmet
4 | 22-32-004-020 | Drainage Ditch 1.5 mi N of N Jct Co Rd A34 |  | Bridge Deck Overlay |  | 737000
4 | 25-32-004-010 | 0.6 mi N of 190th St |  | Grading | 250000
9 | 24-32-009-010 | In Estherville, Des Moines River Bridge to S 28th St | 1.8 | Grade & Pave |  |  | 8025000
9 | 25-32-009-010 | Des Moines River 0.6 mi W of IA 4 |  | Bridge Deck Overlay |  |  |  |  | 2865000
(43) Harrison
37 | 21-43-037-010 | Boyer River 0.1 mi W of US 30 | 0.1 | Bridge Replacement |  |  | 5369000
|  |  |  | Right of Way |  |  | 11000
(47) Ida
31 | 24-47-031-010 | Ashton Creek 1.0 mi N of Co Rd D15 |  | Bridge Deck Overlay |  |  |  | 520000
175 | 21-47-175-010 | Morehead Creek 2.6 mi W of W Jct Co Rd L51 |  | Bridge Deck Overlay | 431000
(60) Lyon
9 | 24-60-009-030 | Approx 1.4 mi W of Co Rd K60 |  | Culvert Replacement |  | 400000
|  |  |  | Right of Way |  | 10000
9 | 18-60-009-010 | South Dakota east 0.5 mi |  | Grade & Pave |  | 512000
9 | 24-60-009-040 | Little Rock River 1.0 mi W of Co Rd L26 |  | Bridge Deck Overlay |  |  |  |  | 975000
75 | 21-60-075-010 | Little Rock River 0.4 mi S of Co Rd A44 |  | Bridge Rehabilitation | 759000
(67) Monona
29 | 20-67-029-030 | Co Rd E24 Interchange |  | Bridge Deck Overlay | 1084000
29 | 22-67-029-020 | Onawa Rest Area 2.6 mi S of IA 175 (SB |  | Rest Area Improvement |  |  |  | 4500000
29 | 24-67-029-060 | Onawa Rest Area 2.6 mi S of IA 175 (NB) |  | Rest Area Improvement |  | 5125000
29 | 24-67-029-050 | Onawa Rest Area 2.6 mi S of IA 175 (NB) | 0.7 | Grade & Pave | 7050000
|  |  |  | Traffic Signs | 164000
|  |  |  | Lighting | 164000
29 | 22-67-029-040 | N of Co Rd E60 to IA 175 (SB) | 7.7 | Paving |  |  | 26199000
37 | 22-67-037-010 | Norway Creek 2.6 mi E of IA 183 |  | Bridge Deck Overlay |  | 750000
37 | 24-67-037-010 | Beaver Creek 4.4 mi E of IA 175 |  | Bridge Replacement |  |  |  | 3250000
|  |  |  | Right of Way |  |  |  | 12000
37 | 24-67-037-020 | IA 175 to IA 183 in Soldier | 9.7 | Pavement Rehab | 1146000
141 | 24-67-141-030 | Soldier River 3.9 mi W of IA 183 |  | Bridge New |  |  |  | 4264000
|  |  |  | Right of Way |  |  |  | 5000
141 | 23-67-141-010 | Maple River 0.1 mi E of W Jct IA 175 in Mapleton |  | Bridge Replacement |  |  | 4627000
|  |  |  | Right of Way |  |  | 12000
175 | 16-67-175-010 | Missouri River E of Decatur Nebraska (State Share) |  | Bridge Rehabilitation | 111000 | 111000 | 111000 | 111000 | 111000
175 | 20-67-175-020 | Little Sioux River 1.5 mi W of IA 37 |  | Bridge Replacement |  | 5574000
|  |  |  | Right of Way | 11000
175 | 13-67-175-010 | Missouri River E of Decatur Nebraska (State Share) | 0.3 | Bridge Washing | 22000 | 22000 | 22000 | 22000 | 22000
175 | 21-67-175-020 | I-29 Interchange |  | Grade & Pave | 24568000
|  |  |  | Bridge Replacement | 4761000
|  |  |  | Traffic Signs | 623000
|  |  |  | Lighting | 418000
|  |  |  | Erosion Control |  | 200000
183 | 24-67-183-020 | Jordan Creek 0.8 mi S of Co Rd E54 |  | Bridge Deck Overlay |  |  |  | 520000
(71) O'Brien
10 | 21-71-010-010 | Dry Run 0.2 mi W of W Jct US 59 |  | Bridge Deck Overlay | 838000
18 | 24-71-018-030 | Stream 0.2 mi W of Co Rd M22 |  | Culvert New |  |  |  | 1550000
|  |  |  | Right of Way |  |  |  | 5000
18 | 24-71-018-050 | ECL Hartley to Clay County Line | 3.9 | Pavement Rehab | 465000
18 | 23-71-018-010 | In Sheldon, from B St to 0.3 mi E of IA 60 | 1.4 | Miscellaneous | 500000
(72) Osceola
9 | 24-72-009-020 | Otter Creek 2.5 mi W of Co Rd L40 |  | Bridge Deck Overlay |  |  |  | 130000
9 | 24-72-009-030 | Polly Creek 0.9 mi W of IA 60 |  | Bridge New |  |  |  | 775000
|  |  |  | Right of Way |  |  |  | 7000
59 | 24-72-059-010 | Approx 0.2 mi S of 250th St |  | Culvert Replacement |  | 500000
|  |  |  | Right of Way |  | 10000
59 | 21-72-059-010 | Drainage Ditch 1.1 mi N of Co Rd A46 |  | Bridge Deck Overlay | 604000
59 | 24-72-059-020 | Approx 0.9 mi n of Co Rd A22 |  | Culvert Replacement |  | 800000
|  |  |  | Right of Way |  | 10000
60 | 23-72-060-030 | Drainage Ditch 2.6 mi N of Co Rd B14 (SB) |  | Bridge New |  |  | 1250000
|  |  |  | Right of Way |  |  | 10000
60 | 21-72-060-010 | Drainage Ditch 1.1 mi S of Co Rd L36 (SB) |  | Culvert Replacement | 1603000
|  |  |  | Right of Way | 5000
(74) Palo Alto
4 | 22-74-004-010 | Drainage Ditch 1.3 mi S of Co Rd B57 |  | Bridge Replacement |  |  | 1224000
4 | 21-74-004-020 | W Fork Des Moines River 3.2 mi S of S Jct US 18 | 0.1 | Bridge Replacement |  |  | 7133000
18 | 21-74-018-020 | Superior St to Huron St in Emmetsburg | 13.1 | Pavement Rehab | 782000
18 | 25-74-018-070 | Side Ditch Bridge 2.0 mi W of IA 4 |  | Bridge New |  |  |  |  | 652000
|  |  |  | Right of Way |  |  |  |  | 5000
(75) Plymouth
3 | 24-75-003-030 | Big Sioux Overflow 1.0 mi W of IA 12 |  | Bridge New |  |  |  |  | 2475000
|  |  |  | Right of Way |  |  |  |  | 10000
3 | 23-75-003-030 | Floyd River 1.0 mi E of US 75 in Le Mars |  | Bridge Deck Overlay |  | 1220000
3 | 25-75-003-040 | Big Sioux Overflow 1.3 mi W of IA 12 |  | Bridge New |  |  |  |  | 2475000
|  |  |  | Right of Way |  |  |  |  | 5000
3 | 25-75-003-050 | Westfield Creek 0.2 mi W of W Jct IA 12 |  | Bridge New |  |  |  |  | 3712000
|  |  |  | Right of Way |  |  |  |  | 5000
12 | 22-75-012-010 | Beaver Creek 0.5 mi N of Co Rd C16 |  | Bridge Deck Overlay |  | 770000
12 | 22-75-012-030 | Broken Kettle Creek 0.1 mi N of S Jct Co Rd K18 |  | Bridge Replacement |  | 2804000
75 | 22-75-075-020 | W Fork Floyd River 2.4 mi N of Co Rd R38 |  | Bridge Deck Overlay |  | 1131000
75 | 24-75-075-030 | Stream 0.6 mi S of Co Rd C60 (NB) |  | Bridge New |  |  |  | 1950000
|  |  |  | Right of Way |  |  | 10000
75 | 21-75-075-010 | S of W Grover St to N of Maple St in Hinton | 0.7 | Right of Way | 4174000
|  |  |  | Grade & Pave |  |  |  | 8268000
|  |  |  | Traffic Signals |  |  |  | 2119000
|  |  |  | Bridge Replacement |  |  |  | 2360000
75 | 16-75-075-030 | N of Maple St in Hinton to S of 2nd St in Merrill | 6.4 | Erosion Control | 358000
75 | 24-75-075-050 | 0.4 mi N of IA 60 to 0.5 mi S of IA 10 | 11.6 | Pavement Rehab | 1338000
404 | 24-75-404-010 | Floyd River 0.4 mi N of IA 3 in Le Mars (NB) |  | Bridge Rehabilitation |  |  |  | 2600000
(76) Pocahontas
3 | 21-76-003-040 | Little Cedar Creek 4.4 mi E of Co Rd N14 |  | Bridge Deck Overlay | 275000
3 | 24-76-003-010 | North Lizard Creek 0.8 mi W of IA 15 |  | Bridge Deck Overlay |  |  |  | 520000
3 | 21-76-003-030 | Lizard Creek 0.9 mi E of IA 4 in Pocahontas |  | Bridge Deck Overlay | 626000
3 | 21-76-003-050 | Drainage Ditch 5.0 mi W of IA 4 |  | Culvert Replacement | 1146000
|  |  |  | Right of Way | 10000
4 | 23-76-004-030 | North Lizard Creek 5.6 mi N of IA 3 |  | Bridge Deck Overlay |  | 892000
4 | 25-76-004-030 | Pilot Creek 1.4 mi N of Co Rd C26 |  | Bridge Deck Overlay |  |  |  |  | 880000
7 | 25-76-007-020 | Big Cedar Creek 0.4 mi E of Co Rd N28 |  | Bridge Deck Overlay |  |  |  |  | 782000
10 | 23-76-010-010 | Little Cedar Creek 3.7 mi W of Co Rd N28 |  | Bridge Deck Overlay |  | 739000
15 | 22-76-015-010 | Pilot Creek at the N Jct Co Rd C26 |  | Bridge Replacement |  | 2184000
(81) Sac
20 | 23-81-020-010 | North Raccoon River 1.0 mi W of Co Rd M54 (EB/WB) |  | Bridge Deck Overlay |  | 1938000
71 | 24-81-071-010 | Carroll Co to Jct IA 175 in Auburn | 2.8 | Grade & Pave |  |  |  | 7012000
175 | 24-81-175-010 | High St 1.9 mi E of Co Rd M64 |  | Bridge New |  |  |  | 3900000
|  |  |  | Right of Way |  |  |  | 10000
(83) Shelby
59 | 24-83-059-010 | Lyon Creek 2.6 mi S of IA 37 |  | Bridge Deck Overlay |  |  |  | 600000
(84) Sioux
10 | 24-84-010-010 | UP RR 1.0 mi W of IA 60 |  | Bridge Deck Overlay |  |  |  | 1300000
10 | 24-84-010-020 | Dry Creek 0.4 mi W of IA 12 in Hawarden |  | Bridge New |  |  |  | 1950000
|  |  |  | Right of Way |  |  |  | 4000
18 | 25-84-018-050 | Rock River 0.3 mi W of Co Rd K24 |  | Grading | 200000
60 | 23-84-060-010 | Floyd River Tributary 0.5 mi S of Co Rd K64 (SB) |  | Bridge Deck Overlay |  |  | 482000
60 | 21-84-060-010 | Floyd River Tributary 0.5 mi S of Co Rd K64 (NB) |  | Bridge Replacement |  | 1954000
|  |  |  | Right of Way |  | 11000
75 | 24-84-075-020 | W Fork Floyd River 0.1 mi N of IA 10 |  | Bridge Deck Overlay |  |  |  | 110000
75 | 17-84-075-010 | S of 12th St NE in Sioux Center to S Jct US 18 | 6.1 | Traffic Signals |  |  | 342000
|  |  |  | Grade & Pave |  |  | 26140000
(97) Woodbury
12 | 19-97-012-010 | Gordon Dr Viaduct, Rustin St to Virginia St in Sioux City | 1.2 | Right of Way |  | 26400000
|  |  |  | Grade & Pave |  |  | 21910000 | 40789000 | 40381000
|  |  |  | Bridge New |  | 2402000 |  | 31009000 | 8101000
|  |  |  | Bridge Removal |  |  | 3475000
|  |  |  | Culvert New |  |  | 1101000
|  |  |  | Traffic Signals |  |  | 3355000
|  |  |  | Lighting |  |  | 1883000
|  |  |  | Traffic Signs |  |  |  |  | 2056000
|  |  |  | Bridge Replacement |  |  | 15520000 |  | 13710000
20 | 22-97-020-040 | Sunnybrook Dr 1.7 mi W of IA 12 in Sioux City (EB/WB) |  | Bridge Deck Overlay |  | 903000
20 | 21-97-020-070 | US 20 Ramp G over I-29 |  | Bridge Deck Overlay | 1265000
20 | 21-97-020-050 | WB Ramp over IA 376 and RR |  | Bridge Deck Overlay | 2583000
20 | 24-97-020-020 | 0.4 mi E of Franklin Ave to E of Humboldt Ave near Moville | 3.6 | Paving | 10537000
|  |  |  | Paving | 9924000
20 | 98-97-020-010-08 | Mitigation - Woodbury Ida and Sac Counties US 20 |  | Wetland Mitigation |  | 195000
20 | 25-97-020-030 | Little Sioux River 0.4 mi W of IA 31 (EB/WB) |  | Bridge Deck Overlay |  |  |  |  | 7034000
29 | 23-97-029-070 | Sergeant Bluff Rest Area (SB) (Remove Ramps) |  | Grading | 655000
29 | 22-97-029-030 | Sergeant Bluff Rest Area (NB) (Remove) |  | Grading | 892000
29 | 20-97-029-070 | SB Weigh Station 0.6 mi N of Co Rd K35 |  | Paving | 2571000
|  |  |  | Weigh Scale | 3670000
29 | 06-97-029-010 | Southbridge Interchange 2.5 mi south of Sergeant Bluff |  | Right of Way | 872000
|  |  |  | Traffic Signals | 888000
|  |  |  | Bridge New | 500000
|  |  |  | Traffic Signs | 100000
29 | 25-97-029-090 | Monona County Line to SCL of Sergeant Bluff (NB) | 14 | Pavement Rehab |  |  |  |  | 5608000
75 | 25-97-075-040 | CCP RR, BNSF RR, and Business 75 5.8 mi N of IA 12 (NB) |  | Bridge Deck Overlay |  |  |  |  | 6121000
77 | 16-97-077-010 | Missouri River in Sioux City (State Share) | 0.1 | Bridge Washing | 36000 | 35779.93 | 36000 | 36000 | 36000
77 | 23-97-077-020 | Wesley Pkwy over Tri View Ave and BNSF RR in Sioux City |  | Bridge Deck Overlay |  |  | 296000
77 | 25-97-077-010 | Missouri River in Sioux City |  | Bridge Rehabilitation |  |  |  |  | 300000
129 | 16-97-129-010 | Missouri River in Sioux City (State Share) | 0.2 | Bridge Washing | 50000
|  |  |  | Bridge Washing |  | 50000 | 50000 | 50243.26 | 50000
141 | 24-97-141-010 | Fork Little Sioux River 0.3 mi W of Co Rd K64 |  | Bridge New |  |  |  | 975000
|  |  |  | Right of Way |  |  |  | 4000
141 | 24-97-141-020 | Smokey Hollow Creek 0.2 mi E of IA 31 |  | Bridge New |  |  |  | 2275000
|  |  |  | Right of Way |  |  |  | 4000
141 | 23-97-141-030 | W Branch Little Sioux River 0.8 mi E of Co Rd K64 |  | Bridge Replacement |  |  |  | 2983000
|  |  |  | Right of Way |  |  |  | 12000
175 | 20-97-175-010 | Reynolds Creek 1.6 mi W of Co Rd L37 |  | Bridge Replacement |  | 3007000
376 | 21-97-376-030 | Tributary to Floyd River 0.1 mi N of Co Rd D12 in Sioux City (SB) |  | Bridge Replacement | 1213000
(00) Statewide
0 | 24-00-000-210 | Various Counties and Routes in District 3 |  | Pavement Rehab | 2520000
|  |  |  | Pavement Rehab | 2800000

## Sheet2
2026 - 2030 Five Year Program
This information is valid for the date of Commission approval of 06/10/2025
Line Items
Project Estimated Costs X $1000
| County | Location | Type Of Work | 2026 | 2027 | 2028 | 2029 | 2030
| Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide Interstate Lighting | Lighting | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
| Statewide | Statewide Interstate Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 9900000 | 10000000 | 10100000 | 10200000 | 10300000
| Statewide | Statewide Interstate Signing | Traffic Signs | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
| Statewide | Statewide Interstate Pavement Maintenance | Pavement Rehab | 9500000 | 14500000 | 14500000 | 14500000 | 14500000
| Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 166700000 | 155900000 | 185500000 | 192500000
| Statewide | Statewide Safety Specific | Paving | 0 | 35000000 | 36000000 | 37000000 | 38000000
| Statewide | American with Disabilities Act | Pedestrian Improvement | 5000000 | 5500000 | 6000000 | 6500000 | 7000000
| Statewide | Construction Industry Training Program | Training | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
| Statewide | Cooperative City/County/State Highway Research | Research | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Emergency & Contingency (U-STEP/C-STEP) | Construction | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
| Statewide | Post Letting Project Cost | Construction | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
| Statewide | Prevocational Training and DBE Support Services | Training | 360000 | 360000 | 360000 | 360000 | 360000
| Statewide | Scenic Byway Program | Signs | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Consultant Services | Outside Services Engineering | 72000000 | 74000000 | 74000000 | 74000000 | 74000000
| Statewide | Statewide Contract Maintenance | Construction | 42850000 | 43350000 | 48500000 | 49000000 | 49500000
| Statewide | Statewide Railroad Crossings | Construction | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Statewide Traffic Control Devices/Signs/Lighting | Traffic Signs and Lighting | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
| Statewide | Statewide Operations | Outside Services Engineering | 16000000 | 16000000 | 16000000 | 16000000 | 16000000
| Statewide | Statewide ITS | Equipment | 8000000 | 8000000 | 8000000 | 8000000 | 8000000
| Statewide | Winter Operations Materials | Materials | 15000000 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Summer Infrastructure Rehabilitation Materials | Materials | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
| Statewide | Pavement Marking Materials | Paint | 7700000 | 7700000 | 7700000 | 7700000 | 7700000