## Sheet1
2026 - 2030 IOWA HIGHWAY PROGRAM
S.F 257 Only: No |  |  |  |  | Project Estimated Costs X $1000
Route | Project Code | Location | Miles | Type of Work | 2026 | 2027 | 2028 | 2029 | 2030
(01) Adair
80 | 22-01-080-060 | At the Co Rd P28 Interchange |  | Bridge Rehabilitation |  | 1625000
80 | 22-01-080-050 | At the Co Rd G30 Interchange |  | Bridge Rehabilitation |  | 1853000
80 | 22-01-080-040 | Antique Country Dr 3.5 mi W of IA 25 (EB/WB) |  | Bridge Rehabilitation |  | 445000
80 | 23-01-080-040 | Co Rd N54 Interchange at Adair |  | Right of Way |  |  |  | 10000
|  |  |  | Bridge Replacement |  |  |  |  | 3955000
92 | 24-01-092-010 | 0.7 mi E of Bridgewater Rd |  | RipRap | 162000
|  |  |  | Right of Way | 2000
92 | 24-01-092-020 | Middle Nodaway River 2.4 mi W of IA 25 |  | Bridge Rehabilitation |  |  |  | 1170000
92 | 19-01-092-010 | W Fork Nodaway River 1.6 mi E of Co Rd N51 | 0.1 | Bridge Replacement | 3036000
(02) Adams
34 | 22-02-034-010 | Metz Creek 2.3 mi. W of W Jct. IA 25 |  | Bridge Replacement |  | 1172000
|  |  |  | Right of Way |  | 12000
34 | 24-02-034-010 | Kemp Creek 4.8 mi W of IA 148 |  | Bridge New |  |  |  |  | 3575000
|  |  |  | Right of Way |  |  |  |  | 10000
34 | 22-02-034-020 | E Nodaway River and RR 0.8 mi W of IA 148 |  | Bridge Replacement |  |  |  |  | 20859000
|  |  |  | Right of Way |  |  |  |  | 1259000
148 | 21-02-148-010 | Branch E Nodaway River 0.4 mi N of Co Rd N28 |  | Bridge Deck Overlay |  | 445000
(05) Audubon
44 | 22-05-044-010 | David's Creek 0.2 mi W of Co Rd N36 |  | Bridge Deck Overlay | 1221000
71 | 21-05-071-010-90 | Mitigation - Stream 0.6 mi N of I-80 |  | Mitigation | 128000
71 | 21-05-071-010 | Stream 0.6 mi N of I-80 |  | Culvert Replacement | 1330000
|  |  |  | Right of Way | 5000
71 | 25-05-071-010 | Stream 3.1 mi N of I-80 |  | Bridge Deck Overlay |  |  |  |  | 326000
71 | 25-05-071-020 | Stream 1.7 mi N of I-80 |  | Bridge New |  |  |  |  | 1303000
|  |  |  | Right of Way |  |  |  |  | 5000
(15) Cass
6 | 22-15-006-010 | Spring Creek 1.4 mi E of IA 48 |  | Bridge Replacement |  |  | 2613000
|  |  |  | Right of Way |  |  | 12000
6 | 23-15-006-010 | Turkey Creek 3.7 mi E of IA 48 |  | Bridge New |  |  | 3740000
|  |  |  | Right of Way |  |  | 10000
71 | 25-15-071-010 | Lone Tree Creek 0.1 mi S of Co Rd G35 |  | Bridge Rehabilitation |  |  |  |  | 652000
80 | 20-15-080-020 | IA 148 Interchange |  | Bridge Rehabilitation | 1523000
80 | 24-15-080-010 | Pottawattamie Co to E of IA 173 (EB) | 5.6 | Pavement Rehab |  |  | 2493000
80 | 23-15-080-020 | 770th St 1.7 mi E of IA 148 (EB/WB) |  | Right of Way |  |  |  | 12000
|  |  |  | Bridge New |  |  |  | 9542000
83 | 21-15-083-010 | Indian Creek 1.3 mi W of Co Rd M56 |  | Bridge Rehabilitation | 1705000
83 | 25-15-083-010 | Buck Creek 1.0 mi E of IA 173 |  | Bridge Deck Overlay |  |  |  |  | 1173000
83 | 25-15-083-020 | Compton Creek 0.1 mi W of Co Rd M56 |  | Culvert New |  |  |  |  | 977000
|  |  |  | Right of Way |  |  |  |  | 5000
92 | 25-15-092-010 | Union St in Griswold to US 71 | 8.2 | Pavement Rehab | 4323000
(25) Dallas
6 | 25-25-006-010 | Common Place Intersection 0.3 mi S of Adel City Limits |  | Grade & Pave | 3000000
44 | 25-25-044-040 | North Raccoon River 0.7 mi W of US 169 |  | Bridge Rehabilitation |  |  |  |  | 13023000
|  |  |  | Right of Way |  |  |  |  | 5000
80 | 23-25-080-030 | Co Rd R16 3.1 mi E of US 169 |  | Bridge Deck Overlay |  |  | 813000
80 | 21-25-080-020 | Co Rd R22 (Ute Ave) Interchange |  | Bridge Rehabilitation | 1207000
80 | 24-25-080-030 | E of Co Rd P58 to 0.5 mi E of US 169 (WB) | 3.3 | Pavement Rehab |  |  |  |  | 3778000
80 | 22-25-080-030 | W of US 6/169 to E of US 6/169 Interchange | 1 | Right of Way |  |  | 112000
|  |  |  | Erosion Control |  |  |  |  | 340000
|  |  |  | Mitigation |  |  | 665000
|  |  |  | Bridge Replacement |  |  | 3053000 | 3336000
|  |  |  | Grade & Pave |  |  | 10319000 | 10320000
|  |  |  | Traffic Signs |  |  | 914000 | 448000
80 | 18-25-080-020-01 | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 4 | Traffic Signs | 1092000
|  |  |  | Erosion Control |  | 195000
|  |  |  | Grade & Pave | 16932000
|  |  |  | Bridge Replacement | 3809000
80 | 25-25-080-020 | Madison Co to 0.7 mi E of Co Rd P53/Co Rd F60 (WB) | 1.6 | Pavement Rehab |  |  |  |  | 2069000
80 | 25-25-080-030 | Madison Co to 1.8 mi E of Co Rd P57 (EB) | 6.6 | Pavement Rehab |  |  |  |  | 6163000
141 | 24-25-141-010 | Frog Creek 0.1 mi W of IA 144 (EB/WB) |  | Bridge Deck Overlay |  |  |  | 1070000
141 | 22-25-141-020 | At the US 169 Interchange (EB/WB) |  | Bridge Deck Overlay |  | 2031000
169 | 22-25-169-020 | North Raccoon River 1.4 mi N of US 6 |  | Bridge Rehabilitation |  |  |  | 5091000
169 | 25-25-169-010 | N Raccoon River Overflow0.5 mi N of US 6 |  | Bridge Deck Overlay |  |  |  |  | 1303000
(36) Fremont
2 | 16-36-002-020 | Missouri River E of Nebraska City (State Share) | 0.2 | Bridge Washing | 21000 | 21389.97 | 21000 | 21000 | 21000
2 | 23-36-002-030 | W Nishnabotna River Overflow 1.8 mi W of Co Rd L68 |  | Bridge New |  |  | 561000
2 | 22-36-002-010 | Missouri River Overflow 0.5 mi E of the Missouri River |  | Bridge Deck Overlay |  | 1591000
2 | 24-36-002-020 | 0.1 mi E of 342nd Ave to East Nishnabotna River | 4 | Paving | 8619000
2 | 22-36-002-020 | W Nishnabotna River Overflow 1.1 mi E of E Jct US 275 |  | Bridge New |  |  | 12985000
|  |  |  | Right of Way |  |  | 13000
2 | 21-36-002-010 | W Nishnabotna River 1.7 mi E of E Jct US 275 | 0.1 | Bridge New |  |  | 6813000
|  |  |  | Right of Way |  |  | 233000
2 | 98-36-002-010-05 | Sidney ByPass - Flyway Farms Mitigation Site |  | Wetland Mitigation | 52000
29 | 24-36-029-030 | 2.5 mi S of IA 2 |  | RipRap | 250000
|  |  |  | Right of Way | 10000
29 | 23-36-029-030 | NB Weigh Station 1.4 mi N of IA 2 |  | Paving |  |  |  |  | 2184000
29 | 21-36-029-020 | BNSF RR and Main St 0.4 mi N of Missouri | 0.1 | Bridge Deck Overlay | 3763000
29 | 24-36-029-050 | Missouri State Line to IA 2 (SB) | 10.1 | Pavement Rehab |  |  | 4250000
29 | 24-36-029-060 | 0.4 mi S of Co Rd L31 to Mills Co (NB/SB) | 4.3 | Pavement Rehab |  |  | 8145000
275 | 23-36-275-010 | IA 2 to Sidney | 2.5 | Pavement Rehab | 1432000
333 | 22-36-333-020 | IA 333 over I-29 |  | Bridge Deck Overlay |  | 1445000
(43) Harrison
29 | 22-43-029-070 | Allen Creek 1.9 mi N of US 30 (NB/SB) |  | Bridge Rehabilitation |  | 2619000
29 | 22-43-029-080 | At the US 30 Interchange (SB) |  | Bridge Rehabilitation |  | 2960000
29 | 22-43-029-110 | Burcham Creek 2.7 mi S of IA 127 (NB/SB) |  | Bridge Replacement |  | 4791000
29 | 25-43-029-070 | Co Rd F20 Interchange - Ramps | 0.6 | Pavement Rehab |  |  |  |  | 997000
29 | 25-43-029-080 | 0.2 mi N of 106th Trail north 0.6 mile (NB/SB) | 0.6 | Pavement Rehab |  |  |  |  | 623000
30 | 21-43-030-010 | Allen Creek 0.9 mi W of I-29 |  | Bridge Deck Overlay | 441000
30 | 16-43-030-020 | Missouri River E of Blair Nebraska (State Share) | 0.2 | Bridge Washing | 35000 | 35243.26 | 35000 | 35000 | 35000
30 | 21-43-030-020 | Stream 0.8 mi E of Co Rd F58 |  | Culvert Replacement | 2340000
|  |  |  | Right of Way | 52000
|  |  |  | Miscellaneous | 105000
|  |  |  | Mitigation | 130000
30 | 24-43-030-040 | Youngs Ditch 0.8 mi E of Co Rd K45 |  | Bridge New |  |  |  | 3250000
|  |  |  | Right of Way |  |  |  | 10000
30 | 18-43-030-010 | Missouri Valley Bypass | 13.8 | Right of Way | 9929000
|  |  |  | Mitigation |  | 1400000
|  |  |  | Grading |  | 35083000
|  |  |  | Bridge New |  | 23226000
|  |  |  | Paving |  |  |  | 29319000
|  |  |  | Traffic Signs |  |  |  | 312000
|  |  |  | Lighting |  |  |  | 179000
|  |  |  | Pavement Rehab |  |  |  |  | 6572000
(61) Madison
80 | 23-61-080-010 | At the Co Rd P48 Interchange |  | Bridge New |  |  |  |  | 3200000
80 | 25-61-080-020 | Co Rd P48 to Dallas Co (EB) | 2 | Pavement Rehab |  |  |  |  | 2431000
92 | 22-61-092-010 | Middle River 2.0 mi W of Co Rd P53 |  | Bridge Rehabilitation |  | 1438000
(65) Mills
34 | 24-65-034-030 | At Co Rd L35 Interchange (NB/SB) |  | Bridge Deck Overlay |  |  |  | 1950000
34 | 12-65-034-020 | Missouri River N of Plattsmouth Nebraska (State Share) | 0.2 | Bridge Washing | 25000 | 25000 | 25000 | 25000 | 25000
34 | 24-65-034-020 | BNSF RR 0.5 mi E of I-29 (EB/WB) |  | Bridge Deck Overlay |  |  |  | 3900000
34 | 21-65-034-020 | Missouri River N of Plattsmouth, Nebraska (State Share) | 0.3 | Bridge Deck Overlay | 6400000
34 | 25-65-034-030 | Missouri River N of Plattsmouth Nebraska |  | Lighting |  |  |  |  | 260000
34 | 25-65-034-020 | Hillman Rd Intersection 1.0 mi W of 221st St |  | Grade & Pave | 480000
59 | 24-65-059-010 | Stream 1.1 mi S of Co Rd H12 (Side Ditch) |  | Bridge New |  |  |  | 455000
|  |  |  | Right of Way |  |  |  | 10000
59 | 23-65-059-010 | At the Jct US 34 |  | Bridge New |  |  | 4117000
|  |  |  | Right of Way |  |  | 161000
(69) Montgomery
34 | 22-69-034-020 | Crabapple Creek 3.1 mi E of US 59 |  | Bridge Deck Overlay |  | 497000
34 | 24-69-034-020 | Indian Creek 1.2 mi E of US 59 |  | Bridge Deck Overlay |  |  |  | 455000
48 | 23-69-048-020 | Nishnabotna River Overflow 2.0 mi S of Co Rd H14 |  | Bridge Deck Overlay |  | 1162000
48 | 22-69-048-010 | East Nishnabotna River 1.7 mi N of US 34 | 0.1 | Bridge Deck Overlay |  | 1386000
48 | 21-69-048-010 | Red Oak Creek 1.3 mi S of US 34 in Red Oak |  | Bridge Replacement | 1585000
|  |  |  | Right of Way | 21000
71 | 24-69-071-020 | Fultons Creek 3.4 mi N of US 34 |  | Bridge Deck Overlay |  |  |  | 455000
71 | 24-69-071-030 | At US 34 Interchange |  | Bridge Deck Overlay |  |  |  | 975000
(73) Page
48 | 24-73-048-010 | Rocky Branch 1.2 mi S of Co Rd M41 |  | Bridge Deck Overlay |  |  |  | 520000
59 | 24-73-059-010 | Stream 1.5 mi N of IA 48 |  | Bridge Deck Overlay |  |  |  | 455000
71 | 25-73-071-020 | West Nodaway River 0.3 mi S of N Jct IA 2 |  | Bridge Deck Overlay |  |  |  |  | 2605000
(78) Pottawattamie
6 | 24-78-006-030 | Silver Creek 1.0 mi E of Co Rd L66 |  | Bridge New |  |  |  | 3900000
|  |  |  | Right of Way |  |  |  | 10000
6 | 16-78-006-030 | 6th St to 0.22 mi E of I-80 in Council Bluffs |  | Pavement Rehab | 5000000
29 | 24-78-029-040 | 0.6 mi N of NCL Council Bluffs to 1.1 mi S of I-680 (SB) | 3.1 | Pavement Rehab |  |  |  |  | 2491000
29 | 21-78-029-010 | Co Rd L19 Interchange |  | Bridge Replacement |  |  | 3276000
|  |  |  | Right of Way |  |  | 23000
29 | 23-78-029-030 | At the I-880 Interchange (NB/SB) |  | Bridge Rehabilitation |  |  | 3983000
29 | 24-78-029-030 | S of IA 192 to 0.74 mi N of 235th St – Various Locations | 30.7 | Pavement Rehab |  |  | 3058000
29 | 24-78-029-050 | 0.9 mi S of Co Rd L19 to S of I-880 (SB) | 5.4 | Pavement Rehab | 6500000
29 | 22-78-029-020 | At the N 16th St Interchange in Council Bluffs (NB) |  | Mitigation |  | 7000
|  |  |  | Bridge Replacement |  | 9062000
29 | 25-78-029-040 | I-680 to I-880 - Various Locations | 9 | Grading |  | 2500000
59 | 21-78-059-010 | Drainage Ditch 2.4 mi N of N Jct US 6 |  | Bridge Deck Overlay | 276000
59 | 21-78-059-020 | Stream 1.5 mi S of Co Rd G30 |  | Bridge Replacement |  | 1832000
|  |  |  | Mitigation |  | 131000
59 | 24-78-059-040 | Stream 0.6 mi N of S Jct Co Rd G30 |  | Bridge New |  |  |  | 1950000
|  |  |  | Right of Way |  |  |  | 10000
59 | 21-78-059-030 | Stream 0.9 mi S of Co Rd G30 |  | Bridge Replacement |  | 2260000
59 | 20-78-059-020 | At Jct IA 92 |  | Bridge Replacement | 4116000
59 | 24-78-059-010 | In Avoca, Pershing St to S of Co Rd F66 | 1.5 | Grade & Pave |  | 13422000
59 | 24-78-059-020 | In Avoca, High St to Pershing St | 0.7 | Grade & Pave |  |  | 3930000
80 | 22-78-080-040 | Drainage Ditch 0.3 mi W of Co Rd M16 |  | Right of Way |  | 5000
|  |  |  | Culvert Extension |  | 571000
80 | 16-78-080-020 | Missouri River in Council Bluffs (State Share) | 0.6 | Bridge Washing | 42000 | 42000 | 42000 | 42000 | 42000
80 | 22-78-080-050 | Stream 1.6 mi E of Co Rd M47 |  | Right of Way |  | 5000
|  |  |  | Culvert Extension |  | 1120000
80 | 20-78-080-080 | 0.4 mi E of I-880 to 0.1 mi W of Silver Creek Bridge (WB) |  | Pavement Rehab |  |  | 1857000
80 | 24-78-080-040 | 0.4 mi NE of Rest Area to Cass Co Line – Various Locations | 21.7 | Patching | 1500000
80 | 20-78-080-020 | US 6 to 2.2 mi E of US 6 | 2.3 | Pavement Rehab |  |  | 2481000
80 | 24-78-080-060 | W Nishnabotna River to 0.7 mi E of Rest Area (EB) | 5.8 | Pavement Rehab |  |  | 5081000
80 | 25-78-080-050 | Missouri River in Council Bluffs (EB/WB) |  | Bridge Rehabilitation |  |  |  |  | 166000
80 | 25-78-080-070 | 2.3 mi NE of NCL Council Bluffs to 0.45 mi SW of Magnolia Rd (EB/WB) | 5.4 | Pavement Rehab | 6500000
80 | 25-78-080-080 | Co Rd L66 Interchange |  | Right of Way |  |  |  |  | 5000
|  |  |  | Bridge New |  |  |  |  | 12098000
80 | 25-78-080-100 | 0.45 mi SW of Co Rd G30 east approx 4 miles (EB/WB) | 4.1 | Pavement Rehab |  |  |  |  | 6231000
92 | 24-78-092-010 | Farm Creek 6.3 mi E of US 59 |  | Bridge Deck Overlay |  |  |  | 520000
275 | 12-78-275-010 | Missouri River in Council Bluffs (State Share) | 0.1 | Bridge Washing | 57000 | 56633.22 | 57000 | 57000 | 57000
480 | 16-78-480-010 | Missouri River in Council Bluffs (State Share) | 0.4 | Bridge Washing | 30000 | 30316.61 | 30000 | 30000 | 30000
680 | 16-78-680-010 | Missouri River in Council Bluffs (State Share) | 0.1 | Bridge Washing | 48000 | 48169.9 | 48000 | 48000 | 48000
680 | 24-78-680-010 | Missouri River 3.1 mi W of I-29 (EB/WB) |  | Bridge Rehabilitation |  | 1000000
880 | 23-78-880-040 | At the IA 191 Interchange (WB) |  | Bridge Deck Overlay |  |  |  | 1388000
880 | 21-78-880-010 | Co Rd L34 Interchange |  | Bridge New |  |  |  |  | 21200000
880 | 23-78-880-010 | Mosquito Creek 0.5 mi E of IA 191 (EB) |  | Bridge Deck Overlay | 1948000
880 | 23-78-880-050 | UP RR and Co Rd L20 0.5 mi E of I-29 (EB/WB) |  | Bridge Deck Overlay | 2554000
880 | 21-78-880-020 | BNSF RR 0.3 mi E of IA 191 |  | Bridge Rehabilitation | 3523000
880 | 25-78-880-030 | Pigeon Creek 4.2 mi W of IA 191 (EB/WB) |  | Bridge Deck Overlay |  |  |  | 1247000
(80) Ringgold
2 | 24-80-002-010 | Walnut Creek 0.9 mi W of W Jct US 169 |  | Bridge Deck Overlay |  |  |  | 650000
2 | 25-80-002-010 | Mount Ayr to NCL Kellerton | 9.5 | Pavement Rehab | 5821000
25 | 24-80-025-010 | Stream 2.3 mi N of N Jct Co Rd J23 |  | Bridge New |  |  |  | 520000
|  |  |  | Right of Way |  |  |  | 10000
169 | 25-80-169-010 | Middle Fork Grand River 1.0 mi N of Co Rd P32 |  | Bridge Deck Overlay |  |  |  |  | 1173000
(83) Shelby
37 | 21-83-037-010 | Mill Creek 3.7 mi E of US 30 |  | Bridge Deck Overlay | 909000
44 | 24-83-044-010 | West Nishnabotna River 5.8 mi E of US 59 |  | Bridge Deck Overlay |  |  |  | 910000
44 | 25-83-044-010 | West Nishnabotna River 1.3 mi E of US 59 |  | Bridge Deck Overlay |  |  |  |  | 2345000
59 | 22-83-059-010 | Drainage Ditch 2.6 mi N of I-80 |  | Bridge Deck Overlay |  | 848000
59 | 21-83-059-010 | West Nishnabotna River 0.8 mi S of Co Rd F58 | 0.1 | Bridge Deck Overlay | 961000
173 | 23-83-173-020 | S of High St in Elk Horn to IA 44 | 3.1 | Pavement Rehab | 1656000
(87) Taylor
2 | 22-87-002-010 | East 102 River just E of Co Rd N44 |  | Bridge Deck Overlay |  | 1041000
2 | 25-87-002-010 | West 102 River 1.7 mi E of Co Rd N26 |  | Bridge Deck Overlay |  |  |  |  | 1693000
148 | 21-87-148-010 | Middle Branch W 102 River 2.0 mi S of Co Rd J20 |  | Bridge Rehabilitation | 1020000
148 | 24-87-148-010 | W Fork 102 River 0.1 mi N of Co Rd J20 |  | Bridge Rehabilitation |  |  |  | 975000
(88) Union
25 | 23-88-025-010 | Branch Platte River 3.4 mi S of US 34 |  | Bridge Deck Overlay |  | 904000
34 | 23-88-034-060 | BNSF RR 3.3 mi E of E Jct IA 25 |  | Bridge Deck Overlay |  |  | 1301000
34 | 23-88-034-040 | Abandoned RR 1.7 mi W of E Jct US 169 |  | Grading |  |  | 1712000
34 | 23-88-034-050 | Grand River 1.2 mi W of E Jct US 169 |  | Bridge Deck Overlay |  |  | 1079000
34 | 22-88-034-020 | Twelve Mile Creek 3.2 mi W of W Jct US 169 |  | Bridge Deck Overlay |  | 1098000
169 | 24-88-169-010 | Twelve Mile Creek 1.6 mi S of US 34 |  | Bridge Deck Overlay |  |  |  | 715000

## Sheet2
2026 - 2030 Five Year Program
This information is valid for the date of Commission approval of 06/10/2025
Line Items
Project Estimated Costs X $1000
| County | Location | Type Of Work | 2026 | 2027 | 2028 | 2029 | 2030
| Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide Interstate Lighting | Lighting | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
| Statewide | Statewide Interstate Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 9900000 | 10000000 | 10100000 | 10200000 | 10300000
| Statewide | Statewide Interstate Signing | Traffic Signs | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
| Statewide | Statewide Interstate Pavement Maintenance | Pavement Rehab | 9500000 | 14500000 | 14500000 | 14500000 | 14500000
| Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 166700000 | 155900000 | 185500000 | 192500000
| Statewide | Statewide Safety Specific | Paving | 0 | 35000000 | 36000000 | 37000000 | 38000000
| Statewide | American with Disabilities Act | Pedestrian Improvement | 5000000 | 5500000 | 6000000 | 6500000 | 7000000
| Statewide | Construction Industry Training Program | Training | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
| Statewide | Cooperative City/County/State Highway Research | Research | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Emergency & Contingency (U-STEP/C-STEP) | Construction | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
| Statewide | Post Letting Project Cost | Construction | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
| Statewide | Prevocational Training and DBE Support Services | Training | 360000 | 360000 | 360000 | 360000 | 360000
| Statewide | Scenic Byway Program | Signs | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Consultant Services | Outside Services Engineering | 72000000 | 74000000 | 74000000 | 74000000 | 74000000
| Statewide | Statewide Contract Maintenance | Construction | 42850000 | 43350000 | 48500000 | 49000000 | 49500000
| Statewide | Statewide Railroad Crossings | Construction | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Statewide Traffic Control Devices/Signs/Lighting | Traffic Signs and Lighting | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
| Statewide | Statewide Operations | Outside Services Engineering | 16000000 | 16000000 | 16000000 | 16000000 | 16000000
| Statewide | Statewide ITS | Equipment | 8000000 | 8000000 | 8000000 | 8000000 | 8000000
| Statewide | Winter Operations Materials | Materials | 15000000 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Summer Infrastructure Rehabilitation Materials | Materials | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
| Statewide | Pavement Marking Materials | Paint | 7700000 | 7700000 | 7700000 | 7700000 | 7700000