## Slide 1
Annual Utility Meeting
District 4 Update
3/2/2023
Wes Mayberry, P.E.
Assistant District Engineer
February 26, 2026

## Slide 2
District 4 Staff
District Engineer
Wes Mayberry
Assistant Engineer
Orest Lechnowsky, PE
West Staff Engineer
Scott Suhr
District Planner
Scott Schram

## Slide 3
17 Counties
703 Bridges
3,792 Lane Miles
17 Maintenance Garages
2 Construction Residencies
District 4

## Slide 4
District 4 Utility Staff
district engineer
assistant district engineer
Nate Epperson
District Utility Coordinator
Mike Frank
Nick Mocha
Blake Asberry
Engineering Operations Technician
Permits for:
Harrison, Shelby, Pottawattamie, Mills, Montgomery, Fremont, Page
Engineering Operations Technician
Permits for:
Audubon, Guthrie, Dallas, Cass, Adair, Madison, Union, Taylor, Ringgold

## Slide 5
EOT Areas of Responsibilities

## Slide 6: District 4

## Slide 7
Major
Projects
District 4
I 80 Dallas County Grand Prairie to Jordan Creek
Grand Prairie Parkway to Jordan Creek
Bridges/Grade/Pave
2024 - $20M Bridge COMPLETE
2025 - $24.2M Bridge/Paving COMPLETE
2026 - $24.2M Bridge/Paving
1/21/2026 Letting
I 80 Dallas County Grand Prairie to Jordan Creek
EB:
Intermediate lift of HMA is finished.
Open to Traffic
Final surface lift placed Spring 2026
WB
Let 1/21/2026

## Slide 8
Major
Projects
District 4
I 80 Dallas County Racoon River Bridges
US 6/US 169 in DeSoto to Co Rd R16
Widening and Bridge Replacement at the South and North Raccoon Rivers
All Lanes Open 11/19/2025
Remove old EB pavement in 2026

## Slide 9
Major
Projects
District 4
I 80 Dallas County
US 6 / US 169 Desoto Interchange
I-80 Bridge Replacements
FY27 – ROW/Structures
$25.9M
I 80 Dallas County
Grand Prairie Parkway to Jordan Creek
Widen to 6 Lanes
FY26: $24.2 WB Bridges and Paving
Adair I 80
Adair Interchange
2029 – ROW
2030 – Bridge Replacement
$3.955 M
Notes: Updated Adair 2028 to 2029/2030

## Slide 10
Major
Projects
District 4
I 80 Pottawattamie County
0.4 mi E of I-880 to 0.1 mi W of Silver Creek Bridge (WB)
2026 Patching
$1.4M
I 80 Dallas County
E of Co Rd P58 to 0.5 mi E of US 169 (WB)
2030 Resurfacing
$3.778M
Adair I 80
Cass Co to IA 25 (WB)
2025 Resurfacing
$4 M
COMPLETE
I 80 Pottawattamie County
W Nishnabotna River to 0.7 mi E of Rest Area (EB)
2028 Resurfacing
$5.1M
I 80 Cass County
Pottawattamie Co to E of IA 173 (EB)
2028 Resurfacing
$2.5M
I 80 Dallas County
CO RD P48 TO DALLAS CO (EB)
FY30 HMA Resurfacing ($2.43M)
I 80 Dallas County
MADISON CO TO 0.7 MI E OF CO RD P53 (WB)
FY30 HMA Resurfacing ($2.07M)
I 80 Pottawattamie County
CO RD L66 Interchange
FY30 Bridge New ($12.1M)
I 80 Pottawattamie County
In Avoca, Pershing St to S of Co Rd F66
FY27 Grade & Pave ($13.42M)

## Slide 11
Major
Projects
District 4
US 30 Harrison County
Missouri Valley Bypass
$35M Bridges and Grading 7/20/2027
$29M Paving 7/17/2029
I 29 Pottawattamie County
0.9 mi S of Co Rd L19 to S of I-880 (SB)
2026 PCC Overlay
$6.5M
I 29 Pottawattamie County
0.6 mi N of NCL Council Bluffs to 1.1 mi S of I-680 (SB)
FY30 HMA Resurfacing ($2.49M)
I 29 Pottawattamie County
AT THE IA 192 INTERCHANGE IN COUNCIL BLUFFS (NB)
FY27 Bridge Replacement ($9.062M)
Notes: Added PCC Overlay in 2026 and bridge replacement in FY27

## Slide 12
Highway 30 Missouri Valley by-pass
FY 26 Right of way programmed
FY 28 grading and culverts
FY 30 Paving

## Slide 13
Major
Projects
District 4
Roundabout
*Safety Project * US 59 Page County
IA 2 Intersection
FY27 Grade & Pave ($2.58M)
Notes: There are 3 Fremont County Bridges, but one is a small $500K deck overlay, not considered a major project..

## Slide 14
Major
Projects
District 4
Taylor IA 148
NCL Bedford to US 34
Pavement Rehab
$12.3M
COMPLETE
Adams US 34
West of Corning
2028 – ROW / Structures
$16.4 M

## Slide 15
Hwy 59 – City of Avoca (Rural Section)
Programmed FY 28

## Slide 16
Hwy 59 – City of Avoca (Urban Section)
Programmed FY 29

## Slide 18
Survey – Utility Locates
One call locates vs private locates
Survey

## Slide 19
Traffic Control Standard Road Plans
Sign Sizes
Channelizers
Spacing

## Slide 20
Wes Mayberry, P.E.
712-250-0496 (cell)
Wes.mayberry@iowadot.us​
iowadot.gov
Questions?