## Sheet1
2026 - 2030 IOWA HIGHWAY PROGRAM
S.F 257 Only: No |  |  |  |  | Project Estimated Costs X $1000
Route | Project Code | Location | Miles | Type of Work | 2026 | 2027 | 2028 | 2029 | 2030
(04) Appanoose
5 | 23-04-005-010 | Drainage Ditch 0.4 mi N of Co Rd T30 |  | Bridge New |  |  | 630000
|  |  |  | Right of Way |  |  | 10000
(20) Clarke
35 | 22-20-035-010 | White Breast Creek 1.3 mi S of US 34 (NB/SB) |  | Bridge Rehabilitation |  | 2286000
(26) Davis
63 | 20-26-063-010 | Middle Chequest Creek 0.2 mi N of 180th St | 0.1 | Bridge Replacement | 2721000
(27) Decatur
35 | 22-27-035-020 | At the Co Rd J20 Interchange |  | Bridge Deck Overlay |  | 838000
35 | 25-27-035-040 | US 69 Interchange at Lamoni - Ramps | 0.7 | Pavement Rehab |  |  |  |  | 623000
69 | 21-27-069-030 | I-35 Interchange | 0.1 | Bridge Deck Overlay | 524000
69 | 21-27-069-020 | Dickersons Branch 1.1 mi S of Co Rd J66 |  | Bridge Deck Overlay | 839000
69 | 25-27-069-020 | Zadie Creek 0.9 mi W of I-35 |  | Bridge New |  | 700000
(29) Des Moines
34 | 23-29-034-020 | Broadway Ave 1.0 mi W of US 61 in West Burlington (EB) |  | Bridge Deck Overlay | 1233000
34 | 23-29-034-040 | Gear Ave 1.6 mi W of US 61 in West Burlington |  | Bridge Deck Overlay | 1599000
34 | 23-29-034-050 | 4th St 2.1 mi E of US 61 in Burlington |  | Bridge Rehabilitation |  |  | 437000
34 | 23-29-034-060 | 5th St 2.0 mi E of US 61 in Burlington |  | Bridge Rehabilitation |  |  | 481000
34 | 23-29-034-030 | BNSF RR 0.3 mi W of US 61 in West Burlington (EB/WB) |  | Bridge Deck Overlay |  |  | 3051000
34 | 16-29-034-010 | Mississippi River in Burlington (State Share) | 0.4 | Bridge Washing | 50000 | 49633.22 | 50000 | 50000 | 50000
34 | 22-29-034-030 | Broadway Ave 1.0 mi W of US 61 in Burlington (WB) |  | Bridge Deck Overlay |  | 1080000
34 | 22-29-034-010 | BNSF RR and City Streets 1.4 mi E of US 61 in Burlington | 0.1 | Bridge Rehabilitation |  | 2109000
34 | 24-29-034-010 | Mississippi River in Burlington |  | Bridge Painting |  |  |  | 1000000
34 | 22-29-034-020 | BNSF RR and City Streets 1.5 mi E of US 61 in Burlington | 0.1 | Bridge Rehabilitation |  | 4970000
61 | 15-29-061-010 | Branch Smith Creek 1.0 mi S of Louisa Co | 0.1 | Culvert Replacement | 1309000
61 | 21-29-061-010 | Skunk River 0.5 mi N of IA 16 (SB) |  | Bridge Deck Overlay |  | 1588000
61 | 97-29-061-010-02 | S of 210th St to N of Mediapolis | 8.4 | Erosion Control | 233000
|  |  |  | Pavement Rehab | 1228000
61 | 97-29-061-010-03 | N of Mediapolis to 0.5 mi N of IA 78 | 16.3 | Erosion Control |  | 373855
|  |  |  | Grade & Pave | 31227000
|  |  |  | Traffic Signs | 340000
|  |  |  | Lighting | 209000
|  |  |  | Culvert Replacement | 301000
|  |  |  | Pavement Rehab |  | 2012000
(44) Henry
34 | 24-44-034-010 | E US 218 Interchange to E of Nebraska Ave (WB) | 3.4 | Pavement Rehab | 2250000
34 | 25-44-034-010 | Jefferson Co Line to Iowa Ave (EB) | 9.9 | Paved Shoulders | 3480000
78 | 23-44-078-020 | Stream 2.0 mi W of W Jct Co Rd W66 |  | Bridge Replacement |  |  | 1250000
|  |  |  | Right of Way |  |  | 10000
218 | 23-44-218-020 | US 218 Ramp G 3.3 mi N of S Jct US 34 |  | Bridge Deck Overlay |  |  | 670000
218 | 24-44-218-010 | US 34 Interchange (NB/SB) |  | Bridge Deck Overlay |  |  |  | 2600000
(52) Johnson
22 | 25-52-022-010 | Co Rd X14 to IA 70 | 9.4 | Pavement Rehab | 4800000
(54) Keokuk
21 | 21-54-021-020 | Cedar Creek 1.1 mi N of IA 92 |  | Bridge Replacement | 2168000
|  |  |  | Right of Way | 2288000
78 | 23-54-078-010 | Stream 3.9 mi E of IA 149 |  | Culvert New |  |  | 940000
|  |  |  | Right of Way |  |  | 10000
78 | 21-54-078-010 | Stream 3.4 mi W of IA 1 |  | Bridge Replacement | 1809000
|  |  |  | Right of Way | 10000
92 | 21-54-092-010 | Rock Creek 0.4 mi W of Co Rd V45 |  | Bridge Deck Overlay | 531000
92 | 25-54-092-010 | Bridge Creek 0.1 mi W of E Jct IA 149 |  | Bridge Deck Overlay |  |  |  |  | 1238000
92 | 25-54-092-020 | Cedar Creek 2.4 mi E of IA 21 |  | Bridge Rehabilitation |  |  |  |  | 2084000
149 | 22-54-149-010 | North Skunk River 2.5 mi S of W Jct IA 92 | 0.1 | Bridge Deck Overlay |  | 1487000
(56) Lee
2 | 21-56-002-010 | Big Sugar Creek 3.4 mi W of W Jct US 61 | 0.1 | Bridge Deck Overlay | 1028000
16 | 21-56-016-010 | Little Cedar Creek 1.7 mi E of Co Rd W46 |  | Bridge Deck Overlay | 596000
16 | 22-56-016-010 | Sugar Creek 0.3 mi W of US 218 |  | Bridge Replacement |  |  |  | 3403000
|  |  |  | Right of Way |  |  |  | 13000
61 | 21-56-061-020 | Lost Creek 2.4 mi S of IA 16 (NB) |  | Bridge Replacement |  |  |  |  | 3760000
|  |  |  | Right of Way |  |  |  |  | 6000
61 | 24-56-061-010 | In Keokuk, Des Moines River Bridge to US 218 | 3.7 | Grade & Pave |  |  |  | 12911000
136 | 16-56-019-010 | Mississippi River in Keokuk (State Share) | 0.1 | Bridge Washing | 20000 | 19853.29 | 20000 | 20000 | 20000
136 | 23-56-019-010 | Mississippi River in Keokuk |  | Bridge Rehabilitation |  |  | 50000
218 | 21-56-218-010 | BNSF RR 4.4 mi S of US 61 |  | Bridge Deck Overlay | 807000
(58) Louisa
61 | 21-58-061-010 | DME RR 3.4 mi N of W Jct IA 92 (NB) | 0.1 | Bridge Deck Overlay | 418000
61 | 23-58-061-030 | Iowa River 4.2 mi S of IA 92 |  | Bridge Painting |  | 1190000
61 | 24-58-061-010 | Iowa River 4.2 mi S of IA 92 |  | Bridge Deck Overlay |  |  |  | 3900000
61 | 11-58-061-010 | 0.5 mi N of IA 78 to 2.0 mi S of IA 92 | 30.8 | Wetland Mitigation |  | 1000000
|  |  |  | Mitigation |  | 1200000
|  |  |  | Right of Way | 7400000
|  |  |  | Bridge New |  | 13792000 |  | 31669000
|  |  |  | Paving |  |  |  | 24975000
|  |  |  | Bridge Replacement |  |  |  |  | 3960000
|  |  |  | Traffic Signals |  |  |  |  | 1496000
|  |  |  | Culvert Replacement |  |  |  | 1540000
|  |  |  | Grading |  | 45576000 |  | 12362000
|  |  |  | Culvert New |  | 1175000 |  |  | 1092000
|  |  |  | Grade & Pave |  |  |  | 9021000 | 18431000
|  |  |  | Traffic Signs |  | 218000 |  | 1013000 | 249000
|  |  |  | Lighting |  |  |  | 215000
70 | 24-58-070-010 | Iowa River 0.9 mi N of IA 92 |  | Bridge Deck Overlay |  |  |  |  | 2038000
92 | 23-58-092-010 | Monkey Run Creek 0.6 mi W of IA 70 in Columbus Jct |  | Bridge Deck Overlay |  | 660000
92 | 21-58-092-010 | Main St and Collins Rd 0.3 mi W of IA 70 in Columbus Jct | 0.1 | Bridge Deck Overlay | 614000
92 | 23-58-092-020 | Iowa River 0.5 mi E of IA 70 |  | Bridge Deck Overlay | 2440000
(59) Lucas
14 | 23-59-014-010 | At the Jct US 34 in Chariton |  | Bridge New |  |  | 4370000
|  |  |  | Right of Way |  |  | 10000
34 | 22-59-034-020 | BNSF RR 0.1 mi E of W Jct US 65 in Lucas |  | Bridge Deck Overlay |  |  | 1593000
34 | 22-59-034-030 | Russell Blvd, BNSF RR, and UP RR E of IA 14 in Chariton | 0.1 | Bridge Deck Overlay |  |  | 2465000
65 | 24-59-065-010 | Chariton River 2.2 mi N of Co Rd H50 |  | Bridge Deck Overlay |  |  |  | 650000
(62) Mahaska
63 | 13-62-063-020 | NW Bypass of Oskaloosa | 17.3 | Erosion Control |  |  | 199000
|  |  |  | Lighting |  | 197000
|  |  |  | Bridge New | 2653000
|  |  |  | Paving |  | 20136000
|  |  |  | Traffic Signs |  | 382000
63 | 25-62-063-010 | N of Co Rd G63 to S of 293rd St - Various Locations | 1.3 | Grade & Pave | 1000000
|  |  |  | Paving |  | 6800000
(63) Marion
5 | 23-63-005-030 | English Creek 1.3 mi S of S Jct IA 92 |  | Bridge Deck Overlay |  | 912000
5 | 24-63-005-020 | At IA 14 Interchange in Knoxville (NB/SB) |  | Bridge Deck Overlay |  |  |  | 1820000
14 | 21-63-014-020 | Teter Creek 0.2 mi S of Co Rd G40 | 0.1 | Bridge Deck Overlay | 746000
14 | 21-63-014-010 | White Breast Creek 2.1 mi S of Co Rd G40 | 0.1 | Bridge Deck Overlay | 1946000
14 | 24-63-014-020 | Hayes Dr to N of Co Rd G28 | 3.4 | Grade & Pave |  |  | 9501000
14 | 24-63-014-010 | N of Kermit Dr in Knoxville to Hayes Dr | 3.9 | Grade & Pave |  | 8274000
(68) Monroe
34 | 22-68-034-010 | Cedar Creek 4.4 mi W of IA 5 |  | Bridge Rehabilitation |  | 1139000
34 | 21-68-034-030 | Coal Creek 2.0 mi W of IA 5 |  | Bridge Replacement |  | 3449000
|  |  |  | Right of Way | 6000
34 | 25-68-034-030 | 0.3 mi E of 550th Ave to 0.3 mi W of IA 5 | 8.7 | Pavement Rehab | 8500000
34 | 25-68-034-040 | 0.2 mi E of 520th Ave to 0.1 mi E of 642nd Ave | 12.1 | Grade & Pave |  | 7500000
(70) Muscatine
6 | 21-70-006-030 | E Branch Wapsinonoc Creek 0.5 mi E of IA 70 |  | Bridge Replacement |  | 1848000
|  |  |  | Right of Way |  | 16000
22 | 24-70-022-010 | Pine Cree 0.1 mi E of Co Rd Y26 |  | Bridge Deck Overlay |  |  |  | 715000
22 | 22-70-022-010 | Pike Run Creek 1.2 mi E of IA 70 |  | Bridge Deck Overlay |  | 828000
22 | 23-70-022-020 | Stream 0.2 mi E of Co Rd Y36 |  | Culvert Replacement |  |  | 1250000
|  |  |  | Right of Way |  |  | 10000
22 | 25-70-022-010 | Stream 0.6 mi W of Co Rd Y36 |  | Bridge Deck Overlay |  |  |  |  | 1107000
38 | 24-70-038-020 | Mosquito Creek 2.2 mi S of US 6 |  | Bridge Deck Overlay |  |  |  | 500000
38 | 22-70-038-010 | Mad Creek 0.6 mi N of US 61 |  | Bridge Rehabilitation |  | 1211000
70 | 23-70-070-020 | Wapsinonoc Creek 1.1 mi S of US 6 |  | Bridge Deck Overlay |  | 889000
92 | 16-70-092-010 | Mississippi River in Muscatine (State Share) | 0.6 | Bridge Washing | 50000 | 49633.22 | 50000 | 50000 | 50000
92 | 22-70-092-010 | Mississippi River in Muscatine |  | Bridge Rehabilitation |  | 3077000
(89) Van Buren
16 | 22-89-016-010 | Stump Creek 3.3 mi W of Co Rd V64 |  | Bridge Deck Overlay |  | 590000
(90) Wapello
34 | 24-90-034-010 | In Ottumwa, Des Moines River Bridge to RR Bridge | 1.2 | Grade & Pave |  |  |  |  | 5159000
34 | 23-90-034-010 | Bear Creek and CPKC RR 4.2 mi W of Co Rd H35 |  | Bridge Replacement |  |  | 9437000
|  |  |  | Right of Way |  |  | 12000
63 | 23-90-063-020 | Fudge Creek 4.3 mi S of IA 137 (NB/SB) |  | Bridge Deck Overlay | 2006000
63 | 21-90-063-010 | Abandoned RR 4.8 mi N of Co Rd J15 (Bridge Removal) |  | Grade & Pave | 761000
149 | 20-90-149-010 | Des Moines River Bridge to W Woodland Ave in Ottumwa | 0.7 | Traffic Signals |  |  | 1705000
|  |  |  | Grade & Pave |  |  | 5958000
149 | 22-90-149-010 | Des Moines River and BNSF RR N of US 34 in Ottumwa | 0.4 | Bridge Rehabilitation |  |  |  | 33798000
149 | 22-90-149-030 | DME RR 3.9 mi N of US 34 (NB/SB) |  | Bridge Replacement |  |  | 7442000
|  |  |  | Right of Way |  |  | 12000
(91) Warren
35 | 24-91-035-020 | Clarke Co to Clanton Creek Bridge (NB/SB) | 11.3 | Pavement Rehab | 8000000
35 | 00-91-035-030-05 | N of IA 92 to S of North River | 6.4 | Traffic Signs |  |  | 36000
|  |  |  | Grade & Pave |  |  | 11163000
35 | 00-91-035-030-06 | N of North River to S of Badger Creek | 4.8 | Traffic Signs | 124000
|  |  |  | Mitigation | 204000
|  |  |  | Grade & Pave | 21759000
|  |  |  | Culvert Extension | 680000
35 | 00-91-035-030-04 | 1.8 miles S of Co Rd G14 to 0.25 mi N of Adams St (NB) |  | Mitigation |  | 281000
|  |  |  | Grade & Pave |  | 32552000
|  |  |  | Traffic Signs |  | 1427000
92 | 23-91-092-010 | Stream 1.9 mi E of IA 28 |  | Culvert New |  |  | 940000
|  |  |  | Right of Way |  |  | 10000
(92) Washington
22 | 24-92-022-020 | Iowa River Overflow 1.7 mi E of US 218 |  | Bridge Deck Overlay |  |  |  | 520000
22 | 23-92-022-010 | Smith Creek 3.6 mi W of IA 1 |  | Bridge Deck Overlay |  | 877000
22 | 22-92-022-010 | English River Overflow 2.5 mi W of IA 1 |  | Bridge Rehabilitation |  | 849000
78 | 23-92-078-010 | IA 1 in Brighton to WCL Wayland | 8.7 | Pavement Rehab | 3948000
92 | 85-92-092-010 | E of US 218 to IA 70 in Columbus Junction | 9.4 | Erosion Control | 282000
218 | 22-92-218-010 | At the IA 22 Interchange (SB) |  | Bridge Deck Overlay |  | 1567000
218 | 25-92-218-010 | Henry Co to IA 92 (NB/SB) | 9 | Pavement Rehab | 8200000
218 | 25-92-218-020 | IA 92 to Co Rd W64 (SB) | 1.6 | Pavement Rehab | 1100000
(93) Wayne
65 | 22-93-065-010 | Drainage Ditch 2.8 mi N of IA 2 |  | Culvert Repair |  | 167000

## Sheet2
2026 - 2030 Five Year Program
This information is valid for the date of Commission approval of 06/10/2025
Line Items
Project Estimated Costs X $1000
| County | Location | Type Of Work | 2026 | 2027 | 2028 | 2029 | 2030
| Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide Interstate Lighting | Lighting | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
| Statewide | Statewide Interstate Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 9900000 | 10000000 | 10100000 | 10200000 | 10300000
| Statewide | Statewide Interstate Signing | Traffic Signs | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
| Statewide | Statewide Interstate Pavement Maintenance | Pavement Rehab | 9500000 | 14500000 | 14500000 | 14500000 | 14500000
| Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 166700000 | 155900000 | 185500000 | 192500000
| Statewide | Statewide Safety Specific | Paving | 0 | 35000000 | 36000000 | 37000000 | 38000000
| Statewide | American with Disabilities Act | Pedestrian Improvement | 5000000 | 5500000 | 6000000 | 6500000 | 7000000
| Statewide | Construction Industry Training Program | Training | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
| Statewide | Cooperative City/County/State Highway Research | Research | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Emergency & Contingency (U-STEP/C-STEP) | Construction | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
| Statewide | Post Letting Project Cost | Construction | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
| Statewide | Prevocational Training and DBE Support Services | Training | 360000 | 360000 | 360000 | 360000 | 360000
| Statewide | Scenic Byway Program | Signs | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Consultant Services | Outside Services Engineering | 72000000 | 74000000 | 74000000 | 74000000 | 74000000
| Statewide | Statewide Contract Maintenance | Construction | 42850000 | 43350000 | 48500000 | 49000000 | 49500000
| Statewide | Statewide Railroad Crossings | Construction | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Statewide Traffic Control Devices/Signs/Lighting | Traffic Signs and Lighting | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
| Statewide | Statewide Operations | Outside Services Engineering | 16000000 | 16000000 | 16000000 | 16000000 | 16000000
| Statewide | Statewide ITS | Equipment | 8000000 | 8000000 | 8000000 | 8000000 | 8000000
| Statewide | Winter Operations Materials | Materials | 15000000 | 15000000 | 15000000 | 15000000 | 15000000
| Statewide | Summer Infrastructure Rehabilitation Materials | Materials | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
| Statewide | Pavement Marking Materials | Paint | 7700000 | 7700000 | 7700000 | 7700000 | 7700000