## Sheet1
2027 - 2031 IOWA HIGHWAY PROGRAM
S.F 257 Only: No | [5 empty] | Project Estimated Costs X $1000
Route |  | Project Code | Location | Miles | Type of Work | 2027 | 2028 | 2029 | 2030 | 2031
(08) Boone
30 | 1 | 25-08-030-010 | Co Rd R27/Corporal Roger Snedden Dr Intersection in Boone |  | Right of Way | 10000
| 1 |  |  |  | Grade & Pave | 2904000
| 1 |  |  |  | Traffic Signs | 75000
| 1 |  |  |  | Lighting | 120000
1
30 | 1 | 24-08-030-020 | Linn St and SE Marshall St Intersections in Boone | 0.7 | Grade & Pave | 2700000
| 1 |  |  |  | Traffic Signs | 75000
| 1 |  |  |  | Lighting | 120000
| 1 |  |  |  | Right of Way | 200000
1
169 | 1 | 22-08-169-020 | US 30 Interchange |  | Bridge Deck Overlay | 623000
1
(25) Dallas | 1
44 | 1 | 25-25-044-020 | Dallas Center to Grimes | 7.2 | Pavement Rehab | 3263000
1
(37) Greene | 1
4 | 1 | 25-37-004-010 | Hardin Creek 1.2 mi N of US 30 |  | Bridge Deck Overlay |  |  |  | 1055000
1
30 | 1 | 21-37-030-010 | Buttrick Creek 2.8 mi W of IA 144 | 0.1 | Bridge Replacement | 2389000
1
30 | 1 | 25-37-030-010 | Jefferson to Grand Junction | 6.2 | Pavement Rehab | 4748000
1
(38) Grundy | 1
20 | 1 | 26-38-020-010 | IA 14 to U Ave | 6.8 | Paved Shoulders | 1800000
1
175 | 1 | 24-38-175-010 | Branch Blackhawk Creek 0.8 mi W of Co Rd T69 |  | Bridge Deck Overlay |  |  | 354000
1
(39) Guthrie | 1
25 | 1 | 26-39-025-010 | IA 141 to US 30 | 12.8 | Pavement Rehab | 5900000
1
(40) Hamilton | 1
17 | 1 | 25-40-017-020 | Boone River 1.3 mi S of US 20 |  | Bridge Deck Overlay |  |  |  | 2605000
1
20 | 1 | 25-40-020-010 | US 69 to I-35 (WB) | 4 | Paving |  |  |  |  | 10695000
1
35 | 1 | 24-40-035-020 | 1 mi N of IA 175 to 1 mi N of Co Rd D41 (SB) | 6.1 | Pavement Rehab |  | 1440000
1
35 | 1 | 24-40-035-030 | Co Rd D25/220th St to 0.1 mi S of Co Rd R75 | 7.1 | Pavement Rehab |  | 9822000
1
35 | 1 | 25-40-035-010 | 1 mi N of IA 175 to 1 mi N of Co Rd D41 (NB) | 6 | Pavement Rehab | 1500000
1
175 | 1 | 20-40-175-030 | E of I-35 to US 65 in Hubbard | 12.9 | Pavement Rehab | 4470000
1
(46) Humboldt | 1
169 | 1 | 22-46-169-010 | W Fork Des Moines River 0.6 mi S of IA 3 in Humboldt |  | Bridge Rehabilitation | 2319000
1
(50) Jasper | 1
6 | 1 | 23-50-006-020 | North Skunk River 1.3 mi E of IA 224 |  | Bridge Replacement |  | 6333000
| 1 |  |  |  | Right of Way |  | 60000
1
6 | 1 | 25-50-006-010 | 0.25 mi E of E 60th St |  | Culvert New |  | 542000
| 1 |  |  |  | Right of Way |  | 5000
1
6 | 1 | 25-50-006-020 | IAIS RR 1.5 mi E of IA 224 |  | Bridge New |  |  |  | 4298000
| 1 |  |  |  | Right of Way |  |  |  | 5000
1
14 | 1 | 24-50-014-020 | In Newton, N of 4th Ave to N of 23rd Ave | 1.5 | Grade & Pave | 5263000
1
14 | 1 | 24-50-014-030 | In Newton, I-80 to 0.25 mi N of 4th Ave | 1.7 | Grade & Pave |  |  | 9794000
1
65 | 1 | 23-50-065-010 | Indian Creek 0.2 mi S of IA 117 (NB) |  | Bridge Deck Overlay | 910000
1
80 | 1 | 25-50-080-030 | IAIS RR 0.4 mi W of IA 14 (EB/WB) |  | Right of Way |  | 10000
| 1 |  |  |  | Bridge New |  | 6552000
1
80 | 1 | 25-50-080-040 | IA 14 Interchange - Ramps | 0.4 | Pavement Rehab |  |  |  | 1371000
1
80 | 1 | 26-50-080-030 | Cherry Creek 1.2 mi W of IA 14 (EB/WB) |  | Right of Way |  | 10000
| 1 |  |  |  | Bridge New |  | 4914000
1
80 | 1 | 26-50-080-060 | Prairie Creek 4.3 mi E of IA 117 | 1 | Right of Way |  |  |  |  | 10000
| 1 |  |  |  | Bridge New |  |  |  |  | 6230000
1
80 | 1 | 26-50-080-070 | Iowa Speedway Dr Interchange 4.0 mi E of IA 14 | 1 | Right of Way |  |  |  |  | 10000
| 1 |  |  |  | Bridge New |  |  |  |  | 18692000
1
80 | 1 | 26-50-080-080 | IA 224 Interchange | 1 | Right of Way |  |  |  |  | 10000
| 1 |  |  |  | Bridge New |  |  |  |  | 18692000
1
117 | 1 | 22-50-117-010 | At the I-80 Interchange |  | Bridge Deck Overlay |  | 534000
1
224 | 1 | 26-50-224-010 | 0.1 mi S of N 75th Ave |  | Culvert Replacement | 532000
| 1 |  |  |  | Right of Way | 2000
1
(64) Marshall | 1
14 | 1 | 26-64-014-020 | UP RR, Madison, and Market St in Marshalltown |  | Bridge Deck Overlay |  |  |  |  | 6231000
1
14 | 1 | 26-64-014-010 | Linn Creek in Marshalltown |  | Bridge Deck Overlay |  |  |  |  | 1745000
1
330 | 1 | 22-64-330-010 | Clear Creek 1.8 mi S of Co Rd S52 |  | Bridge Deck Overlay | 486000
1
330 | 1 | 20-64-330-010 | Story Co Line to US 30 (Various Locations) | 29.5 | Pavement Rehab | 3500000
1
330 | 1 | 26-64-330-030 | Linn Creek 1.8 mi N of US 30 |  | Bridge New |  |  |  |  | 3365000
| 1 |  |  |  | Right of Way |  |  |  |  | 10000
1
330 | 1 | 26-64-330-020 | North Timber Creek 2.7 mi S of US 30 (NB/SB) |  | Bridge Deck Overlay |  |  |  |  | 1371000
1
(77) Polk | 1
6 | 1 | 26-77-006-020 | US 65 to S of I-80 in Altoona (NB/SB) | 1.2 | Right of Way | 5000
| 1 |  |  |  | Pavement Rehab | 2095000
1
28 | 1 | 26-77-028-020 | Raccoon River 2.1 mi S of I-235 (NB) |  | Bridge Deck Overlay |  |  |  |  | 2866000
1
35 | 1 | 16-77-035-050 | SW I-35/80/235 Interchange in West Des Moines | 4.4 | Erosion Control |  |  | 400000
| 1 |  |  |  | Grade & Pave | 43751000
| 1 |  |  |  | Bridge New | 74610000
| 1 |  |  |  | Traffic Signs | 4654000
| 1 |  |  |  | Noise Wall | 1295000
1
35 | 1 | 15-77-035-040-01 | N of NE 36th St in Ankeny to N of 315th St | 25.4 | Erosion Control | 1200000
1
35 | 1 | 10-77-035-010-05 | I-35/235 Interchange NE of Des Moines to US 65 | 0.1 | Traffic Signs | 2290000
| 1 |  |  |  | Erosion Control |  | 300000
| 1 |  |  |  | Grade & Pave | 22603000
| 1 |  |  |  | Bridge Replacement | 8061000
1
35 | 1 | 25-77-035-070 | SW I-80/I-235 Interchange - Various Ramps | 0.6 | Pavement Rehab |  |  |  | 997000
1
35 | 1 | 15-77-035-040-02 | N of 315th St to 0.5 mi S of Co Rd E57/260th St | 29.8 | Bridge Replacement | 2600000
| 1 |  |  |  | Traffic Signs | 1825000
| 1 |  |  |  | Erosion Control |  |  | 500000
| 1 |  |  |  | Mitigation | 100000
| 1 |  |  |  | Grade & Pave | 50673000
| 1 |  |  |  | Culvert Extension | 2802000
1
65 | 1 | 21-77-065-020 | US 6 Interchange 1.0 mi S of I-80 | 0.1 | Bridge Deck Overlay |  |  | 1813000
1
65 | 1 | 24-77-065-020 | At N IA 5 Interchange (NB/SB) |  | Bridge Deck Overlay |  |  | 2781000
1
65 | 1 | 24-77-065-030 | NE 46th Ave 1.2 mi S of I-80 (NB/SB) |  | Bridge Deck Overlay |  |  | 3515000
1
65 | 1 | 25-77-065-050 | IA 163 to I-80 (NB & SB) | 5.5 | Pavement Rehab | 4879000
1
65 | 1 | 26-77-065-020 | S of I-80 to 0.2 mi N of Lincoln St SE (NB/SB) | 3.2 | Pavement Rehab | 5472000
1
69 | 1 | 17-77-069-010 | DM River to N of Maury Ave in Des Moines (State Share) | 0.5 | Pavement Widening | 2900000
| 1 |  |  |  | Traffic Signals | 307000
1
69 | 1 | 19-77-069-010 | Fourmile Creek 0.3 mi N of Co Rd F22 |  | Bridge Replacement | 2356000
1
69 | 1 | 20-77-069-030 | Des Moines River 1.4 mi S of I-235 in Des Moines | 0.3 | Bridge Replacement |  |  | 24727000
| 1 |  |  |  | Right of Way |  |  | 240000
1
69 | 1 | 25-77-069-030 | BN RR, Scott Ave, and MLK Pkwy 0.7 mi S of I-235 |  | Bridge New |  |  |  | 52091000
| 1 |  |  |  | Right of Way |  |  |  | 10000
1
69 | 1 | 25-77-069-020 | Co Rd F22/NE 126th Ave Intersection |  | Grade & Pave | 3240000
| 1 |  |  |  | Right of Way | 10000
1
80 | 1 | 15-77-080-060 | University Ave to N of Douglas Ave | 7 | Grade & Pave | 7418000
| 1 |  |  |  | Traffic Signs | 300000
| 1 |  |  |  | Lighting | 2870000
| 1 |  |  |  | Traffic Signals | 2499000
| 1 |  |  |  | Erosion Control |  | 200000
1
80 | 1 | 19-77-080-010 | 2.1 mi E of IA 28/Merle Hay Rd | 268.2 | Guardrail | 500000
1
80 | 1 | 22-77-080-080 | Mitchellville Rest Area 1.4 mi W of Co Rd S27 (EB) | 0.6 | Right of Way |  | 349000
| 1 |  |  |  | Grading |  | 574000
| 1 |  |  |  | Grade & Pave |  |  | 10936000
| 1 |  |  |  | Traffic Signs |  |  | 342000
| 1 |  |  |  | Lighting |  |  | 247000
1
80 | 1 | 24-77-080-050 | Mitchellville Rest Area 1.4 mi W of Co Rd S27 (EB) |  | Rest Area Improvement |  | 5125000
1
80 | 1 | 26-77-080-030 | IA 28 / Merle Hay Rd Interchange |  | Traffic Signals | 500000
1
235 | 1 | 19-77-235-030 | SW I-35/80 Interchange to NE I-35/80 Interchange | 14.6 | Landscaping | 137000 |  | 285000 |  | 298000
1
235 | 1 | 25-77-235-070 | 0.3 mi W of 73rd Street to 31st Street (WB) | 3 | Pavement Rehab |  |  |  | 4204000
1
235 | 1 | 25-77-235-080 | 0.3 mi W of 73rd Street to 31st Street (EB) | 3 | Pavement Rehab |  |  |  | 4204000
1
235 | 1 | 25-77-235-090 | 50th Street to 0.3 mi W of 73rd Street (EB/WB) | 3.4 | Pavement Rehab |  |  |  | 8270000
1
415 | 1 | 24-77-415-030 | Rock Creek 1.9 mi N of IA 160 |  | Bridge Deck Overlay |  |  | 1342000
1
(79) Poweshiek | 1
6 | 1 | 23-79-006-010 | Stony Creek 0.4 mi W of W Jct Co Rd V18 |  | Bridge Replacement |  | 2174000
| 1 |  |  |  | Right of Way |  | 10000
1
63 | 1 | 22-79-063-010 | Stream 4.4 mi N of Co Rd G17 |  | Culvert Replacement | 1246000
| 1 |  |  |  | Right of Way | 10000
1
80 | 1 | 21-79-080-010 | W of IA 21 to E of IA 21 | 4 | Lighting | 90000 | 90000
| 1 |  |  |  | Traffic Signs | 100000 | 250000
| 1 |  |  |  | Erosion Control |  |  | 300000
| 1 |  |  |  | Grade & Pave |  | 14028000
| 1 |  |  |  | Bridge Replacement |  | 2812000
1
80 | 1 | 22-79-080-010 | 50th St 2.1 mi E of IA 146 (EB/WB) |  | Bridge Deck Overlay | 2525000
1
80 | 1 | 23-79-080-010 | At US 63 Interchange (EB/WB) |  | Right of Way |  |  | 700000
| 1 |  |  |  | Bridge Replacement |  |  | 2907000 |  | 3477000
| 1 |  |  |  | Grade & Pave |  |  | 13866000 |  | 10870000
| 1 |  |  |  | Lighting |  |  |  |  | 250000
| 1 |  |  |  | Traffic Signs |  | 225000 | 450000 |  | 225000
1
80 | 1 | 25-79-080-020 | Co Rd V18 and Co Rd V38 Interchanges - Ramps | 9.2 | Pavement Rehab |  |  |  | 1122000
1
146 | 1 | 24-79-146-010 | North Skunk River 2.7 mi N of US 63 |  | Bridge Replacement |  |  | 9828000
| 1 |  |  |  | Right of Way |  |  | 20000
1
(00) Statewide | 1
0 | 1 | 26-00-000-090 | Various Counties and Routes in District 1 |  | Pavement Markings | 500000
1
(85) Story | 1
30 | 1 | 13-85-030-010-01 | 610th Ave Interchange at Nevada | 2.1 | Right of Way | 9750000
| 1 |  |  |  | Erosion Control |  |  |  | 350000
| 1 |  |  |  | Railroad Signals | 500000
| 1 |  |  |  | Grading |  |  | 7200000
| 1 |  |  |  | Bridge New |  |  | 3309000
| 1 |  |  |  | Paving |  |  |  | 9947000
| 1 |  |  |  | Traffic Signs |  | 300000 | 125000 | 375000
| 1 |  |  |  | Lighting |  |  |  | 180000
1
30 | 1 | 19-85-030-020 | South Skunk River from Duff Ave to Dayton Ave in Ames (EB/WB) | 15.8 | Bridge Replacement | 4030000
| 1 |  |  |  | Erosion Control |  | 350000
| 1 |  |  |  | Grade & Pave | 2771000
| 1 |  |  |  | Traffic Signs | 200000
| 1 |  |  |  | Culvert New | 1746000
| 1 |  |  |  | Lighting | 216000
1
30 | 1 | 23-85-030-010 | W Branch Indian Creek 0.5 mi E of Co Rd S14 (WB) |  | Bridge Deck Overlay | 898000
1
30 | 1 | 26-85-030-010 | At Co Rd R38 Interchange (NB) |  | Bridge Deck Overlay |  |  |  |  | 1495000
1
30 | 1 | 26-85-030-020 | Bike Path & Trail 1.1 mi W of US 69 (WB) |  | Bridge Deck Overlay |  |  |  |  | 1620000
1
35 | 1 | 11-85-035-020-04 | 0.5 mi S of Co Rd E57/260th St to 0.6 mi N of US 30 | 1.9 | Right of Way |  | 5900000
| 1 |  |  |  | Lighting |  |  |  | 450000 | 350000
| 1 |  |  |  | Bridge Replacement |  |  |  | 7150000 | 5500000
| 1 |  |  |  | Grade & Pave |  |  | 12560000 | 14100000 | 17000000
| 1 |  |  |  | Traffic Signs |  | 475000 | 750000 | 750000 | 750000
1
35 | 1 | 25-85-035-020 | 13th St Interchange 1.8 mi N of US 30 in Ames (NB/SB) |  | Bridge Deck Overlay |  |  |  | 2345000
1
35 | 1 | 26-85-035-060 | US 30 to Hamilton Co (SB) | 14.3 | Pavement Rehab |  |  |  |  | 11903000
1
65 | 1 | 25-85-065-010 | 0.2 mi S of 310th St in Collins |  | Culvert New |  | 436000
| 1 |  |  |  | Right of Way |  | 5000
1
65 | 1 | 25-85-065-020 | 0.2 mi S of Co Rd E41 in Colo |  | Culvert New |  | 75000
1
(86) Tama | 1
63 | 1 | 20-86-063-010 | NCL Toledo to 0.5 mi S of IA 96 | 23.5 | Erosion Control | 250000
1
63 | 1 | 21-86-063-030 | Iowa River 1.3 mi N of Co Rd E64 | 0.3 | Bridge Deck Overlay | 1274000
1
(91) Warren | 1
5 | 1 | 26-91-005-020 | Scotch Ridge Rd to US 65 | 1.6 | Paved Shoulders | 800000
1
65 | 1 | 22-91-065-010 | Stream 0.2 mi N of Co Rd G24 (NB) |  | Bridge Replacement | 1956000
| 1 |  |  |  | Right of Way | 5000
1
(94) Webster | 1
144 | 1 | 22-94-144-010 | East Buttrick Creek 2.2 mi S of IA 175 |  | Culvert Replacement | 956000
| 1 |  |  |  | Right of Way | 29000
| 1 |  |  |  | Mitigation | 94000
1
169 | 1 | 22-94-169-020 | Bass Creek 0.6 mi S of Co Rd C56 |  | Culvert Replacement |  | 2055000
| 1 |  |  |  | Right of Way |  | 15000
| 1 |  |  |  | Mitigation |  | 110000
1
175 | 1 | 20-94-175-020 | Des Moines River 1.8 mi E of Co Rd P70 |  | Bridge Replacement |  | 15463000
| 1 |  |  |  | Right of Way |  | 22000
1
175 | 1 | 20-94-175-030 | Ditch #52 0.8 mi E of Co Rd P29 |  | Culvert Replacement | 980000
1
(99) Wright | 1
35 | 1 | 24-99-035-010 | 0.1 mi S of Co Rd R75 to 0.6 mi N of Co Rd C47 (NB/SB) | 9.8 | Pavement Rehab |  |  | 12680000

## Sheet2
2027 - 2031 Five Year Program
This information is valid for the date of Commission approval of None
Line Items
Project Estimated Costs X $1000
| County | Location | Type Of Work | 2027 | 2028 | 2029 | 2030 | 2031
| Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 108672000 | 193330000 | 198399000 | 209400000
| Statewide | Statewide Safety Specific | Paving | 0 | 36000000 | 37000000 | 38000000 | 38000000
| Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 5000000 | 15000000 | 15000000 | 15000000
| Statewide | American with Disabilities Act | Pedestrian Improvement | 5500000 | 5500000 | 5500000 | 5500000 | 5500000
| Statewide | Construction Training Program | Training | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
| Statewide | Cooperative City/County/State Highway Research | Research | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Emergency & Contingency (U-STEP/C-STEP) | Construction | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
| Statewide | Pavement Markings | Paint | 12700000 | 12700000 | 12700000 | 12700000 | 12700000
| Statewide | Post Letting Project Cost | Construction | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
| Statewide | Prevocational Training and DBE Support Services | Training | 360000 | 360000 | 360000 | 360000 | 360000
| Statewide | Scenic Byway Program | Signs | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Consultant Services | Outside Services Engineering | 75000000 | 75000000 | 75000000 | 75000000 | 75000000
| Statewide | Statewide Contract Maintenance | Construction | 53300000 | 58000000 | 58500000 | 59000000 | 59500000
| Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide ITS | Equipment | 8000000 | 8000000 | 8000000 | 8000000 | 8000000
| Statewide | Statewide Lighting | Lighting | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide Operations | Outside Services Engineering | 16000000 | 16000000 | 16000000 | 16000000 | 16000000
| Statewide | Statewide Railroad Crossings | Construction | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 10600000 | 10700000 | 10800000 | 10900000 | 11000000
| Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Statewide Traffic Control Devices | Signs | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
| Statewide | Summer Infrastructure Rehabilitation Materials | Materials | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
| Statewide | Winter Operations Materials | Materials | 12000000 | 12000000 | 12000000 | 12000000 | 12000000