## Sheet1
2027 - 2031 IOWA HIGHWAY PROGRAM
S.F 257 Only: No | [5 empty] | Project Estimated Costs X $1000
Route |  | Project Code | Location | Miles | Type of Work | 2027 | 2028 | 2029 | 2030 | 2031
(11) Buena Vista
7 | 3 | 25-11-007-040 | W of 70th Ave to E of 80th Ave | 1.7 | Grade & Pave |  | 4700000
| 3 |  |  |  | Railroad Signals |  | 400000
3
71 | 3 | 24-11-071-010 | S of S Jct IA 10 to 0.25 mi N of Clay Co Line | 4.2 | Pavement Rehab | 743000
3
(13) Calhoun | 3
4 | 3 | 26-13-004-010 | 0.25 mi S of Rockwell City to E Jct Co Rd D36 | 1.2 | Pavement Rehab | 210000
3
(14) Carroll | 3
71 | 3 | 22-14-071-010 | UP RR and Local Streets 0.2 mi S of US 30 in Carroll |  | Bridge Deck Overlay |  | 2009000
3
71 | 3 | 24-14-071-020 | 0.5 mi S of Co Rd E25 to Sac Co | 7.6 | Grade & Pave |  |  |  | 18109000
3
(18) Cherokee | 3
3 | 3 | 24-18-003-010 | Fork Little Sioux River 2.5 mi E of IA 143 |  | Bridge Deck Overlay |  |  | 650000
3
31 | 3 | 24-18-031-010 | Stratton Creek 0.1 mi N of Co Rd C66 |  | Bridge Replacement |  |  | 1988000
| 3 |  |  |  | Right of Way |  |  | 5000
3
59 | 3 | 24-18-059-010 | Grey Creek 2.1 mi N of Co Rd C16 |  | Bridge Deck Overlay |  |  | 455000
3
(21) Clay | 3
18 | 3 | 23-21-018-010 | Little Sioux River 2.1 mi W of W Jct US 71 |  | Bridge Replacement |  | 2500000
| 3 |  |  |  | Right of Way |  | 10000
| 3 |  |  |  | Mitigation |  | 60000
3
18 | 3 | 23-21-018-020 | N US 71 Intersection in Spencer |  | Grade & Pave | 3650000
| 3 |  |  |  | Traffic Signs | 60000
| 3 |  |  |  | Lighting | 225000
| 3 |  |  |  | Grade & Pave | 500000
| 3 |  |  |  | Pavement Rehab | 700000
| 3 |  |  |  | Right of Way | 600000
3
71 | 3 | 25-21-071-010 | 18th St SW to 0.1 mi E of the E Jct US 18 in Spencer | 2 | Pavement Markings | 519000
3
(24) Crawford | 3
30 | 3 | 20-24-030-010 | Boyer River 2.7 mi W of US 59 | 0.1 | Bridge Replacement |  | 3726000
3
30 | 3 | 22-24-030-010 | UP RR 0.4 mi E of W Jct US 59 in Denison (EB/WB) |  | Bridge Replacement |  |  | 22182000
| 3 |  |  |  | Right of Way |  |  | 46000
3
30 | 3 | 25-24-030-020 | Flasher Creek 5.6 mi N of IA 37 |  | Bridge Deck Overlay |  |  |  | 652000
3
30 | 3 | 21-24-030-010 | 20th St in Denison to E of Carroll Co Line | 25.7 | Pavement Rehab | 8610000
3
39 | 3 | 25-24-039-010 | Otter Creek 5.6 mi N of US 59 |  | Bridge New |  |  |  | 6310000
| 3 |  |  |  | Right of Way |  |  |  | 5000
3
59 | 3 | 22-24-059-020 | Boyer River 0.1 mi S of IA 39 in Denison (SB) |  | Bridge Deck Overlay | 1068000
3
59 | 3 | 25-24-059-020 | CC RR 0.4 mi S of IA 39 (NB/SB) |  | Bridge New |  |  |  |  | 13065000
| 3 |  |  |  | Right of Way |  |  |  |  | 5000
3
141 | 3 | 25-24-141-010 | Emigrant Creek 2.1 mi W of Co Rd M 14 |  | Bridge Deck Overlay |  |  |  | 977000
3
141 | 3 | 26-24-141-010 | In Charter Oak, Emigrant Creek 0.7 mi W of W Jct Co Rd L51 |  | Bridge Deck Overlay |  |  |  |  | 374000
3
(32) Emmet | 3
4 | 3 | 22-32-004-020 | Drainage Ditch 1.5 mi N of N Jct Co Rd A34 |  | Bridge Deck Overlay | 737000
3
9 | 3 | 24-32-009-010 | In Estherville, Des Moines River Bridge to S 28th St | 1.8 | Right of Way |  | 11000
| 3 |  |  |  | Grade & Pave |  | 8025000
3
9 | 3 | 25-32-009-010 | Des Moines River 0.6 mi W of IA 4 |  | Bridge Deck Overlay |  |  |  | 2865000
3
(43) Harrison | 3
29 | 3 | 26-43-029-050 | Little Sioux River 0.4 mi N of Co Rd F20 (NB/SB) |  | Bridge Rehabilitation |  |  | 1141000
3
37 | 3 | 21-43-037-010 | Boyer River 0.1 mi W of US 30 | 0.1 | Bridge Replacement |  | 6431000
| 3 |  |  |  | Right of Way |  | 20000
3
(47) Ida | 3
31 | 3 | 24-47-031-010 | Ashton Creek 1.0 mi N of Co Rd D15 |  | Bridge Deck Overlay |  |  | 520000
3
175 | 3 | 26-47-175-020 | Chestnut St in Battle Creek to N Jct US 59 | 5.4 | Pavement Rehab | 565000
3
175 | 3 | 26-47-175-030 | Branch Odebolt River 2.5 mi W of Co Rd M31 |  | Bridge New |  |  |  |  | 748000
| 3 |  |  |  | Right of Way |  |  |  |  | 10000
3
(60) Lyon | 3
9 | 3 | 18-60-009-010 | South Dakota east 0.5 mi |  | Grade & Pave |  |  | 560000
3
9 | 3 | 24-60-009-030 | Approx 1.4 mi W of Co Rd K60 |  | Culvert Replacement | 444000
| 3 |  |  |  | Right of Way | 10000
3
9 | 3 | 24-60-009-040 | Little Rock River 1.0 mi W of Co Rd L26 |  | Bridge Deck Overlay |  |  |  | 1019000
3
(67) Monona | 3
29 | 3 | 22-67-029-020 | Onawa Rest Area 2.6 mi S of IA 175 (SB |  | Rest Area Improvement |  |  | 5125000
3
29 | 3 | 22-67-029-040 | N of Co Rd E60 to IA 175 (SB) | 7.7 | Paving |  | 25071000
3
29 | 3 | 24-67-029-060 | Onawa Rest Area 2.6 mi S of IA 175 (NB) |  | Rest Area Improvement | 5125000
3
29 | 3 | 25-67-029-010 | Co Rd E90 Interchange |  | Bridge Deck Overlay |  |  |  |  | 1021000
3
37 | 3 | 22-67-037-010 | Norway Creek 2.6 mi E of IA 183 |  | Bridge Deck Overlay | 750000
3
37 | 3 | 24-67-037-010 | Beaver Creek 4.4 mi E of IA 175 |  | Bridge Replacement |  |  | 3151000
| 3 |  |  |  | Right of Way |  |  | 12000
3
141 | 3 | 23-67-141-010 | Maple River 0.1 mi E of W Jct IA 175 in Mapleton |  | Bridge Replacement |  | 5109000
| 3 |  |  |  | Right of Way |  | 10000
3
141 | 3 | 24-67-141-030 | Soldier River 3.9 mi W of IA 183 |  | Bridge Replacement |  |  | 5414000
| 3 |  |  |  | Right of Way |  |  | 4000
3
175 | 3 | 13-67-175-010 | Missouri River E of Decatur Nebraska (State Share) | 0.5 | Bridge Washing | 22000 | 22000 | 22000 | 22000 | 22000
3
175 | 3 | 16-67-175-010 | Missouri River E of Decatur Nebraska (State Share) | 0.5 | Bridge Rehabilitation | 111000 | 111000 | 111000 | 111000 | 111000
3
175 | 3 | 20-67-175-020 | Little Sioux River 1.5 mi W of IA 37 | 0.1 | Bridge Replacement | 8494000
3
3
175 | 3 | 26-67-175-020 | IA 37 to 0.26 mi SW of S Front St in Mapleton | 13 | Pavement Rehab | 2060000
3
175 | 3 | 26-67-175-060 | Maple River 0.1 mi W of IA 37 |  | Bridge Deck Overlay |  |  |  |  | 1495000
3
175 | 3 | 26-67-175-070 | Blue Lake Creek 2.1 mi W of I-29 |  | Bridge New |  |  |  |  | 810000
| 3 |  |  |  | Right of Way |  |  |  |  | 10000
3
175 | 3 | 24-67-175-010 | Missouri River E of Decatur, Nebraska |  | Bridge New |  |  |  |  | 24300000
3
183 | 3 | 24-67-183-020 | Jordan Creek 0.8 mi S of Co Rd E54 |  | Bridge Deck Overlay |  |  | 520000
| 3 |  |  |  | Right of Way |  |  | 11000
3
183 | 3 | 26-67-183-010 | Soldier River 1.1 mi S of IA 141 |  | Bridge Deck Overlay |  |  |  |  | 1153000
3
(71) O'Brien | 3
18 | 3 | 24-71-018-030 | Stream 0.2 mi W of Co Rd M22 |  | Culvert Replacement |  |  | 1450000
| 3 |  |  |  | Right of Way |  |  | 5000
| 3 |  |  |  | Mitigation |  |  | 120000
3
18 | 3 | 26-71-018-010 | Drainage Ditch 1.3 mi E of Co Rd M12 |  | Bridge New |  |  |  |  | 1122000
| 3 |  |  |  | Right of Way |  |  |  |  | 10000
3
(72) Osceola | 3
9 | 3 | 24-72-009-020 | Otter Creek 2.5 mi W of Co Rd L40 |  | Bridge Deck Overlay |  |  | 851000
3
9 | 3 | 24-72-009-030 | Polly Creek 0.9 mi W of IA 60 |  | Culvert Replacement |  |  | 1029000
| 3 |  |  |  | Right of Way |  |  | 6000
| 3 |  |  |  | Mitigation |  |  | 115000
3
59 | 3 | 24-72-059-010 | Approx 0.2 mi S of 250th St |  | Culvert Replacement | 382000
| 3 |  |  |  | Right of Way | 10000
3
59 | 3 | 24-72-059-020 | Approx 0.9 mi n of Co Rd A22 |  | Culvert Replacement | 460000
| 3 |  |  |  | Right of Way | 10000
| 3 |  |  |  | Mitigation | 50000
3
60 | 3 | 23-72-060-030 | Drainage Ditch 2.6 mi N of Co Rd B14 (SB) |  | Bridge New |  | 1250000
| 3 |  |  |  | Right of Way |  | 10000
| 3 |  |  |  | Mitigation |  | 80000
3
(74) Palo Alto | 3
4 | 3 | 21-74-004-020 | W Fork Des Moines River 3.2 mi S of S Jct US 18 | 0.1 | Bridge Replacement |  | 6826000
3
4 | 3 | 22-74-004-010 | Drainage Ditch 1.3 mi S of Co Rd B57 |  | Bridge Replacement |  | 1363000
3
18 | 3 | 25-74-018-070 | Side Ditch Bridge 2.0 mi W of IA 4 |  | Bridge New |  |  |  | 1283000
| 3 |  |  |  | Right of Way |  |  |  | 5000
3
18 | 3 | 25-74-018-060 | 0.67 mi E of Co Rd N28 to Superior St in Emmetsburg | 7.4 | Pavement Rehab | 3548000
3
18 | 3 | 25-74-018-040 | Emmetsburg to Cylinder | 7.3 | Pavement Rehab | 3436000
3
18 | 3 | 25-74-018-030 | 4th St in Cylinder to 0.14 mile E of ECL Cylinder | 0.5 | Pavement Rehab | 352000
3
18 | 3 | 25-74-018-050 | 0.14 mile E of ECL Cylinder to W Jct IA 15 | 5.2 | Pavement Rehab | 2321000
3
(75) Plymouth | 3
3 | 3 | 23-75-003-030 | Floyd River 1.0 mi E of US 75 in Le Mars |  | Bridge Deck Overlay | 1167000
3
3 | 3 | 24-75-003-030 | Big Sioux Overflow 1.0 mi W of IA 12 |  | Bridge New |  |  |  | 2586000
| 3 |  |  |  | Right of Way |  |  |  | 10000
3
3 | 3 | 25-75-003-040 | Big Sioux Overflow 1.3 mi W of IA 12 |  | Bridge New |  |  |  | 2475000
| 3 |  |  |  | Right of Way |  |  |  | 5000
3
3 | 3 | 25-75-003-050 | Westfield Creek 0.2 mi W of W Jct IA 12 |  | Bridge New |  |  |  | 3712000
| 3 |  |  |  | Right of Way |  |  |  | 5000
3
12 | 3 | 22-75-012-010 | Beaver Creek 0.5 mi N of Co Rd C16 |  | Bridge Deck Overlay | 770000
3
12 | 3 | 22-75-012-030 | Broken Kettle Creek 0.1 mi N of S Jct Co Rd K18 |  | Bridge Replacement | 2301000
3
12 | 3 | 26-75-012-010 | NCL Akron to 8th St in Hawarden | 11.9 | Pavement Rehab | 1557000
3
75 | 3 | 21-75-075-010 | S of W Grover St to N of Maple St in Hinton | 1.5 | Railroad Signals |  |  | 1350000
| 3 |  |  |  | Grade & Pave |  |  | 7650000
| 3 |  |  |  | Traffic Signals |  |  | 2119000
| 3 |  |  |  | Bridge Replacement |  |  | 2708000
3
75 | 3 | 22-75-075-020 | W Fork Floyd River 2.4 mi N of Co Rd R38 |  | Bridge Deck Overlay | 1131000
3
75 | 3 | 24-75-075-030 | Stream 0.6 mi S of Co Rd C60 (NB) |  | Bridge New |  |  | 1501000
3
75 | 3 | 26-75-075-030 | Stream 1.3 mi N of Co Rd C70 (NB/SB) |  | Bridge New |  |  |  |  | 1495000
| 3 |  |  |  | Right of Way |  |  |  |  | 10000
3
75 | 3 | 26-75-075-020 | Co Rd C80 and Co Rd C70 Intersections | 1.5 | Grade & Pave | 1800000
| 3 |  |  |  | Traffic Signs | 100000
| 3 |  |  |  | Lighting | 100000
3
404 | 3 | 24-75-404-010 | Floyd River 0.4 mi N of IA 3 in Le Mars (NB) |  | Bridge Rehabilitation |  |  | 3260000
3
(76) Pocahontas | 3
3 | 3 | 24-76-003-010 | North Lizard Creek 0.8 mi W of IA 15 |  | Bridge Deck Overlay |  |  | 520000
3
3 | 3 | 25-76-003-010 | In Pocahontas, from W of W 2nd St to 0.15 mi E of NE 6th St | 0.8 | Pavement Rehab | 1166000
3
4 | 3 | 23-76-004-030 | North Lizard Creek 5.6 mi N of IA 3 |  | Bridge Deck Overlay | 854000
3
4 | 3 | 25-76-004-030 | Pilot Creek 1.4 mi N of Co Rd C26 |  | Bridge Deck Overlay |  |  |  | 880000
3
4 | 3 | 25-76-004-020 | SCL Pocahontas to Jct. Ia 3 | 0.3 | Pavement Rehab | 444000
3
4 | 3 | 26-76-004-010 | N Jct IA 7 to 0.35 mi S of IA 3 in Pocahontas | 9.4 | Pavement Rehab | 4120000
3
7 | 3 | 25-76-007-020 | Big Cedar Creek 0.4 mi E of Co Rd N28 |  | Bridge Deck Overlay |  |  |  | 782000
3
10 | 3 | 23-76-010-010 | Little Cedar Creek 3.7 mi W of Co Rd N28 |  | Bridge Deck Overlay | 707000
3
15 | 3 | 22-76-015-010 | Pilot Creek at the N Jct Co Rd C26 |  | Bridge Replacement | 2160000
3
15 | 3 | 25-76-015-010 | Pine St in Rolfe to Co Rd C12 | 9.2 | Pavement Rehab | 1474000
3
(81) Sac | 3
20 | 3 | 23-81-020-010 | North Raccoon River 1.0 mi W of Co Rd M54 (EB/WB) |  | Bridge Deck Overlay | 1855000
3
71 | 3 | 24-81-071-010 | Carroll Co to Jct IA 175 in Auburn | 2.8 | Grade & Pave |  |  | 7012000
3
71 | 3 | 26-81-071-010 | S Jct IA 175 in Auburn to N Jct IA 175 | 7.8 | Pavement Rehab | 1748000
3
175 | 3 | 24-81-175-010 | High St 1.9 mi E of Co Rd M64 |  | Bridge New |  |  | 7989000
| 3 |  |  |  | Right of Way |  |  | 10000
3
175 | 3 | 26-81-175-010 | IA 471 to W Jct. US 71 | 9.4 | Pavement Rehab | 4085000
3
(83) Shelby | 3
59 | 3 | 24-83-059-010 | Lyon Creek 2.6 mi S of IA 37 |  | Bridge Deck Overlay |  |  | 600000
3
(84) Sioux | 3
10 | 3 | 24-84-010-010 | UP RR 1.0 mi W of IA 60 |  | Bridge Deck Overlay |  |  | 1300000
3
10 | 3 | 24-84-010-020 | Dry Creek 0.4 mi W of IA 12 in Hawarden |  | Grading |  |  | 749000
| 3 |  |  |  | Right of Way |  |  | 4000
3
10 | 3 | 25-84-010-070 | In Orange City, from W of Albany Ave to Salem Ave | 0.9 | Pavement Rehab | 347000
3
10 | 3 | 26-84-010-030 | Floyd River 0.7 mi W of N Jct IA 60 |  | Bridge Deck Overlay |  |  |  |  | 2119000
3
18 | 3 | 24-84-018-040 | Division St in Hull to College Dr. in Sheldon | 13.2 | Pavement Rehab | 1410000
3
60 | 3 | 21-84-060-010 | Floyd River Tributary 0.5 mi S of Co Rd K64 (NB) |  | Bridge Replacement | 2572000
3
60 | 3 | 23-84-060-010 | Floyd River Tributary 0.5 mi S of Co Rd K64 (SB) |  | Bridge Deck Overlay |  | 482000
3
75 | 3 | 17-84-075-010 | S of 12th St NE in Sioux Center to S Jct US 18 | 6.1 | Traffic Signals |  | 342000
| 3 |  |  |  | Grade & Pave |  | 20984000
3
75 | 3 | 24-84-075-020 | W Fork Floyd River 0.1 mi N of IA 10 |  | Bridge Deck Overlay |  |  | 1099000
3
75 | 3 | 26-84-075-020 | W Fork Floyd River 2.8 mi S of Co Rd B58 |  | Bridge Deck Overlay |  |  |  |  | 1246000
3
(00) Statewide | 3
0 | 3 | 26-00-000-110 | Various Counties and Routes in District 3 |  | Pavement Markings | 500000
3
(97) Woodbury | 3
12 | 3 | 19-97-012-010 | Gordon Dr Viaduct, Rustin St to Virginia St in Sioux City | 2.4 | Railroad Signals |  | 750000
| 3 |  |  |  | Bridge Rehabilitation | 150000
| 3 |  |  |  | Right of Way | 23520000
| 3 |  |  |  | Grade & Pave |  | 21481000 | 40281000 | 39853000
| 3 |  |  |  | Bridge New | 2402000
| 3 |  |  |  | Bridge Removal |  | 6542000
| 3 |  |  |  | Culvert New |  | 1101000
| 3 |  |  |  | Traffic Signals |  | 3355000
| 3 |  |  |  | Traffic Signs |  | 2488000
| 3 |  |  |  | Bridge Replacement |  | 27572000 | 29394000 | 7245000
3
12 | 3 | 26-97-012-040 | US 20/US 75 Interchange (NB/SB) |  | Bridge Deck Overlay |  |  |  |  | 5358000
3
20 | 3 | 98-97-020-010-08 | Mitigation - Woodbury Ida and Sac Counties US 20 |  | Wetland Mitigation | 195000
3
20 | 3 | 22-97-020-040 | Sunnybrook Dr 1.7 mi W of IA 12 in Sioux City (EB/WB) |  | Bridge Deck Overlay | 903000
3
20 | 3 | 25-97-020-030 | Little Sioux River 0.4 mi W of IA 31 (EB/WB) |  | Bridge Deck Overlay |  |  |  | 3517000
3
20 | 3 | 25-97-020-040 | Eastland Ave to Fayette Ave | 2 | Pavement Markings | 344000
3
29 | 3 | 25-97-029-090 | Monona County Line to SCL of Sergeant Bluff (NB) | 14 | Pavement Rehab |  |  |  | 5608000
3
29 | 3 | 26-97-029-010 | Big Sioux River in Sioux City (NB/SB) |  | Bridge Rehabilitation |  | 600000
3
29 | 3 | 26-97-029-030 | Frontage Rd and IA 12/S Virginia St Intersection in Sioux City |  | Traffic Signals | 103000
3
29 | 3 | 25-97-029-100 | SCL of Sergeant Bluff to South Dakota (NB/SB) | 11.2 | Pavement Rehab |  |  |  |  | 5209000
3
31 | 3 | 17-97-031-010-01 | Co Rd C66 in Washta to US 59 | 9.9 | Culvert Extension | 1450000
3
75 | 3 | 25-97-075-040 | CCP RR, BNSF RR, and Business 75 5.8 mi N of IA 12 (NB) |  | Bridge Deck Overlay |  |  |  | 6121000
3
77 | 3 | 16-97-077-010 | Missouri River in Sioux City (State Share) | 0.3 | Bridge Washing | 35780 | 36000 | 36000 | 36000 | 36000
3
77 | 3 | 23-97-077-020 | Wesley Pkwy over Tri View Ave and BNSF RR in Sioux City |  | Bridge Rehabilitation | 283000
3
77 | 3 | 25-97-077-010 | Missouri River in Sioux City |  | Bridge Rehabilitation |  |  |  | 300000
3
129 | 3 | 16-97-129-010 | Missouri River in Sioux City (State Share) | 0.3 | Bridge Washing | 50000 | 50000 | 50243 | 50000 | 50000
3
141 | 3 | 23-97-141-030 | W Branch Little Sioux River 0.8 mi E of Co Rd K64 |  | Bridge Replacement |  |  | 3407000
| 3 |  |  |  | Right of Way |  |  | 12000
3
141 | 3 | 24-97-141-010 | Fork Little Sioux River 0.3 mi W of Co Rd K64 |  | Bridge New |  |  |  | 1947000
3
141 | 3 | 24-97-141-020 | Smokey Hollow Creek 0.2 mi E of IA 31 |  | Bridge Replacement |  |  | 1924000
| 3 |  |  |  | Right of Way |  |  | 20000
3
175 | 3 | 20-97-175-010 | Reynolds Creek 1.6 mi W of Co Rd L37 |  | Bridge Replacement | 1988000
3
376 | 3 | 21-97-376-020 | Lincoln Way to N of Cunningham Dr in Sioux City | 1.8 | Pavement Rehab | 1087000
3
376 | 3 | 21-97-376-030 | Tributary to Floyd River 0.1 mi N of Co Rd D12 in Sioux City (SB) |  | Bridge Replacement | 1284000
3
376 | 3 | 26-97-376-020 | Dry Creek 0.1 mi N of Co Rd D12 (NB) |  | Bridge Deck Overlay |  |  |  |  | 150000
3
376 | 3 | 26-97-376-030 | Floyd River 1.3 mi S of Co Rd D12 |  | Bridge New |  |  |  |  | 21684000
| 3 |  |  |  | Right of Way |  |  |  |  | 10000

## Sheet2
2027 - 2031 Five Year Program
This information is valid for the date of Commission approval of None
Line Items
Project Estimated Costs X $1000
| County | Location | Type Of Work | 2027 | 2028 | 2029 | 2030 | 2031
| Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 108672000 | 193330000 | 198399000 | 209400000
| Statewide | Statewide Safety Specific | Paving | 0 | 36000000 | 37000000 | 38000000 | 38000000
| Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 5000000 | 15000000 | 15000000 | 15000000
| Statewide | American with Disabilities Act | Pedestrian Improvement | 5500000 | 5500000 | 5500000 | 5500000 | 5500000
| Statewide | Construction Training Program | Training | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
| Statewide | Cooperative City/County/State Highway Research | Research | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Emergency & Contingency (U-STEP/C-STEP) | Construction | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
| Statewide | Pavement Markings | Paint | 12700000 | 12700000 | 12700000 | 12700000 | 12700000
| Statewide | Post Letting Project Cost | Construction | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
| Statewide | Prevocational Training and DBE Support Services | Training | 360000 | 360000 | 360000 | 360000 | 360000
| Statewide | Scenic Byway Program | Signs | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Consultant Services | Outside Services Engineering | 75000000 | 75000000 | 75000000 | 75000000 | 75000000
| Statewide | Statewide Contract Maintenance | Construction | 53300000 | 58000000 | 58500000 | 59000000 | 59500000
| Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide ITS | Equipment | 8000000 | 8000000 | 8000000 | 8000000 | 8000000
| Statewide | Statewide Lighting | Lighting | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide Operations | Outside Services Engineering | 16000000 | 16000000 | 16000000 | 16000000 | 16000000
| Statewide | Statewide Railroad Crossings | Construction | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 10600000 | 10700000 | 10800000 | 10900000 | 11000000
| Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Statewide Traffic Control Devices | Signs | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
| Statewide | Summer Infrastructure Rehabilitation Materials | Materials | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
| Statewide | Winter Operations Materials | Materials | 12000000 | 12000000 | 12000000 | 12000000 | 12000000