## Sheet1
2027 - 2031 IOWA HIGHWAY PROGRAM
S.F 257 Only: No | [5 empty] | Project Estimated Costs X $1000
Route |  | Project Code | Location | Miles | Type of Work | 2027 | 2028 | 2029 | 2030 | 2031
(01) Adair
80 | 4 | 22-01-080-040 | Antique Country Dr 3.5 mi W of IA 25 (EB/WB) |  | Bridge Rehabilitation | 516000
4
80 | 4 | 22-01-080-050 | At the Co Rd G30 Interchange |  | Bridge Rehabilitation | 1729000
4
80 | 4 | 22-01-080-060 | At the Co Rd P28 Interchange |  | Bridge Rehabilitation | 1625000
4
80 | 4 | 23-01-080-040 | Co Rd N54 Interchange at Adair |  | Bridge Replacement |  |  |  | 3502000
4
92 | 4 | 24-01-092-020 | Middle Nodaway River 2.4 mi W of IA 25 |  | Bridge Rehabilitation |  |  | 1170000
4
(02) Adams | 4
34 | 4 | 22-02-034-010 | Metz Creek 2.3 mi. W of W Jct. IA 25 |  | Bridge Replacement | 2056000
| 4 |  |  |  | Right of Way | 12000
4
34 | 4 | 22-02-034-020 | E Nodaway River and RR 0.8 mi W of IA 148 |  | Bridge Replacement |  |  |  | 21208000
| 4 |  |  |  | Right of Way |  |  |  | 24000
4
34 | 4 | 24-02-034-010 | Kemp Creek 4.8 mi W of IA 148 |  | Bridge Replacement |  |  |  | 5611000
4
148 | 4 | 21-02-148-010 | Branch E Nodaway River 0.4 mi N of Co Rd N28 | 0.1 | Bridge Deck Overlay | 445000
4
(05) Audubon | 4
71 | 4 | 25-05-071-010 | Stream 3.1 mi N of I-80 |  | Bridge Deck Overlay |  |  |  | 326000
4
71 | 4 | 25-05-071-020 | Stream 1.7 mi N of I-80 |  | Bridge New |  |  |  | 1303000
| 4 |  |  |  | Right of Way |  |  |  | 5000
4
(15) Cass | 4
6 | 4 | 22-15-006-010 | Spring Creek 1.4 mi E of IA 48 |  | Bridge Replacement |  | 2694000
| 4 |  |  |  | Right of Way |  | 12000
4
6 | 4 | 23-15-006-010 | Turkey Creek 3.7 mi E of IA 48 |  | Bridge Replacement |  | 3785000
| 4 |  |  |  | Right of Way |  | 10000
4
71 | 4 | 25-15-071-010 | Lone Tree Creek 0.1 mi S of Co Rd G35 |  | Bridge Rehabilitation | 568000
4
71 | 4 | 26-15-071-030 | Seven Mile Creek 0.6 mi S of N Jct IA 92 |  | Bridge Deck Overlay |  |  |  |  | 1084000
4
80 | 4 | 23-15-080-020 | 770th St 1.7 mi E of IA 148 (EB/WB) |  | Right of Way |  |  | 12000
| 4 |  |  |  | Bridge New |  |  | 9542000
4
80 | 4 | 24-15-080-010 | Pottawattamie Co to E of IA 173 (EB) | 5.6 | Pavement Rehab |  | 5956000
4
83 | 4 | 25-15-083-010 | Buck Creek 1.0 mi E of IA 173 |  | Bridge Deck Overlay |  |  |  | 1173000
4
83 | 4 | 25-15-083-020 | Compton Creek 0.1 mi W of Co Rd M56 |  | Culvert New |  |  |  | 977000
| 4 |  |  |  | Right of Way |  |  |  | 5000
4
(25) Dallas | 4
6 | 4 | 25-25-006-020 | I-80 Interchange to Common Place Intersection | 3.7 | Paved Shoulders | 665000
| 4 |  |  |  | Pavement Rehab | 2332000
4
44 | 4 | 25-25-044-040 | North Raccoon River 0.7 mi W of US 169 |  | Bridge Rehabilitation |  |  |  | 13023000
4
80 | 4 | 18-25-080-020-01 | W of Grand Prairie Pkwy to E of Jordan Creek Pkwy | 7.8 | Erosion Control | 195000
4
80 | 4 | 21-25-080-020 | Co Rd R22 (Ute Ave) Interchange |  | Bridge New |  |  | 10451000
4
80 | 4 | 22-25-080-030 | W of US 6/169 to E of US 6/169 Interchange | 1 | Right of Way |  | 112000
| 4 |  |  |  | Erosion Control |  |  |  |  | 355000
| 4 |  |  |  | Mitigation |  | 695000
| 4 |  |  |  | Bridge Replacement |  | 3053000 |  | 3486000
| 4 |  |  |  | Grading |  | 10319000
| 4 |  |  |  | Traffic Signs |  | 1124000 |  | 468000
| 4 |  |  |  | Grade & Pave |  |  |  | 10784000
4
80 | 4 | 23-25-080-030 | Co Rd R16 3.1 mi E of US 169 |  | Bridge Deck Overlay |  | 813000
4
80 | 4 | 24-25-080-030 | E of Co Rd P58 to 0.5 mi E of US 169 (WB) | 3.3 | Pavement Rehab |  |  |  | 4303000
4
80 | 4 | 25-25-080-020 | Madison Co to 0.7 mi E of Co Rd P53/Co Rd F60 (WB) | 1.6 | Pavement Rehab |  |  |  | 2069000
4
80 | 4 | 25-25-080-030 | Madison Co to 1.8 mi E of Co Rd P57 (EB) | 6.6 | Pavement Rehab |  |  |  | 6163000
4
80 | 4 | 26-25-080-020 | Sugar Creek 7.9 mi E of US 169 (EB/WB) |  | Bridge Deck Overlay |  |  |  | 1908000
4
80 | 4 | 26-25-080-040 | 0.4 mi E of Co Rd R16 to 0.8 mi E of Grand Prairie Pkwy (EB) | 6 | Pavement Rehab |  |  |  |  | 2051000
4
141 | 4 | 22-25-141-020 | At the US 169 Interchange (EB/WB) |  | Bridge Deck Overlay | 2031000
4
141 | 4 | 24-25-141-010 | Frog Creek 0.1 mi W of IA 144 (EB/WB) |  | Bridge Deck Overlay |  |  | 1070000
4
141 | 4 | 26-25-141-020 | US 169 to 0.4 mi N of 150th St | 5.5 | Pavement Rehab | 7700000
4
169 | 4 | 22-25-169-020 | North Raccoon River 1.4 mi N of US 6 | 0.2 | Bridge Rehabilitation |  |  | 5091000
4
169 | 4 | 25-25-169-010 | N Raccoon River Overflow0.5 mi N of US 6 | 0.1 | Bridge Deck Overlay |  |  |  | 1303000
4
(36) Fremont | 4
2 | 4 | 16-36-002-020 | Missouri River E of Nebraska City (State Share) | 0.5 | Bridge Washing | 21390 | 21000 | 21000 | 21000 | 21000
4
2 | 4 | 21-36-002-010 | W Nishnabotna River 1.7 mi E of E Jct US 275 | 0.2 | Bridge Replacement |  | 6551000
4
2 | 4 | 22-36-002-010 | Missouri River Overflow 0.5 mi E of the Missouri River |  | Bridge Deck Overlay | 1591000
4
2 | 4 | 22-36-002-020 | W Nishnabotna River Overflow 1.1 mi E of E Jct US 275 |  | Bridge Replacement |  | 7192000
| 4 |  |  |  | Right of Way |  | 13000
| 4 |  |  |  | Mitigation |  | 175000
4
2 | 4 | 23-36-002-030 | W Nishnabotna River Overflow 1.8 mi W of Co Rd L68 |  | Bridge Replacement |  | 7484000
4
29 | 4 | 23-36-029-030 | NB Weigh Station 1.4 mi N of IA 2 |  | Paving |  |  |  | 1811000
4
29 | 4 | 24-36-029-050 | Missouri State Line to IA 2 (SB) | 10.1 | Pavement Rehab |  | 4806000
4
29 | 4 | 24-36-029-060 | 0.4 mi S of Co Rd L31 to Mills Co (NB/SB) | 4.3 | Pavement Rehab |  | 8145000
4
29 | 4 | 25-36-029-040 | Co Rd L31/Western Ave 1.7 mi N of Co Rd J24 |  | Bridge Deck Overlay |  |  |  |  | 817000
4
59 | 4 | 26-36-059-010 | Walnut Creek 2.2 mi N of Co Rd J14 |  | Bridge Deck Overlay |  |  |  |  | 897000
4
333 | 4 | 22-36-333-020 | IA 333 over I-29 |  | Bridge Deck Overlay | 1158000
4
(43) Harrison | 4
29 | 4 | 22-43-029-070 | Allen Creek 1.9 mi N of US 30 (NB/SB) |  | Bridge Rehabilitation | 1680000
4
29 | 4 | 22-43-029-080 | At the US 30 Interchange (SB) |  | Bridge Rehabilitation | 2359000
4
29 | 4 | 22-43-029-110 | Burcham Creek 2.7 mi S of IA 127 (NB/SB) |  | Bridge Replacement | 7438000
4
29 | 4 | 25-43-029-060 | Burcham Creek 1.2 mi S of IA 127 (NB/SB) |  | Bridge Deck Overlay |  |  | 997000
4
29 | 4 | 25-43-029-070 | Co Rd F20 Interchange - Ramps | 0.6 | Pavement Rehab |  |  |  | 997000
4
29 | 4 | 25-43-029-080 | 0.2 mi N of 106th Trail north 0.6 mile (NB/SB) | 0.6 | Pavement Rehab |  |  |  | 623000
4
30 | 4 | 16-43-030-020 | Missouri River E of Blair Nebraska (State Share) | 0.4 | Bridge Washing | 35243 | 35000 | 35000 | 35000 | 35000
4
30 | 4 | 18-43-030-010 | Missouri Valley Bypass | 13.8 | Right of Way | 10376000
| 4 |  |  |  | Mitigation |  | 1529000
| 4 |  |  |  | Grading |  | 32868000
| 4 |  |  |  | Culvert New |  | 858000
| 4 |  |  |  | Bridge New |  | 26852000
| 4 |  |  |  | Paving |  |  |  |  | 30382000
| 4 |  |  |  | Traffic Signs |  |  |  |  | 124000
| 4 |  |  |  | Lighting |  |  |  |  | 196000
| 4 |  |  |  | Traffic Signals |  |  |  |  | 491000
4
30 | 4 | 24-43-030-040 | Youngs Ditch 0.8 mi E of Co Rd K45 |  | Bridge Replacement |  |  | 3029000
| 4 |  |  |  | Right of Way |  |  | 10000
4
30 | 4 | 26-43-030-030 | Missouri River E of Blair Nebraska |  | Lighting |  |  |  |  | 100000
4
(61) Madison | 4
80 | 4 | 23-61-080-010 | At the Co Rd P48 Interchange |  | Bridge New |  |  |  | 3200000
4
80 | 4 | 25-61-080-020 | Co Rd P48 to Dallas Co (EB) | 2 | Pavement Rehab |  |  |  | 2431000
4
80 | 4 | 26-61-080-010 | Co Rd P48 to Dallas Co (WB) | 2 | Pavement Rehab |  |  |  |  | 2117000
4
92 | 4 | 22-61-092-010 | Middle River 2.0 mi W of Co Rd P53 |  | Bridge Rehabilitation | 992000
4
(65) Mills | 4
29 | 4 | 26-65-029-030 | US 34 to 1.9 mi N of Co Rd H10 (SB) |  | Pavement Rehab | 8000000
4
29 | 4 | 26-65-029-040 | Rist Ave 1.7 mi N of Co Rd L31 |  | Grading | 300000
| 4 |  |  |  | Bridge Removal | 2000000
4
29 | 4 | 26-65-029-050 | 0.6 mi N of the Rest Area to Pottawattamie Co (NB/SB) | 5 | Pavement Rehab |  |  |  |  | 10889000
4
34 | 4 | 12-65-034-020 | Missouri River N of Plattsmouth Nebraska (State Share) | 0.5 | Bridge Washing | 25000 | 25000 | 25000 | 25000 | 25000
4
34 | 4 | 24-65-034-020 | BNSF RR 0.5 mi E of I-29 (EB/WB) |  | Bridge Deck Overlay |  |  | 3900000
4
34 | 4 | 24-65-034-030 | At Co Rd L35 Interchange (NB/SB) |  | Bridge Deck Overlay |  |  | 1950000
4
34 | 4 | 25-65-034-030 | Missouri River N of Plattsmouth Nebraska |  | Lighting |  |  |  | 130000
4
34 | 4 | 25-65-034-040 | E of BNSF RR to 0.1 mi E of US 275 | 8.1 | Pavement Rehab | 10274000
4
59 | 4 | 23-65-059-010 | At the Jct US 34 |  | Bridge Replacement |  | 8044000
| 4 |  |  |  | Right of Way |  | 161000
4
59 | 4 | 24-65-059-010 | Stream 1.1 mi S of Co Rd H12 (Side Ditch) |  | Grading |  |  | 211000
4
(69) Montgomery | 4
34 | 4 | 22-69-034-020 | Crabapple Creek 3.1 mi E of US 59 |  | Bridge Deck Overlay | 497000
4
34 | 4 | 24-69-034-020 | Indian Creek 1.2 mi E of US 59 |  | Bridge Deck Overlay |  |  | 455000
4
48 | 4 | 22-69-048-010 | East Nishnabotna River 1.7 mi N of US 34 | 0.1 | Bridge Deck Overlay | 1386000
4
48 | 4 | 23-69-048-020 | Nishnabotna River Overflow 2.0 mi S of Co Rd H14 |  | Bridge Deck Overlay | 1112000
4
71 | 4 | 24-69-071-020 | Fultons Creek 3.4 mi N of US 34 |  | Bridge Deck Overlay |  |  | 455000
4
71 | 4 | 24-69-071-030 | At US 34 Interchange | 0.1 | Bridge Deck Overlay |  |  | 975000
4
(73) Page | 4
2 | 4 | 26-73-002-020 | East Nodaway River 0.3 mi W of Co Rd N14 |  | Bridge Deck Overlay |  |  |  |  | 1495000
4
48 | 4 | 24-73-048-010 | Rocky Branch 1.2 mi S of Co Rd M41 |  | Bridge Deck Overlay |  |  | 520000
4
59 | 4 | 24-73-059-010 | Stream 1.5 mi N of IA 48 |  | Bridge New |  |  |  |  | 2300000
| 4 |  |  |  | Right of Way |  |  |  |  | 8000
4
59 | 4 | 26-73-059-020 | Co Rd J18 to Mills Co Line | 2.4 | Pavement Rehab | 712000
4
59 | 4 | 25-73-059-010 | IA 2 Intersection | 0.2 | Grade & Pave | 2600000
| 4 |  |  |  | Traffic Signs | 50000
| 4 |  |  |  | Lighting | 160000
| 4 |  |  |  | Right of Way | 10000
4
71 | 4 | 25-73-071-020 | West Nodaway River 0.3 mi S of N Jct IA 2 |  | Bridge Deck Overlay |  |  |  | 2605000
4
(78) Pottawattamie | 4
6 | 4 | 24-78-006-030 | Silver Creek 1.0 mi E of Co Rd L66 |  | Bridge Replacement |  |  | 4478000
| 4 |  |  |  | Right of Way |  |  | 11000
4
29 | 4 | 21-78-029-010 | Co Rd L19 Interchange |  | Bridge Replacement |  | 4745000
4
29 | 4 | 22-78-029-020 | At the N 16th St Interchange in Council Bluffs (NB) |  | Bridge Replacement |  | 8455000
4
29 | 4 | 23-78-029-030 | At the I-880 Interchange (NB/SB) |  | Bridge Rehabilitation |  | 3983000
4
29 | 4 | 24-78-029-030 | S of IA 192 to 0.74 mi N of 235th St – Various Locations | 30.7 | Pavement Rehab |  | 2587000
4
29 | 4 | 24-78-029-040 | 0.6 mi N of NCL Council Bluffs to 1.1 mi S of I-680 (SB) | 3.1 | Pavement Rehab |  |  |  | 3322000
4
29 | 4 | 25-78-029-040 | I-680 to I-880 - Various Locations | 9 | Grading | 2648000
4
59 | 4 | 21-78-059-020 | Stream 1.5 mi S of Co Rd G30 |  | Bridge Replacement | 2181000
4
59 | 4 | 21-78-059-030 | Stream 0.9 mi S of Co Rd G30 |  | Bridge Replacement | 1826000
4
59 | 4 | 24-78-059-010 | In Avoca, Pershing St to S of Co Rd F66 | 1.5 | Grade & Pave | 13422000
4
59 | 4 | 24-78-059-020 | In Avoca, Lyon St to Pershing St | 0.8 | Grade & Pave |  | 3930000
4
59 | 4 | 24-78-059-040 | Stream 0.6 mi N of S Jct Co Rd G30 |  | Bridge Replacement |  |  | 2711000
| 4 |  |  |  | Right of Way |  |  | 10000
4
80 | 4 | 16-78-080-020 | Missouri River in Council Bluffs (State Share) | 1.1 | Bridge Washing | 42000 | 42000 | 42000 | 42000 | 42000
4
80 | 4 | 20-78-080-020 | US 6 to 2.2 mi E of US 6 | 2.3 | Pavement Rehab |  | 2481000
4
80 | 4 | 20-78-080-080 | 0.4 mi E of I-880 to 0.1 mi W of Silver Creek Bridge (WB) |  | Pavement Rehab |  | 1857000
4
80 | 4 | 22-78-080-040 | Drainage Ditch 0.3 mi W of Co Rd M16 | 0.1 | Right of Way | 5000
| 4 |  |  |  | Culvert Extension | 606000
4
80 | 4 | 22-78-080-050 | Stream 1.6 mi E of Co Rd M47 |  | Right of Way | 5000
| 4 |  |  |  | Culvert Extension | 1296000
4
80 | 4 | 24-78-080-060 | W Nishnabotna River to 0.7 mi E of Rest Area (EB) | 5.8 | Pavement Rehab |  | 4569000
4
80 | 4 | 25-78-080-050 | Missouri River in Council Bluffs (EB/WB) |  | Bridge Rehabilitation |  |  |  | 166000
4
80 | 4 | 25-78-080-080 | Co Rd L66 Interchange |  | Right of Way |  |  |  | 5000
| 4 |  |  |  | Bridge New |  |  |  | 12698000
4
80 | 4 | 25-78-080-100 | 0.45 mi SW of Co Rd G30 to 0.5 mi SW of 290th St (EB/WB) | 4.7 | Pavement Rehab | 7780000
4
80 | 4 | 94-78-080-370 | WB Underwood Rest Area 1.0 Mi N of Co Rd G30 | 1.7 | Rest Area Improvement |  |  |  |  | 6000000
4
80 | 4 | 26-78-080-040 | WB Underwood Rest Area 1.0 Mi N of Co Rd G30 | 0.5 | Right of Way |  |  |  |  | 205000
4
80 | 4 | 26-78-080-050 | Franklin Ave 2.3 mi W of US 6 (EB/WB) |  | Bridge Deck Overlay |  |  |  | 1908000
4
80 | 4 | 26-78-080-060 | '0.5 mi SW of 290th St to E of I-880 (EB) | 6.3 | Pavement Rehab |  |  |  |  | 7929000
4
80 | 4 | 26-78-080-070 | 0.7 mi E of Weigh Scale to Cass Co (WB) | 4.6 | Pavement Rehab |  |  |  |  | 1562000
4
83 | 4 | 26-78-083-010 | West Nishnabotna River 0.4 mi E of US 59 |  | Bridge Deck Overlay |  |  |  |  | 1495000
4
92 | 4 | 24-78-092-010 | Farm Creek 6.3 mi E of US 59 |  | Bridge New |  |  |  |  | 4500000
| 4 |  |  |  | Right of Way |  |  |  |  | 8000
4
275 | 4 | 12-78-275-010 | Missouri River in Council Bluffs (State Share) | 0.2 | Bridge Washing | 56633 | 57000 | 57000 | 57000 | 57000
4
275 | 4 | 26-78-275-020 | In Council Bluffs over the Missouri River |  | Bridge Rehabilitation | 300000
4
275 | 4 | 26-78-275-030 | BNSF RR and DL #5 0.4 mi N of N Jct I-29 (WB) |  | Bridge Deck Overlay |  |  |  |  | 1495000
4
480 | 4 | 16-78-480-010 | Missouri River in Council Bluffs (State Share) | 0.4 | Bridge Washing | 30317 | 30000 | 30000 | 30000 | 30000
4
680 | 4 | 16-78-680-010 | Missouri River in Council Bluffs (State Share) | 0.3 | Bridge Washing | 48170 | 48000 | 48000 | 48000 | 48000
4
680 | 4 | 24-78-680-010 | Missouri River 3.1 mi W of I-29 (EB/WB) |  | Bridge Rehabilitation |  |  | 1000000
4
680 | 4 | 25-78-680-030 | Missouri River Bridge to I-29 | 3 | Pavement Rehab |  |  | 1235000
4
880 | 4 | 21-78-880-010 | Co Rd L34 Interchange |  | Mitigation |  |  |  | 50000
| 4 |  |  |  | Bridge New |  |  |  | 9523000
4
880 | 4 | 23-78-880-040 | At the IA 191 Interchange (WB) |  | Bridge Deck Overlay |  |  | 1388000
4
880 | 4 | 25-78-880-030 | Pigeon Creek 4.2 mi W of IA 191 (EB/WB) |  | Bridge Deck Overlay |  |  | 1247000
4
(80) Ringgold | 4
2 | 4 | 24-80-002-010 | Walnut Creek 0.9 mi W of W Jct US 169 |  | Bridge Deck Overlay |  |  | 650000
4
2 | 4 | 26-80-002-010 | East Fork Grand River 2.9 mi E of E Jct US 169 |  | Bridge Deck Overlay |  |  |  |  | 997000
4
2 | 4 | 26-80-002-020 | Lotts Creek 4.9 mi E of E Jct US 169 |  | Bridge Deck Overlay |  |  |  |  | 623000
4
2 | 4 | 26-80-002-030 | E Fork Lotts Creek 0.4 mi E of Co Rd P64 |  | Bridge Deck Overlay |  |  |  |  | 717000
4
25 | 4 | 24-80-025-010 | Stream 2.3 mi N of N Jct Co Rd J23 |  | Culvert Replacement |  |  | 1106000
| 4 |  |  |  | Right of Way |  |  | 10000
| 4 |  |  |  | Mitigation |  |  | 55000
4
169 | 4 | 25-80-169-010 | Middle Fork Grand River 1.0 mi N of Co Rd P32 |  | Bridge Deck Overlay |  |  |  | 1173000
4
169 | 4 | 22-80-169-010 | Missouri State Line to IA 2 | 15.1 | Pavement Rehab | 10268000
4
(83) Shelby | 4
44 | 4 | 24-83-044-010 | West Nishnabotna River 5.8 mi E of US 59 |  | Bridge Deck Overlay |  |  | 910000
4
44 | 4 | 25-83-044-010 | West Nishnabotna River 1.3 mi E of US 59 |  | Bridge Deck Overlay |  |  |  | 2345000
4
59 | 4 | 22-83-059-010 | Drainage Ditch 2.6 mi N of I-80 |  | Bridge Deck Overlay | 848000
4
(00) Statewide | 4
0 | 4 | 26-00-000-160 | Various Bridges in Districts 3 and 4 |  | Bridge Rehabilitation | 630000
4
0 | 4 | 26-00-000-120 | Various Counties and Routes in District 4 |  | Pavement Markings | 500000
4
(87) Taylor | 4
2 | 4 | 22-87-002-010 | East 102 River just E of Co Rd N44 |  | Bridge Deck Overlay | 1041000
4
2 | 4 | 25-87-002-010 | West 102 River 1.7 mi E of Co Rd N26 |  | Bridge Deck Overlay |  |  |  | 1693000
4
148 | 4 | 24-87-148-010 | W Fork 102 River 0.1 mi N of Co Rd J20 |  | Bridge Rehabilitation |  |  | 975000
4
(88) Union | 4
25 | 4 | 23-88-025-010 | Branch Platte River 3.4 mi S of US 34 |  | Bridge Deck Overlay | 865000
4
34 | 4 | 22-88-034-020 | Twelve Mile Creek 3.2 mi W of W Jct US 169 |  | Bridge Deck Overlay | 1098000
4
34 | 4 | 23-88-034-040 | Abandoned RR 1.7 mi W of E Jct US 169 |  | Grading |  | 1712000
4
34 | 4 | 23-88-034-050 | Grand River 1.2 mi W of E Jct US 169 |  | Bridge Deck Overlay |  | 1079000
4
34 | 4 | 23-88-034-060 | BNSF RR 3.3 mi E of E Jct IA 25 |  | Bridge Deck Overlay |  | 1301000
4
169 | 4 | 24-88-169-010 | Twelve Mile Creek 1.6 mi S of US 34 |  | Bridge Deck Overlay |  |  | 715000

## Sheet2
2027 - 2031 Five Year Program
This information is valid for the date of Commission approval of None
Line Items
Project Estimated Costs X $1000
| County | Location | Type Of Work | 2027 | 2028 | 2029 | 2030 | 2031
| Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 108672000 | 193330000 | 198399000 | 209400000
| Statewide | Statewide Safety Specific | Paving | 0 | 36000000 | 37000000 | 38000000 | 38000000
| Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 5000000 | 15000000 | 15000000 | 15000000
| Statewide | American with Disabilities Act | Pedestrian Improvement | 5500000 | 5500000 | 5500000 | 5500000 | 5500000
| Statewide | Construction Training Program | Training | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
| Statewide | Cooperative City/County/State Highway Research | Research | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Emergency & Contingency (U-STEP/C-STEP) | Construction | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
| Statewide | Pavement Markings | Paint | 12700000 | 12700000 | 12700000 | 12700000 | 12700000
| Statewide | Post Letting Project Cost | Construction | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
| Statewide | Prevocational Training and DBE Support Services | Training | 360000 | 360000 | 360000 | 360000 | 360000
| Statewide | Scenic Byway Program | Signs | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Consultant Services | Outside Services Engineering | 75000000 | 75000000 | 75000000 | 75000000 | 75000000
| Statewide | Statewide Contract Maintenance | Construction | 53300000 | 58000000 | 58500000 | 59000000 | 59500000
| Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide ITS | Equipment | 8000000 | 8000000 | 8000000 | 8000000 | 8000000
| Statewide | Statewide Lighting | Lighting | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide Operations | Outside Services Engineering | 16000000 | 16000000 | 16000000 | 16000000 | 16000000
| Statewide | Statewide Railroad Crossings | Construction | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 10600000 | 10700000 | 10800000 | 10900000 | 11000000
| Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Statewide Traffic Control Devices | Signs | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
| Statewide | Summer Infrastructure Rehabilitation Materials | Materials | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
| Statewide | Winter Operations Materials | Materials | 12000000 | 12000000 | 12000000 | 12000000 | 12000000