## Sheet1
2027 - 2031 IOWA HIGHWAY PROGRAM
S.F 257 Only: No |  |  |  |  | Project Estimated Costs X $1000
Route | Project Code | Location | Miles | Type of Work | 2027 | 2028 | 2029 | 2030 | 2031
(06) Benton
151 | 26-06-151-010 | Co Rd E66 to Fairfax | 5.2 | Grade & Pave | 1225000
|  |  |  | Grade & Pave | 7600000
218 | 18-06-218-030 | Abandoned RR 2.6 mi N of N Jct US 30 (Remove Bridge) | 0.1 | Grade & Pave |  |  | 3500000
|  |  |  | Right of Way |  | 6000
(10) Buchanan
20 | 24-10-020-020 | Buffalo Creek 2.3 mi E of Co Rd W40 (EB/WB) |  | Bridge Deck Overlay |  |  | 1950000
20 | 24-10-020-030 | Co Rd W35 2.5 mi E of IA 150 |  | Bridge Deck Overlay |  |  | 630000
150 | 22-10-150-010 | Wapsipinicon River in Independence | 0.1 | Bridge Deck Overlay | 1285000
150 | 24-10-150-010 | Branch Bear Creek 3.5 mi N of Co Rd D48 |  | Bridge Deck Overlay |  |  | 260000
187 | 24-10-187-010 | 220th St to IA 3 | 15 | Grading |  | 2374000
|  |  |  | Right of Way |  | 10000
(16) Cedar
30 | 21-16-030-020 | W of Charles Ave E of Lisbon to WCL Stanwood | 11 | Railroad Signals | 4000000
|  |  |  | Pavement Widening | 1384000
30 | 24-16-030-020 | Rock Creek 0.6 mi W of W Jct IA 38 |  | Bridge Deck Overlay |  |  |  | 658000
38 | 26-16-038-020 | Crooked Creek 0.4 mi N of N Jct I-80 |  | Bridge Deck Overlay |  |  |  |  | 586000
80 | 22-16-080-050 | Wilton Truck Parking Only Site 1.4 mi E of W Jct IA 38 (WB) | 0.6 | Right of Way |  |  | 81000
|  |  |  | Grade & Pave |  |  |  | 6613000
|  |  |  | Traffic Signs |  |  |  | 65000
|  |  |  | Lighting |  |  |  | 188000
80 | 25-16-080-020 | Cedar River to Sugar Creek (EB/WB) | 3.1 | Pavement Rehab |  |  |  | 1246000
80 | 25-16-080-030 | E of Co Rd X30 east approx 2.5 mi (WB) | 2.5 | Pavement Rehab |  |  |  | 498000
80 | 25-16-080-040 | Sugar Creek to Scott County (EB/WB) | 8 | Pavement Rehab |  |  |  | 3240000
80 | 26-16-080-020 | West Branch to Davenport | 43.4 | Traffic Signs | 2930000
(23) Clinton
30 | 16-23-030-010 | Mississippi River in Clinton (State Share) | 4.2 | Bridge Washing | 25317 | 25000 | 25000 | 25000 | 25000
30 | 19-23-030-020 | UP RR 0.6 mi E of Co Rd Y4E | 1.4 | Bridge Replacement |  | 7405000
|  |  |  | Grading | 5895000
|  |  |  | Paving |  | 5452000
30 | 21-23-030-030 | Unnamed Stream 1.0 mi E of Co Rd Y4E | 0.1 | Bridge Replacement |  | 2130000
30 | 22-23-030-010 | Brophy's Creek 8.5 mi E of E Jct US 61 (EB) |  | Bridge Deck Overlay | 509000
30 | 19-23-030-020-90 | Mitigation - UP RR Bridge Project |  | Mitigation | 297000
30 | 25-23-030-030 | At E Jct US 61 |  | Bridge Deck Overlay |  |  |  | 1954000
30 | 18-23-030-030 | Wapsipinicon River 1.5 mi E of Co Rd Y4E | 1.5 | Fencing | 525000
67 | 24-23-067-020 | Shadducks Creek 5.7 mi N of N Jct IA 136 |  | Bridge Deck Overlay |  |  | 689000
67 | 25-23-067-010 | UP RR 0.5 mi S of US 30 |  | Bridge Deck Overlay |  |  |  | 3256000
136 | 16-23-136-010 | Mississippi River in Clinton (State Share) | 0.3 | Bridge Washing | 40000 | 39707 | 40000 | 40000 | 40000
136 | 24-23-136-040 | Mill Creek 2.7 mi N of N Jct US 67 |  | Bridge Deck Overlay |  |  | 884000
136 | 26-23-136-030 | Mississippi River in Clinton |  | Bridge Rehabilitation |  |  |  |  | 250000
136 | 26-23-136-010 | W of Charlotte to W of Delmar | 8.3 | Paved Shoulders | 1254000
|  |  |  | Paving | 4700000
(28) Delaware
3 | 25-28-003-010 | E Jct IA 3 to Dubuque Co Line - Various Locations | 19.8 | Grading |  |  |  | 539000
|  |  |  | Right of Way |  |  |  | 10000
13 | 22-28-013-010 | CC RR 1.0 mi N of US 20 |  | Bridge Rehabilitation | 1841000
13 | 24-28-013-010 | At US 20 Interchange |  | Bridge Deck Overlay |  |  | 975000
20 | 22-28-020-010 | Abandoned RR 0.4 mi W of IA 38 (EB) |  | Bridge Deck Overlay | 937000
20 | 26-28-020-020 | Maquoketa River 1.7 mi E of IA 13 (EB/WB) |  | Bridge Deck Overlay |  |  |  |  | 5234000
38 | 23-28-038-010 | Plum Creek 3.5 mi N of Co Rd D22 |  | Bridge Replacement |  | 940000
|  |  |  | Right of Way |  | 10000
38 | 25-28-038-010 | Sand Creek 0.2 mi N of Co Rd D47 |  | Bridge Deck Overlay |  |  |  | 847000
(31) Dubuque
3 | 22-31-003-020 | N Fork Little Maquoketa River 0.1 mi E of Boy Scout Rd |  | Bridge Deck Overlay | 740000
3 | 23-31-003-010 | N Fork Maquoketa River 1.5 mi E of US 52 |  | Bridge Deck Overlay |  | 477000
3 | 10-31-052-020-90 | Mitigation for Section 1 | 5.4 | Mitigation | 150000
20 | 16-31-020-020 | Mississippi River in Dubuque (State Share) | 6.3 | Bridge Washing | 70000 | 70000 | 70000 | 70000 | 70000
20 | 21-31-020-020 | N Fork Maquoketa River 0.6 mi W of IA 136 (WB) | 0.2 | Bridge Replacement |  | 5705000
|  |  |  | Right of Way |  | 6000
20 | 26-31-020-040 | N Branch Catfish Creek 1.7 mi E of IA 32 |  | Culvert Repair |  |  |  |  | 374000
20 | 21-31-020-010 | NW Arterial Intersection In Dubuque, from Old Highway Rd to Crescent Ridge | 1 | Right of Way | 500000
|  |  |  | Grade & Pave |  | 12000000
52 | 10-31-052-020-01 | 0.7 mi N of Boy Scout Rd to S of Co Rd C9Y in Sageville | 5.5 | Erosion Control | 436000
61 | 16-31-061-010 | Mississippi River in Dubuque (State Share) | 1.6 | Bridge Washing |  | 19853 | 20000 | 20000 | 20000
61 | 18-31-061-010 | Peosta Channel 0.2 mi N of E 11th St in Dubuque | 1 | Bridge Washing | 60000 | 60000 | 60000 | 60000 | 60000
61 | 21-31-061-020 | Mississippi River in Dubuque | 0.3 | Bridge Rehabilitation | 5592000
61 | 23-31-061-010 | Over 4th, 5th, and White St 0.6 mi N of US 20 in Dubuque |  | Bridge Deck Overlay | 3803000
151 | 26-31-151-010 | At US 61 Interchange |  | Bridge Deck Overlay |  |  |  |  | 2119000
(48) Iowa
6 | 24-48-006-010 | IAIS RR 1.6 mi E of E Jct IA 21 |  | Bridge New |  |  |  | 10687000
|  |  |  | Right of Way |  |  |  | 10000
6 | 24-48-006-020 | Approx 1.9 mi E of IA 220/Co Rd W16 |  | Culvert Replacement | 406000
|  |  |  | Right of Way | 10000
21 | 23-48-021-030 | 0.3 mi N of IA 212 to 3rd St in Belle Plaine | 1.9 | Grade & Pave |  | 6419000
|  |  |  | Bridge New |  | 5732000
|  |  |  | Culvert Replacement |  | 206000
|  |  |  | Right of Way |  | 57000
|  |  |  | Mitigation |  | 78000
80 | 22-48-080-060 | W of IA 149 to E of IA 149 | 1 | Right of Way | 218000
|  |  |  | Erosion Control |  |  |  | 330000
|  |  |  | Mitigation | 135000
|  |  |  | Bridge Replacement | 3627000 |  | 3961000
|  |  |  | Grade & Pave | 13292000 |  | 9199000
|  |  |  | Traffic Signs | 464000 |  | 239000
|  |  |  | Lighting | 205000 |  | 215000
80 | 22-48-080-070 | Victor Rest Area 2.5 mi E of Co Rd V38 (WB) | 0.7 | Grade & Pave | 6469000
|  |  |  | Traffic Signs | 157000
|  |  |  | Lighting | 226000
80 | 24-48-080-030 | 1.8 mi W of Co Rd V66 to 1.5 mi E of IA 149 (WB) | 6.2 | Pavement Rehab |  |  |  | 11201000
80 | 24-48-080-040 | 1.5 mi E of IA 149 to 1 mi E of US 151 (EB/WB) | 4.6 | Pavement Rehab |  | 1781000
80 | 24-48-080-050 | 1 mi E of US 151 to E of S Roberts Ferry Rd at Tiffin (WB) | 12.1 | Pavement Rehab |  | 9029000
80 | 25-48-080-040 | 1 mi E of US 151 to W of Tiffin Interchange (EB) | 11.4 | Pavement Rehab |  |  |  | 5764000
149 | 25-48-149-020 | Co Rd V66 to SCL of Williamsburg | 5 | Paved Shoulders | 725000
|  |  |  | Pavement Rehab | 1800000
151 | 21-48-151-010 | Iowa River 1.0 mi N of N Jct US 6 | 0.2 | Bridge Deck Overlay | 1489000
151 | 21-48-151-020 | Iowa River Overflow 1.6 mi S of IA 220 | 0.3 | Bridge Deck Overlay | 2725000
220 | 24-48-220-010 | Overflow Iowa River 2.0 mi N of US 6 | 0.1 | Bridge Deck Overlay |  |  |  | 340000
220 | 25-48-220-020 | Mill Race 2.1 mi E of US 6 |  | Bridge Deck Overlay |  |  |  | 977000
(49) Jackson
52 | 16-49-052-020 | Mississippi River in Sabula (State Share) | 0.5 | Bridge Washing | 25317 | 25000 | 25000 | 25000 | 25000
52 | 24-49-052-030 | Pleasant Creek 0.3 mi N of Co Rd Z34 |  | Bridge Deck Overlay |  |  | 650000
61 | 24-49-061-020 | N Fork Maquoketa River 5.4 mi N of IA 64 (NB) |  | Bridge Deck Overlay |  |  | 1300000
61 | 25-49-061-010 | Prairie Creek 2.0 mi of IA 64 (NB) |  | Bridge Deck Overlay |  |  |  | 847000
62 | 22-49-062-010 | Brush Creek 2.0 mi N of Co Rd Y61 |  | Bridge Rehabilitation | 1105000
62 | 26-49-062-010 | Andrew to Bellevue | 10.7 | Paved Shoulders | 1095000
|  |  |  | Pavement Rehab | 4625000
64 | 26-49-064-010 | Bear Creek 0.9 mi E of Co Rd Y34 |  | Bridge Deck Overlay |  |  |  |  | 548000
(52) Johnson
1 | 19-52-001-010 | E Burlington St to N Governor St (SB) (State Share) |  | Grade & Pave | 5665000
1 | 26-52-001-040 | Mill Creek 0.1 mi N of Solon |  | Bridge Deck Overlay |  |  |  |  | 461000
1 | 26-52-001-050 | Iowa River in Iowa City (SB) |  | Bridge New |  |  |  | 6900000
6 | 21-52-006-010 | Iowa River 0.2 mi E of E Jct IA 1 in Iowa City | 0.2 | Bridge Replacement |  |  | 12227000
|  |  |  | Right of Way |  |  | 23000
6 | 24-52-006-030 | Co Rd F46 to WCL West Liberty | 2.2 | Grade & Pave |  |  |  |  | 7622000
6 | 24-52-006-040 | In Tiffin, Roberts Ferry Rd to Park Rd | 0.8 | Culvert Replacement | 600000
|  |  |  | Grade & Pave | 3140000
|  |  |  | Right of Way | 218000
6 | 23-52-006-010 | Pedestrian Bridge S of Newton Rd/Iowa Ave in Iowa City |  | Bridge Rehabilitation | 770000
80 | 16-52-080-020 | 1.5 mi E of IA 1 to 0.9 mi E of Co Rd X30 | 21.8 | Erosion Control | 477007
80 | 23-52-080-010 | US 6 and IAIS RR 0.6 mi W of Co Rd W60 (WB) |  | Bridge Deck Overlay |  | 3297000
218 | 26-52-218-010 | 1 mi S of Riverside Dr to S of I-80 (NB/SB) | 6.6 | Pavement Rehab | 9350000
380 | 16-52-380-030-01 | N of Forevergreen Rd to N of Swan Lake Rd | 3.3 | Erosion Control | 200000
|  |  |  | Landscaping | 119000
380 | 16-52-380-030-02 | N of Swan Lake Rd to N of Co Rd F12/120th St | 12.1 | Miscellaneous | 1144000 | 1254000 | 1374000 | 5682000 | 1647000
|  |  |  | Traffic Signs |  | 799000 | 100000 | 118000 | 243000
|  |  |  | Lighting |  |  | 400000
|  |  |  | Right of Way |  |  |  | 6624000
|  |  |  | Mitigation |  |  |  | 563000
|  |  |  | Grade & Pave |  |  |  |  | 23777000
|  |  |  | Culvert Extension |  |  |  | 1344000
|  |  |  | Bridge Replacement |  |  |  |  | 11114000
(53) Jones
38 | 22-53-038-020 | Big Bear Creek 0.8 mi N of S Jct IS 64 |  | Bridge Deck Overlay | 718000
38 | 22-53-038-030 | Sibles Creek 0.3 mi S of Co Rd E53 |  | Culvert Replacement | 1675000
|  |  |  | Right of Way | 12000
|  |  |  | Mitigation | 100000
38 | 24-53-038-010 | Kitty Creek 0.5 mi N of US 151 in Monticello |  | Bridge Deck Overlay |  |  | 910000
38 | 25-53-038-040 | Maquoketa River 1.5 mi N of Co Rd D62 |  | Bridge Deck Overlay |  |  |  | 3256000
64 | 26-53-064-010 | Little Bear Creek 0.2 mi E of W Jct IA 136 |  | Bridge Deck Overlay |  |  |  |  | 698000
136 | 20-53-136-020 | Maquoketa River 2.5 mi N of Co Rd E17 | 0.2 | Bridge Rehabilitation | 2368000
136 | 22-53-136-010 | Mineral Creek 2.1 mi N of N Jct Co Rd E29 |  | Bridge Replacement | 2647000
|  |  |  | Right of Way | 10000
136 | 24-53-136-010 | Farm Creek 5.4 mi S of US 151 |  | Bridge Deck Overlay |  |  | 520000
151 | 22-53-151-020 | Wapsipinicon River 1.4 mi S of IA 64 (SB) |  | Bridge Replacement |  | 7712000
151 | 24-53-151-010 | Kitty Creek 0.4 mi N of Co Rd X44 (NB) |  | Bridge Deck Overlay |  |  | 975000
(54) Keokuk
149 | 23-54-149-010 | S Fork English River 1.3 mi N of IA 22 | 0.1 | Bridge Deck Overlay | 1185000
(57) Linn
1 | 24-57-001-010 | In Mt Vernon, from SCL to NCL | 1.3 | Grade & Pave | 3472000
13 | 25-57-013-010 | East Indian Creek 2.1 mi N of Co Rd E34 (NB) |  | Bridge Deck Overlay |  |  |  | 326000
13 | 26-57-013-020 | Buffalo Creek 0.1 mi N of S Jct Co Rd D62 |  | Bridge Deck Overlay |  |  |  |  | 1097000
30 | 24-57-030-030 | EB US 30 Ramp to IA 100 |  | Bridge Deck Overlay |  |  | 689000
30 | 24-57-030-040 | Edgewood Rd SW Interchange in Cedar Rapids |  | Bridge Deck Overlay |  |  | 1950000
100 | 26-57-100-030 | IA 922 to IA 151 | 4.1 | Paved Shoulders | 900000
151 | 08-57-151-010 | Co Rd X20 Intersection in Springville | 3.8 | Right of Way |  | 9472000
|  |  |  | Erosion Control |  |  | 365000
|  |  |  | Grade & Pave |  | 10475000
|  |  |  | Traffic Signs |  | 285000
|  |  |  | Bridge New |  | 6533000
|  |  |  | Lighting |  | 205000
151 | 22-57-151-010 | At the N US 30 Interchange (SB) |  | Bridge Deck Overlay | 1418000
151 | 26-57-151-010 | IA 13 to US 61 | 56.9 | Patching | 500000
380 | 25-57-380-070 | Northbound Rest Area approx 1.4 mi N of Co Rd F12 | 0.6 | Paving |  |  |  | 1869000
380 | 26-57-380-060 | J Ave to 1.4 mi N of Co Rd E34/County Home Rd (NB/SB) | 8.4 | Pavement Rehab |  |  |  |  | 11720000
922 | 23-57-922-010 | In Cedar Rapids, from 10 St NE to E of 17th St NE | 0.8 | Pavement Rehab | 900000
(82) Scott
22 | 24-82-022-020 | Moore Creek 3.4 mi W of I-280 in Buffalo |  | Bridge Deck Overlay |  |  | 650000
61 | 22-82-061-020 | 210th St 1.1 mi N of I-80 (NB/SB) | 0.1 | Bridge Deck Overlay | 3479000
61 | 22-82-061-030 | Co Rd F41 / 267th St Interchange (SB) |  | Bridge Deck Overlay | 986000
61 | 23-82-061-020 | DME RR 0.8 mi N of I-80 (NB/SB) |  | Bridge Rehabilitation | 6335000
|  |  |  | Grade & Pave | 1000000
61 | 26-82-061-010 | S of I-80 to N of 210th St | 1.4 | Pavement Rehab | 1800000
61 | 26-82-061-040 | At Co Rd F41 Interchange (NB) |  | Bridge Deck Overlay |  |  |  |  | 1745000
67 | 16-82-067-020 | Mississippi River in Davenport (State Share) | 1 | Bridge Washing | 35317 | 35000 | 35000 | 35000 | 35000
67 | 22-82-067-010 | Crow Creek 5.2 mi S of I-80 in Bettendorf |  | Bridge Deck Overlay | 1092000
67 | 24-82-067-030 | Approx 1.5 mi S of I-80 to N of 218th St | 5 | Slope Improvement |  | 1500000
|  |  |  | Right of Way |  | 50000
67 | 26-82-067-070 | Arsenal Island Rd 1.3 mi N of Rte Termini |  | Bridge Rehabilitation |  |  |  |  | 374000
67 | 26-82-067-080 | Wapsipinicon River 1.6 mi S of Co Rd Z36 |  | Bridge Deck Overlay |  |  |  |  | 3614000
67 | 24-82-067-020 | Mississippi River in Davenport (Centennial Bridge) | 0.3 | Bridge New |  |  |  |  | 60000000
74 | 16-82-074-010 | Mississippi River in Bettendorf (State Share) | 0.7 | Bridge Washing | 75000 | 75000 | 75000 | 75000 | 75000
74 | 23-82-074-040 | At the US 6 Interchange 2.6 mi E of I-80 (EB/WB) |  | Bridge Rehabilitation |  | 3453000
74 | 03-82-074-010-08 | Mississippi River Bridge |  | Mitigation |  | 285000
80 | 16-82-080-010 | Mississippi River in Le Claire (State Share) | 0.7 | Bridge Washing | 100266 | 100000 | 100000 | 100000 | 100000
80 | 19-82-080-030 | Mississippi River in Le Claire (State Share) | 4.2 | Bridge Replacement |  | 80000000 | 81000000 | 80000000
|  |  |  | Mitigation |  | 244000
80 | 21-82-080-030 | IMRL RR 0.4 mi E of US 61 | 0.1 | Bridge Rehabilitation | 5342000
80 | 22-82-080-020 | 1 mi W of Middle Rd to 1 mi E of Middle Rd in Bettendorf | 2 | Erosion Control |  | 273000
80 | 24-82-080-030 | 0.6 mi E of Co Rd Y30 to 1.1 mi W of Co Rd Y40 (EB/WB) | 2.4 | Pavement Rehab |  | 4395000
80 | 25-82-080-050 | At IA 130 Interchange - Eastbound Entrance Ramp |  | Right of Way |  |  |  | 10000
|  |  |  | Grade & Pave |  |  |  | 2295000
80 | 25-82-080-060 | Co Rd Z30 to Mississippi River Bridge (EB/WB) | 3.9 | Pavement Rehab |  |  |  | 3863000
80 | 25-82-080-070 | Cedar County to E of Co Rd Y30 (EB/WB) | 2.7 | Pavement Rehab |  |  |  | 1122000
280 | 16-82-280-010 | Mississippi River in Davenport (State Share) | 0.6 | Bridge Washing | 40000 | 40000 | 40000 | 40000 | 40000
280 | 23-82-280-030 | At the IA 22 Interchange (EB/WB) |  | Bridge Deck Overlay | 1585000
280 | 25-82-280-030 | US 61 Interchange - Ramps | 0.4 | Paving |  |  |  | 3365000
461 | 26-82-461-010 | In Davenport, from Locust St to Central Park Ave (SB) | 0.5 | Pavement Rehab | 600000
461 | 26-82-461-020 | In Davenport, from Lombard St to 59th St (NB) | 1.3 | Pavement Rehab | 3400000
(00) Statewide
0 | 26-00-000-150 | Various Bridges in Districts 1, 2, and 6 |  | Bridge Rehabilitation | 450000
0 | 26-00-000-080 | Various Counties and Routes in District 6 |  | Pavement Rehab | 400000
0 | 26-00-000-140 | Various Counties and Routes in District 6 |  | Pavement Markings | 500000

## Sheet2
2027 - 2031 Five Year Program
This information is valid for the date of Commission approval of None
Line Items
Project Estimated Costs X $1000
| County | Location | Type Of Work | 2027 | 2028 | 2029 | 2030 | 2031
| Statewide | Non-Interstate Pavement Modernization | Pavement Rehab | 0 | 108672000 | 193330000 | 198399000 | 209400000
| Statewide | Statewide Safety Specific | Paving | 0 | 36000000 | 37000000 | 38000000 | 38000000
| Statewide | Statewide Interstate Pavement Rehabilitation | Pavement Rehab | 0 | 5000000 | 15000000 | 15000000 | 15000000
| Statewide | American with Disabilities Act | Pedestrian Improvement | 5500000 | 5500000 | 5500000 | 5500000 | 5500000
| Statewide | Construction Training Program | Training | 1300000 | 1300000 | 1300000 | 1300000 | 1300000
| Statewide | Cooperative City/County/State Highway Research | Research | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Emergency & Contingency (U-STEP/C-STEP) | Construction | 6000000 | 6000000 | 6000000 | 6000000 | 6000000
| Statewide | Pavement Markings | Paint | 12700000 | 12700000 | 12700000 | 12700000 | 12700000
| Statewide | Post Letting Project Cost | Construction | 30000000 | 30000000 | 30000000 | 30000000 | 30000000
| Statewide | Prevocational Training and DBE Support Services | Training | 360000 | 360000 | 360000 | 360000 | 360000
| Statewide | Scenic Byway Program | Signs | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Consultant Services | Outside Services Engineering | 75000000 | 75000000 | 75000000 | 75000000 | 75000000
| Statewide | Statewide Contract Maintenance | Construction | 53300000 | 58000000 | 58500000 | 59000000 | 59500000
| Statewide | Statewide Interstate Guardrail Repair | Guardrail Repair | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide ITS | Equipment | 8000000 | 8000000 | 8000000 | 8000000 | 8000000
| Statewide | Statewide Lighting | Lighting | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
| Statewide | Statewide Operations | Outside Services Engineering | 16000000 | 16000000 | 16000000 | 16000000 | 16000000
| Statewide | Statewide Railroad Crossings | Construction | 500000 | 500000 | 500000 | 500000 | 500000
| Statewide | Statewide Rest Area and Scale Contract Support and Building Repair | Rest Area Improvement | 10600000 | 10700000 | 10800000 | 10900000 | 11000000
| Statewide | Statewide Roadside Improvement | Landscaping | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
| Statewide | Statewide Traffic Control Devices | Signs | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
| Statewide | Summer Infrastructure Rehabilitation Materials | Materials | 1500000 | 1500000 | 1500000 | 1500000 | 1500000
| Statewide | Winter Operations Materials | Materials | 12000000 | 12000000 | 12000000 | 12000000 | 12000000