## PLAT TRACKING
7956 STANLEY HWY 61 ACQUISITION PLATS
TRACKING LOG
2017-08-29
[8 empty] | PLAT |  |  | SUBMITTALS | [12 empty] | STAKING
PARCEL # | Sec/Tshp | #Plats | OWNER | DEED | PIN SEARCH? | CAD TECH | DRAW SUBD/SC | REVIEW | DESC. | PROOF | DIST. | APPR'D | AMES/STANLEY | SIGNED/MAILED | SCs | 7138 PT #s | NOTES | REVISED SUMMARY SHEET | STAKED PRELIM | Additional Work | PARCEL # | HAVE DEED | PREPPED | PIN | POST | CROP AGREEMENT | STRIP MAP UPDATE -TEXT | NOTES
1A |  | 1 | Jennison | 2000-006720 | DONE | CE | SUBD | X |  | x | APPROVED |  | X | X | X | [5 empty] | 1A | DELETED
1B |  | 1 | DIRKS | 2015-001926/001928 | DONE | CE | SUBD | X |  | x | APPROVED |  | X | X | X |  | FORMERLY GRANAMAN |  |  |  | 1B | 2017-08-28
2B |  | 1 | Darnell | E08-000505 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | CNTR,STH 24-70-3 | 4094, 4095 |  |  |  |  | 2B | 2017-08-28
2C |  | 1 | Peterson | 2011-003538/3539 | DONE | CE | SUBD | X |  | x | APPROVED |  | X | X | X | [5 empty] | 2C | 2017-08-28
2E |  | 1 | Blazic | 2008-002525 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | CNTR,STH 24-70-3 | 4094, 4095 |  |  |  |  | 2E | 2017-08-28
3A |  | 1 | Oliver | 99-007906 | DONE? | CE | SC | X |  | x | APPROVED |  | X | X | CNTR,STH 24-70-3 | 4094, 4095 |  |  |  |  | 3A | YES |  | YES | YES | NO | YES
3B |  | 1 | Boyer | 2010-002483 | DONE? | CE | SC | X |  | x | APPROVED |  | X | X | CNTR,STH 24-70-3 | 4094, 4095 |  |  |  |  | 3B | YES |  | YES | YES | NO | YES
4 |  | 1 | Dengler | 2014-0001365 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | CNTR,STH 24-70-3 | 4094, 4095 |  |  |  |  | 4 | YES |  | YES | YES | NO | YES
5 |  | 1 | Graham | 2010-002012 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | CNTR,STH 24-70-3 | 4094, 4095 |  |  |  |  | 5 | YES |  | YES | YES | NO | YES
6(2) |  | 2 | Powell | 2010-005190 | DONE? | CE | SC | X |  | x | APPROVED |  | X | X | CNTR,STH, WEST 24-70-3 | 4094, 4095, 5204 |  |  |  | Plat revisions requested in July 2016 / more revisions Sep 2016 | 6(2) | YES | YES | YES/YES | YES/YES | NO | YES
6A |  | 1 | Niehaus | E12-000835 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | CNTR,NRTH 24-70-3 | 4094, 4092 |  |  | x |  | 6A | YES | YES | YES | YES | NO | YES
6B |  | 1 | Lieb | 97-007355 | DONE |  | SC | X |  | x | APPROVED |  | X | X | NRTH, NW 24-70-3 | 4092, 4091 |  |  |  |  | 6B | YES | YES |  |  | NO | YES | PARTIAL-ONE PIN UNDER JUNK CAR
6C |  | 1 | BURL PROP SOURCE | 2015-005684 | DONE |  | SC | X |  | x | APPROVED |  | X | X | NRTH, NW 24-70-3 | 4092, 4091 |  |  |  |  | 6C | 2017-08-28
6E |  | 1 | Gooch | 98-008232 | DONE |  | SC | X |  | x | APPROVED |  | X | X | NRTH, NW 24-70-3 | 4092, 4091 |  |  |  |  | 6E | YES | YES | YES | YES | NO | YES
7(2) |  | 2? | Phillips Rev. Trust | 2013-004527 |  |  | SC | X |  | X | APPROVED |  | X | X | CNTR,NRTH 24-70-3 | 4094, 4092 |  | X |  |  | 7(2) | YES | YES | 1 OF 2 | 1 OF 2 | NO | YES | PARTIAL- TO STATE DONE/ TO CO. NOT DONE
7A |  | 1 | R&R Development | 2010-005260 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | CNTR,NRTH 24-70-3 | 4094, 4092 |  |  |  |  | 7A | YES | YES | YES | YES | NO | YES
8(3) TA?? |  | 3 | Binder | 353-152 | DONE |  | SC | ON HOLD TA? |  | xxx | ON HOLD TA???? |  |  |  | CNTR,STH, WEST 24-70-3 | 4094, 4095, 5204 |  | X |  |  | 8(3) TA?? | YES | YES | YES | YES | NO | YES
8A |  | 1 | Phillips | 2007-004924 | DONE |  | SC | X |  | x | APPROVED |  | X | X | NRTH, NW 24-70-3 | 4092, 4091 |  |  |  |  | 8A | YES | YES |  |  | NO | YES
9 |  | 1 | Leffler | 366-48 | DONE | CE | ? | X |  | x | APPROVED |  | X | X | NRTH, NW 24-70-3 | 4092, 4091 |  | X |  | Added excess plat June 2016 / Revised plats due to condemnation Apr 2017 | 9 | 2017-08-28 | [5 empty] | CONDEMNATION STAKING TO INCLUDE TEMP EASE
9A |  | 1 | Hutson | 2001-007416 | DONE | CE | SC | X |  | X | APPROVED |  | X | X | CNTR,STH, WEST 24-70-3 | 4094, 4095, 5204 |  |  | X | Revised plat, August 2016 | 9A | YES | YES | YES | YES | NO | YES
10(2) |  | 2 | Johnson, Kenneth | 98-001279 | DONE |  | SUBD | X |  | x | APPROVED |  | X | X | X | [5 empty] | 10(2) | YES | YES | YES/YES | YES/YES | YES | YES | PARTIAL-BECAUSE OF CROPS
12 |  | 0 | Johnson, Vivian | XXXXXX |  | --- |  | --- | --- | --- | --- | --- | --- | --- |  |  | NO SUMMARY SHEET/TOTAL AQCUISITION |  |  |  | 12 | 2017-08-28
12A |  | 1 | Brown, Kent | 2014-006184 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | S 1/4, SW, WEST 13-70-3 | 4092, 4091, 4089 |  |  |  |  | 12A | YES | YES |  |  | NO | YES
12B |  | 1 | Dusenbery | 2000-007386 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | S 1/4, SE, EAST 14-70-3 | 1041, 4091, 4089 |  |  |  |  | 12B | YES | YES | YES | YES | NO | YES
12C |  | 1 | CLASSEN | 2015-004445 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | SE, E 1/4 14-70-3 | 4091, 4089 |  |  |  |  | 12C | YES | YES |  |  | NO | YES
12E |  | 1 | Parrott | 2003-005713 | DONE | CE | SC | X |  | x | APPROVED |  | X | X | SE, S 1/4 14-70-3 | 4091, 1041 |  |  |  |  | 12E | YES | YES | YES | YES | NO | YES
13 |  | 1 | Kolarik | 369-804 | DONE |  | XXXXX | X |  | X | APPROVED |  | X | X | W 1/4, SW, NW 13-70-3 CNTR 14-70-3 | 4089 , 4091, 4090, 4087 |  |  | x twice |  | 13 | 2017-08-28
16-TE |  | 0 | Hammond Trust | 2008-005305 | TEMP ESMNT!! | --- |  | --- | --- | --- | --- | --- | --- | --- | X |  | TEMPORARY EASEMENT ONLY !!!!! |  |  |  | 16-TE | XXXXX
25 |  | 29 | [6 empty] | END OF FIRST PACKAGE
16A |  | 0 TE | Burlington Bank & Trust | 2015-003799 |  | --- |  | --- | --- | --- | --- | --- | --- | --- | [6 empty] | 16A | XXXXX
16B |  | 0 TE | Commercial Plaza Inc. | 2005-007726 |  | --- |  | --- | --- | --- | --- | --- | --- | --- | [6 empty] | 16B | XXXXX
17 |  | 1 | Taeger / Taeger / Taeger | 2011-000082 | [6 empty] | SENT 4-20 | X | X | X | [6 empty] | 17 | YES | YES |  |  | PARTIAL | YES
17A |  | 2 | Stephens | 2010-002805 | [6 empty] | SENT 4-20 | XX | X | X | [5 empty] | Plat revised Feb 2017 | 17A | YES | YES |  |  | NO | YES
18 |  | 2 | Klein | 98-004522 |  | --- |  | --- | --- | --- | --- | --- | --- | --- | [5 empty] | New plat added Feb 2017 | 18 | 2017-08-28
19 |  | 1 | Manning | 94-005400 | [6 empty] | SENT 4-20 | X | X | X |  |  |  |  | x |  | 19 | YES | YES |  |  | NO | YES
19A |  | 3 | Diewold, Andrew | 2012-005698 | [6 empty] | SENT 4-20 | PI???? | X | X | [5 empty] | Plat revised Feb 2017 | 19A | 2017-08-28
20 |  | 1 | Webb | 358-000996 |  |  | X | [5 empty] | X | X | [5 empty] | Plat revised Feb 2017 | 20 | 2017-08-28
21 |  | 1 | Boyle | 2009-005121 |  |  | X | [5 empty] | X | X | [5 empty] | Plat revised Feb 2017 | 21 | YES |  |  |  | NO | YES
22 |  | 0 TA | Lowthorp | 333-000349 |  | --- |  | --- | --- | --- | --- | --- | --- | --- | [6 empty] | 22 | XXXXX
23 |  | 2 | Diewold, Jeffrey | 365-000479 | [6 empty] | SENT 4-29 | x | X | X |  |  |  |  | X |  | 23 | 2017-08-28
24 |  | 2 | Lucas | 2005-001181 |  |  | X | [5 empty] | X | X | [6 empty] | 24 | 2017-08-28
24B |  | 1 | Brown, David | 367-000171 | [6 empty] | SENT 4-20 | X | X | X | [6 empty] | 24B | 2017-08-28
25 |  | 1 | New Life Family Church | 2010-001141 | [6 empty] | SENT 4-29 | X | X | X |  |  |  |  | x |  | 25 | YES |  |  |  | NO | YES
26 |  | 2 | Rickeberg | 2001-002965 | [6 empty] | SENT 4-29 | XX | X | X | [6 empty] | 26 | YES/YES | YES/YES | PARTIAL |  | PARTIAL | YES/YES | PARTIAL STAKING DUE TO C.E. CONVO WITH FARMER
26A |  | 1 | Andries | 97-005729 | [6 empty] | SENT 4-29 | X | X | X |  |  | ESMNT -ON HOLD FIND STONE 1/16TH CORNER |  |  |  | 26A | YES | YES | YES | YES | NO | YES
31 |  | 1 | Koett | 2005-003598 | [6 empty] | SENT 4-20 | X | X | X | [6 empty] | 31 | YES | YES | YES | YES | NO | YES
34 |  | 2 | Pfeiff Farms | 2010-000926 | [6 empty] | SENT 4-29 | XX | X | X |  |  | ESMNT -ON HOLD FIND STONE 1/16TH CORNER |  |  |  | 34 | YES | YES/YES |  |  | PARTIAL | YES/YES
35 | 11-70 | 1 | Pfeiff, Jeanne | 2010-003898 | [6 empty] | SENT 4-29 | X | X | X |  |  | FIELD WORK?? NEED TO ESTABLISH 1/6TH LINE |  |  |  | 35 | YES | YES |  |  | PARTIAL | YES
15 |  | 24 | [6 empty] | END OF SECOND PACKAGE
38 | 2-70 | 1 | Delzell, Craig | 2015-002253 & 2012-005195 | Done | MDK |  | Done | Done | Done | 2016-05-04 | 2016-05-05 | 2016-05-12 | 2016-05-12 | [6 empty] | 38 | YES | YES |  |  | PARTIAL | YES | NEEDS ADDITIONAL ROW INTERSECT POINTS
39 | 2-70 | 1 | Miller, James | UNKNOWN | Done | MDK |  | Done | Done | Done | 2016-05-04 | 2016-05-05 | 2016-05-12 | 2016-05-12 | [6 empty] | 39 | YES | YES |  |  | PARTIAL | YES
40 | 2-70 | 1 | Holmes | 2012-001468 | Done | MDK |  | Done | Done | Done | 2016-05-04 | 2016-05-05 | 2016-05-12 | 2016-05-12 | [6 empty] | 40 | YES | YES |  |  | PARTIAL | YES
43 | 2-70 | 0 | Wolfe | 2012-000464 | Temp Ease Only | --- |  | --- | --- | --- | --- | --- | --- | --- |  |  | Temp Ease Only |  |  |  | 43 | XXXXX
44 | 2-70 | 1 | Cead Farm | 344-64 | Done | MDK |  | Done | Done | Done | 2016-05-10 | 2016-05-11 | 2016-05-12 | 2016-05-12 |  |  |  |  | x |  | 44 | YES | YES | A,B | A,B | PARTIAL | YES
45 | 35-71 | 1 | White Farms | 2009-1933 & 2009-1931 | Done | MDK |  | Done | Done | Done | 2016-04-26 | 2016-04-27 | 2016-04-29 | 2016-04-29 |  |  |  |  | x |  | 45 | YES | YES | YES | YES | PARTIAL | YES
45A | 35-71 | 1 | Nuenviro Design |  | Done | MDK |  | Done | Done | Done | 2016-04-26 | 2016-04-27 | 2016-04-29 | 2016-04-29 | [6 empty] | 45A | YES | YES | YES | YES | PARTIAL | YES
46 | 35-71 | 1 | Chevalier | 2008-000519 | Done | MDK |  | Done | Done | Done | 2016-04-26 | 2016-04-27 | 2016-04-29 | 2016-04-29 | [6 empty] | 46 | YES | YES | YES | YES | NO | YES
48 | 35-71 | 3 | S&S Acres | 2008-003812 | Done | MDK |  | Done | Done | Done | 2016-04-26 | 2016-04-27 | 2016-04-29 | 2016-04-29 | [6 empty] | 48 | YES | YES | YES | YES | PARTIAL | YES
50 | 35-71 | 0 | Siefken | 2012-000072 | Temp Ease Only | --- |  | --- | --- | --- | --- | --- | --- | --- |  |  | Temp Ease Only |  |  |  | 50 | 2017-08-28
51A | 35-71 | 1 | Bartelt, Dale | 2013-003763 | Done | MDK |  | Done | Done | Done | 2016-04-26 | 2016-04-27 | 2016-04-29 | 2016-04-29 | [6 empty] | 51A | YES | YES | YES | YES | PARTIAL | YES
51B | 35-71 | 1 | Breuer / Breuer | 2000-000831 | Done | MDK |  | Done | Done | Done | 2016-04-27 | 2016-04-27 | 2016-04-29 | 2016-04-29 | [6 empty] | 51B | YES | YES | YES | YES | NO | YES
54 | 35-71 | 2 | Birkenstock | 2009-004933 | Done | MDK |  | Done | Done | Done | 2016-04-27 | 2016-05-03 | 2016-05-12 | 2016-05-12 | [6 empty] | 54 | 2017-08-28
56 | 26-71 | 2 | Taeger, Scott | 2003-006109 | Done | MDK |  | Done | Done | Done | 2016-04-19 | 2016-04-22 | 2016-04-29 | 2016-04-29 | [6 empty] | 56 | YES | YES |  |  | PARTIAL | YES
57 | 26-71 | 1 | Jones | 2011-002907 | Done | CE |  | Done | Done | Done | 2016-04-19 | 2016-04-22 | 2016-04-29 | 2016-04-29 | [6 empty] | 57 | YES | YES | YES | YES | PARTIAL | YES
57A | 26-71 | 1 | Thie, Donald | 2013-005830 | Done | CE |  | Done | Done | Done | 2016-04-19 | 2016-04-22 | 2016-04-29 | 2016-04-29 | [6 empty] | 57A | YES | YES | YES | YES | NO | YES
58 | 26-71 | 1 | Bartelt, Dale | 2008-005306 | Done | CE |  | Done | Done | Done | 2016-04-19 | 2016-04-22 | 2016-04-29 | 2016-04-29 | [5 empty] | additional POLs set on 7/12/17 | 58 | YES | YES | YES | YES | NO | YES
59 | 26-71 | 1 | Taeger, Dean | 326-000421 | Done | CE |  | Done | Done | Done | 2016-04-19 | 2016-04-22 | 2016-04-29 | 2016-04-29 | [6 empty] | 59 | YES |  |  |  | PARTIAL | YES
60 | 26-71 | 2 | Miller, Wayne | 2000-001080 | Done | CE |  | Done | Done | Done | 2016-04-19 | 2016-04-22 | 2016-04-29 | 2016-04-29 |  |  |  | added stream ease |  | Added stream mitigation plat July 2016 | 60 | YES | YES | FEE ONLY | FEE ONLY | PARTIAL | YES
61 | 23-71 | 2 | Miller, Jerry | 2014-005668 | Done | MDK |  | Done | Done | Done | 2016-03-04 | 2016-03-18 | 2016-04-01 | 2016-04-01 |  |  |  | added stream ease |  | Added stream mitigation plat July 2016 | 61 | 2017-08-28
63 | 23-71 | 1 | Chase | 2000-003692 & 2010-002627 & 2000-003692 | Done | MDK |  | Done | Done | Done | 2016-03-04 | 2016-03-18 | 2016-04-01 | 2016-04-01 |  |  | May be split up for appraisals, will need to change | added stream ease |  | Added stream mitigation plat July 2016 | 63 | YES | YES | YES | YES | PARTIAL | YES
64 | 23-71 | 2 | Kephart | 2005-007364 | Done | MDK |  | Done | Done | Done | 2016-03-04 | 2016-04-08 | 2016-04-15 | 2016-04-15 | [6 empty] | 64 | YES | YES | YES | YES | NO | YES
END OF THIRD PACKAGE
65 | 23-71 | 1 | Ellerhoff | 362-000074 | Done | MDK |  | Done | Done | Done | 2016-03-04 | 2016-03-18 | 2016-04-01 | 2016-04-01 | [6 empty] | 65 | YES | YES | YES | FEE ONLY | PARTIAL | YES
67 | 23-71 | 2 | Taeger, Dean | 2005-001970 | Done | MDK |  | Done | Done | Done | 2016-03-04 | 2016-03-18 | 2016-04-01 | 2016-04-01 | [6 empty] | 67 | YES | YES | A,B | A,B | PARTIAL | YES
68 | 23-71 | 1 | Duke | 2002-006534 | Done | MDK |  | Done | Done | Done | 2016-03-04 | 2016-03-18 | 2016-04-01 | 2016-04-01 |  |  |  |  | x | Access Control added to plat | 68 | YES | YES |  |  | PARTIAL | YES
69 | 14-71 | 2 | Janssen | 2006-005537 | Done | MDK |  | Done | Done | Done | 2016-03-15 | 2016-03-28 | 2016-04-01 | 2016-04-01 | [6 empty] | 69 | YES | YES | A,B,C | A,B,C | PARTIAL | YES
73 | 14-71 | 1 | Marsa LLP / Cannon | 2008-001346 | Done | MDK |  | Done | Done | Done | 2016-03-15 | 2016-03-28 | 2016-04-01 | 2016-04-01 | [5 empty] | Access Control added to plat | 73 | YES | YES |  |  | PARTIAL
74 | 14-71 | 2 | Flagstone LLLP | 2008-002509 | Done | MDK |  | Done | Done | Done | 2016-03-15 | 2016-03-28 | 2016-04-01 | 2016-04-01 | [5 empty] | Added exhibit for Temp Ease and description | 74 | 2017-08-28 | [5 empty] | CONDEMNATION STAKING TO INCLUDE TEMP EASE
75 | 14-71 | 2 | Loper | 2007-000255 | Done | MDK |  | Done | Done | Done | 2016-03-15 | 2016-03-28 | 2016-04-01 | 2016-04-01 | [6 empty] | 75 | YES | YES | B,C,D | B,C,D | PARTIAL | YES
76 | 14-71 | 1 | Scheihing | 2010-002479 | Done | AB |  | Done | Done | Done | 2016-03-15 | 2016-03-28 | 2016-04-01 | 2016-04-01 | [6 empty] | 76 | YES | YES | YES | YES | PARTIAL | YES
77 | 11-71 | 2 | Iowa County Equip | 2014-000029 | Done | Jen |  | Done | Done | Done | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-15 |  |  |  |  | x |  | 77 | 2017-08-28
78 | 11-71 | 2 | Fye | 2008-006594 | Done | AB |  | Done | Done | Done | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-15 |  |  |  |  | x |  | 78 | 2017-08-28
78A | 11-71,2-71,35-72 | 1 | U.S. Bank | 2012-002669 | Done | Jen |  | Done | Done | Done | 2016-04-08 | 2016-04-11 |  |  |  |  | N tract will be cancelled, other 2 tracts will be split up for appraisals |  |  | Split into 78A, 78B, 78C Plats for 78A and 78B Feb 2017 | 78A | YES | YES |  |  | PARTIAL | YES
78B |  | 1 | [18 empty] | 78B | YES | YES |  |  | PARTIAL
78C |  | 1 | [10 empty] | Hold | [7 empty] | 78C
79 | 11-71 | 1 | Nelson | 2015-003844 | Done | MDK |  | Done | Done | Done | 2016-04-01 | 2016-04-06 | 2016-04-15 | 2016-04-15 | [6 empty] | 79 | YES | YES | YES | YES | PARTIAL | YES
80 | 11-71 | 2 | Brader | 2003-004861 | Done | MDK |  | Done | Done | Done | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-15 | [6 empty] | 80 | YES | YES |  |  | PARTIAL | YES
81 | 11-71 | 1 | Myers | 2015-005279 | Done | Jen |  | Done | Done | Done | 2016-04-01 | 2016-04-06 | 2016-04-15 | 2016-04-15 | [6 empty] | 81 | YES | YES | YES | YES | PARTIAL | YES
82 | 11 & 2-71 | 2 | Mediapolis Farms | 2014-001272 | Done | MDK |  | Done | Done | Done | 2016-04-01 | 2016-04-08 | 2016-04-15 | 2016-04-15 | [6 empty] | 82 | YES/YES | YES/YES | YES/YES | YES/YES | PARTIAL | YES/YES
87 | 2-71 | 1 | Berning Farm | 349-000744 | Done | AB |  | Done | Done | Done | 2016-04-08 | 2016-04-11 | Candelled |  |  |  | Cancelled, but we were done |  |  |  | 87 | [6 empty] | NOW IN SECTION 2
89 | 35-72 | 1 | Roy Frownfelter Trust | 98-007846 | Done | Jen |  | Done | Done | Done | 2016-04-08 | 2016-04-11 | Candelled |  |  |  | Cancelled, but we were done |  |  |  | 89 | [6 empty] | NOW IN SECTION 2
90 | 35-72 | 1 | Frownfelter | 2012-000428 | Done | Jen |  | Done | Done | Done | 2016-04-08 | 2016-04-11 | 2016-04-15 | 2016-04-15 |  |  | Cancelled, but we were done |  |  |  | 90 | [6 empty] | NOW IN SECTION 2
38 |  | 55 | [6 empty] | END OF PROJECT | [10 empty] | Plat for Wetland mitigation (Hickory Bend) area added Jan 2017 | 1M
78 | Parcels | 108 | Plats
-27 | Out 4/1
-16 | Out 4/15
-18 | Out 4/29
-2 | Cancelled 4/29
-14 | Out 5/12
Out 5/27
1 | Remaining
SET ROW SIGNS AT PREVIOUS ROW POINTS THAT ARE STILL ROW POINTS?!?!?!?
GREEN = DONE
YELLOW = ON HOLD CROPS OR OTHER REASON
8/15/2017 NO DEEDS RECORDED IN LAST 7 DAYS
STRIP MAP TO BE UPDATED - PARCELS 1M,18,78A,78B,20,21,19A,17A,9
PREPARE AFFIDAVIT FOR PARCELS 19,18

## Sheet1
PARCEL # | Sec/Tshp | #Plats | PARCEL # | HAVE DEED | PREPPED | PIN | POST | CROP AGREEMENT
17 |  | 1 | 17 | YES | YES
17A |  | 2 | 17A | YES | YES
18 |  | 0 TA | 18 | XXXXX
19 |  | 1 | 19 | 2017-05-24
19A |  | 3 | 19A | 2017-05-24
20 |  | 1 | 20 | 2017-05-24
21 |  | 1 | 21 | 2017-05-24
22 |  | 0 TA | 22 | XXXXX
23 |  | 2 | 23 | 2017-05-24
24 |  | 2 | 24 | 2017-05-24
24B |  | 1 | 24B | 2017-05-24
25 |  | 1 | 25 | 2017-05-24
26 |  | 2 | 26 | YES/YES | YES/YES
26A |  | 1 | 26A | YES | YES
31 |  | 1 | 31 | YES | YES
34 |  | 2 | 34 | YES | YES/YES
35 | 11-70 | 1 | 35 | YES | YES
15 |  | #REF!
38 | 2-70 | 1 | 38 | YES | YES
39 | 2-70 | 1 | 39 | YES
10(2) |  | 2
12 |  | 0
12A |  | 1
12B |  | 1
12C |  | 1
12E |  | 1
13 |  | 1
16-TE |  | 0