## Sheet1
Status | Event | Description | Responsible Office/Section | Milestone | Relationship w/Other Event(s)
Active | A01 | Approval of DOT Commission - Inclusion in 5-Year Program | Program Management | Yes
Archived | A02 | Approval by the DOT Commission - Location Public Hearing | OLE: Public Involvement | Yes
Archived | A03 | FONSI/ROD Signature | OLE: NEPA | No
Active | A04 | Approval by DOT Commission - Design Public Hearing | OLE: Public Involvement/District | Yes
Archived | A05 | Environmental Clearance by FHWA (CE) | OLE: NEPA | Yes
Archived | A06 | Design Approval by FHWA | OLE: Public Involvement | Yes
Archived | A07 | Environmental Clearance - Non Federal Aid | OLE: NEPA | Yes
Archived | A08 | NEPA Re-evaluation | OLE: NEPA | No
Active | AC1 | Access Control Determination | Traffic and Safety | No | Same Start Date as CP1
Active | AC5 | Access Control Validation | Traffic and Safety | No | 3 weeks before D05
Active | B00 | Bridge Office Concept | Bridges and Structures | No
Active | B01 | Bridges and Structures Layout | Bridges and Structures: Preliminary Bridge | No | D03 + 3 Months
Active | B02 | Drainage Design and Miscellaneous Layout to Office of Design | Bridges and Structures | No | If schedule includes D03 then D03 + 3 Mo, else 1 month before Plan-Turn In
Active | B03 | Final Bridge Plans | Bridges and Structures | No | 1st Tuesday of the Month, 2 Months before Letting
Active | B04 | Structural Design Plans to Office of Design | Bridges and Structures | No | Schedule one month before Plan-Turn In
Active | B05 | Section 408 review/approval | Bridges and Structures | No | D05 + 2 months
Active | C02 | Construction Period (Field Work) | District & Construction | No
Active | CFA1 | Capacity Funding Agreement for Interstate Projects | District | No | Scheduled completion same as D05, else 6 months prior to Letting for the first project.
Active | CP1 | Concurrence Point 1 – Purpose and Need | OLE: Water Resources | No
Active | CP2 | Concurrence Point 2 – Alternatives to be Analyzed | OLE: Water Resources | No
Active | CP3 | Concurrence Point 3 – Alternatives to be Carried Forward | OLE: Water Resources | No
Active | CP4 | Concurrence Point 4 – Preferred Alternative | OLE: Water Resources | No
Active | CP5 | Mitigation Concurrence | OLE: Water Resources | No
Active | D00 | Pre-Design Concept | Design: Pre-Design Section | No
Active | D01 | Survey Plan and Photogrammetry (DTM) | Design: Photogrammetry/Survey Section | No | D00 + 6 Months
Active | D02 | Design Field Exam | Design: Rural/Urban Sections | No
Active | D03 | Plans for Preliminary Bridge | Design: Rural/Urban Sections | No | D02 +/- 1 Month
Active | D04 | Design Plans for Bridge | Design: Rural/Urban Sections | No | 17 Weeks before Letting
Active | D05 | Plans to Right Of Way | Design: Rural/Urban Sections | No | B01 and/or S02 +1 Month
Active | D06 | Final Grade Plans | Design: Rural/Urban Sections | No | 1st Tuesday of the Month, 2 Months before Letting
Active | D07 | Final Pave Plans | Design: Rural/Urban Sections | No | 1st Tuesday of the Month, 2 Months before Letting
Active | D08 | Final Grade and Pave Plans | Design: Rural/Urban Sections | No | 1st Tuesday of the Month, 2 Months before Letting
Active | D09 | Final Miscellaneous Plans | Design: Rural/Urban Sections | No | 1st Tuesday of the Month, 2 Months before Letting
Active | DM5 | Design Methods Turn-In | Design: Rural/Urban Sections | Yes | 5 Weeks before Plan Turn-In
Active | DSW1 | Storm Water Permit for Outstanding Iowa Waterways | Design and Districts | No | 120 days before Letting
Active | E01 | Final Erosion Plans | Design: Roadside Development Section | No | 1st Tuesday of the Month, 2 Months before Letting
Active | E02 | Final Landscape Plans | Design: Roadside Development Section | No | 1st Tuesday of the Month, 2 Months before Letting
Active | E03 | Final Mitigation Plans | OLE: Water Resources | No | 1st Tuesday of the Month, 2 Months before Letting
Active | E04 | Roadside Plans for Design | Design: Roadside Development Section | No | 3 months before DM5
Active | F01 | Preliminary Regulated Materials Review | OLE: Regulated Materials | No
Active | F02 | Interim Regulated Materials Review | OLE: Regulated Materials | No
Active | F03 | Final Regulated Materials Review | OLE: Regulated Materials | Yes | D05 +1 Month
Active | FP1 | Financial Plan by OLE | OLE: Location | No
Active | FP2 | Financial Plan by Design | Design | No
Active | FP3 | Financial Plan by Bridges and Structures | Bridges and Structures | No
Active | FP4 | Financial Plan by District | District | No
Active | H00 | Cultural Resources Assessment | OLE: Cultural Resources | No | D00 or B00 +1 Month
Active | H01 | Phase I Archaeological Investigation | OLE: Cultural Resources | No | H00 or S01 +9 Months
Active | H02 | Phase II Archaeological Evaluation | OLE: Cultural Resources | No | H01 or D02 or S02 +10 Months
Active | H03 | Intensive Historical Evaluation | OLE: Cultural Resources | No | H00 +9 Months
Active | H04 | Mitigation for Historic Property Impacts | OLE: Cultural Resources | No | H02 or H03 and D05 +18 Months
Active | H05 | Cultural Re-evaluation | OLE: Cultural Resources | No
Active | IJR1 | Interchange Justification Report by OLE | OLE: Location | No
Active | IJR2 | Interchange Justification Report by Design/Bridges/Structure | Design/Bridges and Structures | No
Active | IJR3 | Interchange Justification Report by District | District | No
Active | IJR4 | Interchange Justification Report by Systems Planning | Systems Planning | No
Active | IJR5 | Interchange Justification Report Approval | FHWA | Yes
Active | ITS0 | Traffic Operations Concept | Traffic Operations | No | 3 Months
Active | ITS1 | Traffic Operations Field Exam | Traffic Operations | No | 3 Months
Active | ITS2 | Preliminary Plan Turn-in | Traffic Operations | No | 5 Weeks before Plan Turn-In
Active | ITS3 | Final ITS Equipment Plans | Traffic Operations | No | 1st Tuesday of the Month, 2 Months before Letting
Active | ITS4 | Final ITS Infrastructure Plans | Traffic Operations | No | 1st Tuesday of the Month, 2 Months before Letting
Active | ITS5 | Final ITS Integration Plans | Traffic Operations | No | 1st Tuesday of the Month, 2 Months before Letting
Active | ITS6 | Final IWZ Plans | Traffic Operations | No | 1st Tuesday of the Month, 2 Months before Letting
Active | ITS7 | Final OTO Other Plans | Traffic Operations | No | 1st Tuesday of the Month, 2 Months before Letting
Active | L01 | Letting-Grade | Contracts & All affected offices | No
Active | L02 | Letting-Paving and Incidentals | Contracts & All affected offices | No
Active | L03 | Letting-Combination Grade and Pave | Contracts & All affected offices | No
Active | L04 | Letting-Miscellaneous | Contracts & All affected offices | No
Active | L05 | Letting-Bridge and Culverts | Contracts & All affected offices | No
Active | L06 | Letting-Erosion Control | Contracts & All affected offices | No
Active | L07 | Letting-Landscape | Contracts & All affected offices | No
Active | L08 | Letting-Mitigation | Contracts & All affected offices | No
Active | L09 | Letting-Traffic Signals | Contracts & All affected offices | No
Active | L10 | Letting-Traffic Signs | Contracts & All affected offices | No
Active | L11 | Letting-Lighting | Contracts & All affected offices | No
Active | L12 | Letting-Dynamic Message Signs | Contracts & All affected offices | No
Active | L13 | Letting-Pavement Markings | Contracts & All affected offices | No
Active | L14 | Letting-ITS Equipment | Contracts & All affected offices | No
Active | L15 | Letting-ITS Infrastructure | Contracts & All affected offices | No
Active | L16 | Letting-ITS Integration | Purchasing | No
Active | L17 | Letting-IWZ | Purchasing / EWO with Vendor | No
Active | L18 | Letting-OTO Other | Contracts / Purchasing | No
Archived | M01 | Final Signing Plans | Traffic & Safety: Traffic Engineering Section | No | 1st Tuesday of the Month, 2 Months before Letting
Archived | M02 | Final Signal Plans | Traffic & Safety: Traffic Engineering Section | No | 1st Tuesday of the Month, 2 Months before Letting
Active | N00 | Prelim Noise Impact | OLE: Noise | No | D00 + 30
Active | N01 | Completion of Noise Study | OLE: Noise | No | D02 + 30 (for NE11) or NE20-60 (for NE20)
Active | N02 | Design Review | OLE: Noise | No | D03 + 45 (adjust based on D03 and B01)
Active | NE10 | Signed PCE | OLE: NEPA | No | D02 + 30 days
Active | NE11 | Signed CE | OLE: NEPA | No | D02 + 60 days
Active | NE20 | Signed EA | OLE: NEPA | No | CP3 + 4 months
Active | NE21 | Signed FONSI | OLE: NEPA | No | NE20 + 5 months
Active | NE30 | Signed DEIS | OLE: NEPA | No | CP3 + 4 months
Active | NE31 | Signed FEIS | OLE: NEPA | No | NE30 + 15 months
Active | NE32 | Signed ROD | OLE: NEPA | No | NE31 + 3 months
Active | NE40 | NEPA Re-evaluation | OLE: NEPA | No | R01 + 60 days
Active | P00 | Planning Concept - Pre-Program | OLE: Location | No | Same Finish as A03
Active | P01 | Location Concept-Clearinghouse Notification | OLE: Location | Yes
Active | P02 | Preliminary Relocation Assistance Plan | ROW: Relocation Section | Yes
Archived | P03 | EA/Draft EIS Signature | OLE: NEPA | Yes
Archived | P04 | Location Public Hearing | OLE: Public Involvement/District | Yes
Active | P05 | Pre-Design Agreement | Local Systems: Agreement | Yes | 1 month after D05
Archived | P06 | Design Public Hearing | OLE: Public Involvement/District | Yes | R01 +8 Weeks
Archived | P07 | Combination Location and Design Hearing | OLE: Public Involvement/District | Yes
Active | P08 | Pre-Construction Agreement | Local Systems: Agreement | Yes | 3 Months before Letting
Active | P09 | Public Information Meeting (PIM) | OLE: Public Involvement/District | Yes | R01 +6-8 Weeks
Active | P10 | Public Involvement Activities by District | District | Yes
Active | P11 | Detour Agreement(s) with Local Jurisdiction(s) by District | District | Yes
Active | P12 | Media Contact | OLE: Public Involvement | Yes
Active | P14 | Corridor Preservation | OLE: Public Involvement | Yes
Active | P15 | Public Hearing | OLE: Public Involvement | Yes
Active | PL1 | Planning Concept - Range of Alternatives | OLE: Location | No | 1 month before CP2 on Major projects
Active | PL2 | Planning Concept - Refined Alternatives | OLE: Location | No | CP3 + 3-4 Months
Active | R00 | Plot Plans and Summary Sheets to District | ROW: Design Section | Yes | Same as P06/P09 or R01 (depends on project)
Active | R01 | Right Of Way Layout | ROW: Design Section | No | D05 + 3 Months
Active | R02 | Right Of Way Appraisal | ROW: Appraisal Section | No | T02 + 3 Months
Active | R03 | Right Of Way Negotiation | ROW: Acquisition Section | No | R02 + 3 Months
Active | R04 | Right Of Way Acquisition | ROW: Condemnation or Title & Close Section | No | R03 + 6 Months
Active | R05 | Right Of Way Relocation | ROW: Relocation Section | No | R04 +1 Month
Archived | R06 | Utility Agreement | Traffic & Safety: Utility Section | Yes | R04 +1 Month
Archived | RR00 | Preliminary Rail Road Review | Rail Road | Yes | CP2 + 1 Month
Active | RR01 | Initial Railroad Concurrence Review | Rail Road | No | Same as completed B2/D2 + 1 Month
Active | RR02 | Railroad Review of ROW Easement | Rail Road | Yes | After T01 & R01 are completed + 1 Month (would like notice to be sent to rail) need D5
Active | RR03 | Final Railroad Concurrence Point | Rail Road | Yes | After D5 + 1 month
Active | RR04 | Railroad Agreement | Rail Road | Yes | After D6/D7/D8 and Traffic Control Staging + 1 Month
Active | S01 | Potential Borrow and Alignment Review | Design: Soils Section | No
Active | S02 | Identification of Soils Related ROW Issues | Design: Soils Section | No
Active | S03 | Soils Design Complete | Design: Soils Section | No
Active | S04 | Soils Submittal to Bridge | Design: Soils Section | No | B01 + 5 Months
Active | T01 | Existing ROW, Property and Sections Lines in CADD | District: ROW | No
Active | T02 | Acquisition Plats and Legal Descriptions | District: ROW | No | P06/P09/P10 + 2 Months
Active | TCP1 | Traffic Critical Projects 1 | Traffic and Safety | No | (same as D00)
Active | TCP2 | Traffic Critical Projects 2 | Traffic and Safety | No | B01 and/or S02 +1 Month (same as D05)
Active | TD00 | Concept | Traffic and Safety | No | (same as D00)
Active | TD01 | Preliminary Traffic Engineering Layout | Traffic and Safety | No | D02 +/- 1 Month (same as D03)
Active | TD03 | Traffic Engineering Info to Bridges | Traffic and Safety | Yes | 1 year before Plan Turn-In
Active | TD05 | Plans for Other Offices | Traffic and Safety | No | 17 weeks before Letting
Active | TD07 | Preliminary Plan Turn-In | Traffic and Safety | Yes | 5 Weeks before Plan Turn-In
Active | TD09 | Final Signal Plans | Traffic and Safety | No | 1st Tuesday of the Month, 2 Months before Letting
Active | TD10 | Final Signing Plans | Traffic and Safety | No | 1st Tuesday of the Month, 2 Months before Letting
Active | TD11 | Final Lighting Plans | Traffic and Safety | No | 1st Tuesday of the Month, 2 Months before Letting
Active | TD12 | Final Dynamic Message Signs Plans | Traffic and Safety | No | 1st Tuesday of the Month, 2 Months before Letting
Active | TD13 | Final Pavement Markings Plans | Traffic and Safety | No | 1st Tuesday of the Month, 2 Months before Letting
Archived | TD14 | ITS Equipment | Traffic and Safety | No | 1st Tuesday of the Month, 2 Months before Letting
Active | TE0 | Desktop Review | OLE: Threatened/Endangered Species | No | D00 + 30 days
Archived | TE0 | Threatened/Endangered Species Review | OLE: Threatened/Endangered Species | No
Active | TE1 | Field Review/Field Work | OLE: Threatened/Endangered Species | No | D02 + 30 days
Archived | TE1 | Threatened/Endangered Species Consultation and Clearance | OLE: Threatened/Endangered Species | No
Active | TE2 | Consultation with USFWS | OLE: Threatened/Endangered Species | No | D05 + 60 days
Active | TE3 | Coordination with Iowa DNR | OLE: Threatened/Endangered Species | No | D05 + 60 days
Active | TE4 | Minimization Measures | OLE: Threatened/Endangered Species | No | Date to be requested/identified by OLE
Active | TE5 | Mitigation Actions | OLE: Threatened/Endangered Species | No | D05 + 60 days
Active | TE6 | Re-evaluation of Impacts | OLE: Threatened/Endangered Species | No | Date to be requested/identified by OLE
Archived | TMP1 | Transportation Management Plan | Traffic and Safety | No | (same as D00)
Archived | TMP2 | Transportation Management Plan | Traffic and Safety | No | B01 and/or S02 +1 Month (same as D05)
Active | U00 | Preliminary Utility Review | Utilities | No | D00 or CP2 + 1 Month
Active | U01 | General Project Info Submitted to Utilities | Utilities | No | D00 + 1 Month
Active | U02 | Project Notification to Utilities | Utilities | No | D02 + 4 Months
Active | U03 | 1st Plan Submital to Utilities | Utilities | No | R01 + 4 Months
Active | U04 | 2nd Plan Submittal to Utilities | Utilities | No | Plan Turn-In Date - 6 Months (or 180 days)
Active | U05 | Utility Agreement | Utilities | No | Start date is U04 Finish Date
Active | U06 | Notice to Proceed to Utilities | Utilities | No | Plan Turn-In Date - 2 Months (or 60 Days)
Active | U07 | Utility Bid Attachment | Utilities | No | Finish date is Plan Turn-In Date
Active | VE1 | Value Engineering Study during Planning Phase | Design: Rural/Urban Sections | No
Active | VE2 | Value Engineering Study during Design Phase | OLE: Location | No | D02 + 1 Month
Active | W00 | Preliminary Wetland Review | OLE: Water Resources | No | D00 or P00 +1 Month
Active | W01 | Wetland Design Review | OLE: Water Resources | No | D02 + 1 Month
Active | W02 | Wetland Field Work | OLE: Water Resources | No | Individual Permit (IP) 7 Months before W04. Nationwide Permit (NWP) 2 Months before W04.
Active | W03 | 404 Permit Submittal | OLE: Water Resources | Yes | Individual Permit (IP) 7 Months before W04. Nationwide Permit (NWP) 2 Months before W04.
Active | W04 | 404 Permit Clearance | OLE: Water Resources | Yes | 6 Months Before Letting
Active | W05 | Mitigation Submittal to Other Offices | OLE: Water Resources | No
Active | W06 | Mitigation Post Construction Report | OLE: Water Resources | No