## Sheet1
Schedule Event | Concurrent Event | Duration (days) | ROW Utilities Supervisor | Regional Utility Program Coordinator | District Utility Coordinator | Utility Company | Utilities Program Admin | Additional Notes
U00 Preliminary Utility Review - conducted by department - includes OneCall locates & survey - look for major impacts & potentially high cost relocations | D00 | 30 | Reviews, monitors, and reports on event status as part of ROW production oversight | Monitors projects with U00 through U02 and stays in contact with the DUC regarding project status and need for point 25 | Monitors the project and determines if utility impacts are likely; determines if the project is a point 25 project
|  |  | Participate and manage Production reporting for ROW Bureau | Ensure MW system fields are correctly noted | Reviews Utility infrastructure within the extent of the project and requests further investigation if necessary (SUE)
|  |  | Liaison between Bureau/TDD/District for project related issues |  | Verifies the owners of utility infrastructure
|  |  |  | Adds or updates utility company information in PSS/MW as needed | Ensures contact information and utility company information is in PSS/MW
Sends out preliminary U00 if needed. Attends PMT meetings. Check into DOT.net distribution maps for potential overhead conflicts and or potential site visits. Note: this is a U01 task.
Enters U00 start/completion date in PSS/MW
U01 Utility investiagion - evaluation of existing utility facilities - request existing locations of utiltiies - department determines utility engineering needed including SUE investigation |  | 90 | Reviews, monitors, and reports on event status as part of ROW production oversight | Reviews preliminary survey information for known infrastructure in the project area | Receives (U01) utility location information and distributes/notifies designer; makes recommendation to project manager on the need for greater SUE investigation | Receives U01 request and provides location information to the DUC in GIS or CAD format; alternatively verifies that the location of the facilities on the plans is accurate. |  | Some DUC's preform these tasks at the U00 event instead of having the U01 created depending on the complexity of the project Note: We need to keep these a separate events for consistency in the utility program.
|  |  | Participate and manage Production reporting for ROW Bureau | Sends U01 to utility company requesting project location information preferably in GIS or CAD format | Requests/receives high level relocation estimate when potential impact is substantial or complex; provides high level estimate to RUPC
|  |  | Liaison between Bureau/TDD/District for project related issues | Identify known utility infrastructure information and conduct a preliminary estimate for major impacts (Top Ten and annual estimates) | As needed reach out to utility companies to identify known information
|  |  |  | Enters U01 start date in PSS/MW | Enters U01 completion date in PSS/MW
U02 Project Notification to Utility Companies - concept provided, they let us know if their facilities could be impacted (we want to turn this around to us telling them of the conflicts) early enough to allow for modificiton to design to avoid major impacts. They request DOT acquire easements if applicable. | D02 | 90 | Reviews, monitors, and reports on event status as part of ROW production oversight | Sends U02 submittal with preliminary plans to utility companies requesting further location information/verification of location on plans | Receives (U02) utility location/verification information and distributes/notifies designer; makes recommendation to project manager for further SUE investigation needs | Util Co reviews D02 Plan Submittal |  | Distribute/notifies designer is not a normal practice for the DUC's
|  |  | Participate and manage Production reporting for ROW Bureau |  | Enters date acknowledged in PSS/MW and sends to ROW (MW will track automatically when Util Co enters field information into the system) | Util Co acknowledges receipt and sends to DUC within 7 days. |  | The work the RUPC and DUC do for the Production Schedule Report or the Letting Report is not noted in this spreadsheet, but each expends a great deal of time on these
|  |  |  | Enters U02 start date in PSS/MW | Enters U02 completion date in PSS/MW
U05 (coordination) |  |  | Coordinate production needs between ROW sections | Ensure MW system fields are correctly noted | Enters easement needed in PSS/MW (system notifies RUPC) | Provides verification of location of existing facilities (90 days window)
|  |  | Provide guidance and facilitate bureau coordination | Communicates Easement Needs to ROW Design for incorporation into R01 | DUC reviews conflict analysis alerts designer requesting design modification to AVOID facilities where practical | Identifies private easement needed |  | Conflict analysis is not a current practice for the DUC's
[5 empty] | Field exam. Confirm it’s a point 25 project. Look at potential needs for new right of way. Determine Overhead Utilities with-in project limits since its not part of the one call request. Reminder and follow-up emails/calls are common to utility companies to get responses for the U02 notifications. |  |  | New Note
PR01 | D05 | 90 | Monitors and initiates collaboration between ROW-Design and RUPCs | ROW Design completes PR1 requesting Utility Easement Needs | Reviews companies in PSS/MW and verifies they are correct/notifies ROW ok to send U03
U03 1st Plan Submittal (final design/ROW plans D05/R01) to utility companies to prepare Preliminary Work Plan; also requests reimbursement for eligible relocations | R01 | 90 | Reviews, monitors, and reports on event status as part of ROW production oversight | Places PR01 plans and D05 plans on ftp site for utility companies to access | Request RUPC to send U03 notifications
|  |  | Coordinate production needs between ROW sections | Sends U03 "1st Plan Submittal" to utility company requesting conflict review and relocation work plan noting utility response deadline to establish timeline for code compliance ; 'PSS/MW report prepares letters and forms for ROW to email to Utility Companies |  | Receives U03 submittal and reviews plans for potential impact with their facilities/prepares Relocation Work Plan when appropriate
|  |  | Participate and manage Production reporting for ROW Bureau |  |  | Reviews U03 1st Plan Submittal
|  |  | Liaison between Bureau/TDD/District for project related issues |  |  | Acknowledges receipt and sends to DUC within 7 days
Prepares Relocation Work Plan with conflict resolutions, estimate and schedule; requests reimbursement when applicable
[5 empty] | Monitors the utility company responses and reaches out to jointly or individually to ensure we have work plan within 90 days | Returns U03 Work Plan to DUC within 90 days |  | Reminder and followup emails/calls are common to utility companies to get responses for the U03 notifications.
|  |  |  | Begins U05 agreement process when utility company is requesting reimbursement | Receives work plan from utility and enters date U03 Work Plan received and updates status in PSS/MW (MW will track automatically alert DUC that activity taking place within system) Forwards utility NEW easement needs to ROW (if any) | Prepares Reimbursement Agreement Request/Existing Easements/Data Inquiry Sheet/Preliminary Estimate
[5 empty] | Reviews work plan for conformity to project/works with Util Co/Designer on modifications to Work Plan/DOT Plans | Makes any necessary revisions to Work Plan and resubmit within 30 calendar days
Notifies Util Co when Work Plan is approved
|  |  |  | Enters U03 "actual" start date for project | Enters U03 completion date in PSS/MW
U05 (coordination) |  |  | Reviews, monitors, and reports on event status as part of ROW production oversight | Work with ROW Design to begin identifying acquisition parcels for priority status | Updates PSS/MW with possible parcels involved in relocation and marks those needing Advanced ROW Purchase |  |  | Tends to be to late in the project to get realistic results for additional ROW needs.
|  |  | Coordinate production needs between ROW sections | Alert ROW Admin/Design/Acquisition regarding possible need for individual clearances; ROW Design/Acquisition coordinates with LEB | Request NEW Easement details from utility company | Provides NEW easement details to DUC
|  |  | Liaison between Bureau/TDD/District for project related issues | Alert ROW Admin/Design to ensure FHWA concurrence with advanced acquisition
|  |  |  | Review and share NEW easement details with ROW-Design | Reviews requests for reimbursement and requests additional information from Util Co | Provides additional information as needed
Facilitate the completion of "Project Inquiry Data Sheet" and "Reimbursement Eligibility Request"
[5 empty] | Joint Utility Meetings as needed. Attending PMT and PIM meetings. |  |  | New Note
R01 | D05 (final) | 30 | Monitors and initiates collaboration between ROW-Design and Utility Program coordinators | Coordinate ROW-Design to incorporate Utility Easement needs within ROW layout | verifies easement needs and impacts are defined correctly | Reviews ROW layout and easement area, then confirms acceptance with layout
U04 2nd Plan Submittal (revised final plan after PIM) to utility companies to prepare Final Work Plan |  | 60 | Coordinate production needs between ROW sections | Sends (U04) final plans & final ROW layout to utility companies; enters "actual start date" to establish timeline for code compliance |  | Receives and reviews (U04) final plans and completes form within 7 calendar days requesting relocation reimbursement or private easements
|  |  | Reviews, monitors, and reports on event status as part of ROW production oversight | Ensures event dates are entered and accurate | Contact each impacted utility privately or jointly prior to U04 to address relocation concerns | Supply to the DOT with final relocation plans and cross sections within 60 days
|  |  | Participate and manage Production reporting for ROW Bureau |  | Receive Final Work Plans from utility companies
|  |  | Liaison between Bureau/TDD/District for project related issues |  | Review compatibility of Final Work Plan and address any concerns or changes with utility companies | Revise Final Work Plan and resubmit within 30 days
[5 empty] | Notify utilities and RUPC of acceptance of Final Relocation Plan |  |  | ROW is not notified of final work plan acceptance.
|  |  |  | Enters U03 "actual" start date for project | Enters U04 completion date in PSS/MW
U05 (coordination) |  |  | Reviews, monitors, and reports on event status as part of ROW production oversight | Monitors ROW activities and establishes priority acquisition parcel for NEW needed easements | Updates PSS/MW with parcels involved in relocation and marks those needing Advanced ROW Purchase |  |  | Parcel acquisition priority list for right of way
|  |  | Coordinate production needs between ROW sections | Coordinate with ROW Design/Acquisition to ensure LEB Clearance or conduct individual clearances
|  |  | Oversight of intra bureau communication | Coordinate with ROW Design to ensure FHWA concurrence with advanced acquisition
Monitor progress through appraisal & acquisition of parcels for utility relocation or easement
|  |  |  | Review submitted material for eligibility and completeness | Reviews requests for reimbursement and requests additional information from Util Co | Prepares Reimbursement Agreement Request/Existing Easements/Data Inquiry Sheet/Final Estimate
[5 empty] | Coordinate sharing of information between utility companies. Coordinate with EOT on relocation permits. Reminder and followup emails/calls are common due to lack of Utility company response to the U04 notification. Attending PMT and PIM meetings. |  |  | New Note
R02/R03/R04 |  | 390 | Monitors ROW bureau progress with Utility Program coordinators
U06 Notice to Proceed to utility companies when Work Plan is approved, agreement is executed, permit is issued, ROW is acquired |  | 30 | Reviews, monitors, and reports on event status as part of ROW production oversight | Facilitates information share regarding acquisition of parcel or easement for relocation | Notifies utilities when ROW is in possession or possession date is identified | Submit utility accommodation permit and approved work plan to District EOT
[5 empty] | Monitors process of work completion | Secures materials and completes the relocation |  | Reminder and followup emails/calls are common to track progress of relocation. Also track right of way acquisitions and letting date changes.
[5 empty] | Enters U06 actual start/finish dates in PSS/MW |  |  | It should be noted that the utility companies need to order materials well in advance of the U06 to ensure delivery by the time they need to relocate
U07 Utility Bid Attachment submitted to Contracts at Plan-Turn-In to include in bid package with status of relocations at time of PTI; gives contractor useful information to bid accordingly |  | 30 | Reviews, monitors, and reports on event status as part of ROW production oversight |  | Develops Utility Bid Attachment listing STATUS of each utility in the project area (impacted or not) with all relocation plans and schedules so contractors can account for it in bid | Provide relocation start and completion dates |  | It should be noted that the Bid Attachment should include a list of remain utility conflicts in the project area as part of the STATUS for each company that has remaining conflicts that need resolved prior to or during construction Reminder and follow up emails/calls are common to request relocation dates, track progress of relocation, confirm if right of way is still not acquired, and letting date changes. Post letting utility coordination continues until construction has been completed for some districts.
|  |  | Target Review oversight for ROW certification | Ensure clearances are correct for ROW certification | Utility Bid Attachment to Contracts for bidding documents
Enters U07 actual start/finish dates in PSS/MW
[5 empty] | Post letting utility coordination: Working with RCE, Contractor, Utility Company, and Consultants to resolve any existing conflicts/relocations that have not yet been completed or came up with project changes. |  |  | New Note: this can take an excessive amount of time in the DUC schedule due to the timeframe needed to complete the task and keep the project on track.
U05 Utility Reimbursement Agreement for utility facility relocations from private easement; includes negotiation, payment and acquisition of real estate interest for area within new public rights of way |  |  | Reviews, monitors, and reports on event status as part of ROW production oversight | Verify eligible for reimbursement by reviewing utility companies existing easements; requests other easement information if not supported | Reviews reimbursement request for conformity to Approved Work Plan and forwards to Regional Utility Coordinator | Provides existing easements, approved work plan and detailed relocation estimate to DUC | Provides guidance on reimbursement eligibility | Not a current practice for the DUC's
|  |  | Coordinate production needs between ROW sections | Review preliminary estimate and request further detail if not supported | Reviews (with Construction Engineer if applicable) and provides initial approval of relocation estimate | Provides preliminary estimate for easement or relocation work | Provides guidance on estimate appropriateness | Not a current practice for the DUC's
|  |  | Participate and manage Production reporting for ROW Bureau | Verify utility consultant use and request additional information if needed | Completes a review of the preliminary estimate of verifies Work Plan is consistent with Approved Work Plan | Orders materials (ideally) | Provides guidance on consultant use as necessary | Not a current practice for the DUC's
|  |  | Liaison between Bureau/TDD/District for project related issues | Writes the proposed relocation agreement for draft review; WorkDay contract number assignment | Reviews agreement for compliance with Approved Relocation Work Plan |  | Utilities program admin reviews and approves agreement and estimate as appropriate
|  |  |  | Requests Pre-Audit when needed and monitors status | Assists with communication between RUPC and utility company as needed
|  |  |  | Reconciles all changes and makes final edits to proposed agreement; sends final proposed agreement to utility company for review and execution; monitors status |  |  | Provides guidance on modifications to agreement language and offers suggested modifications as needed; recommends review by General Counsel as needed
|  |  |  | Negotiates the agreement with utility company as ROW Agent - main point of contact with utility company |  | Reviews proposed agreement and request revisions as needed/often times involves their legal staff in negotiation | Provides guidance on modifications to agreement language and offers suggested modifications as needed; recommends review by General Counsel as needed
|  |  |  | Receives the partially executed agreement from Utility Company and begins approval process for the DOT |  | Secures materials for relocation | Utilities program admin reviews and approves payment
|  |  |  | Prepares Staff Action for reimbursement authority and monitors status; requests signature from Bureau Director & UPA |  | Solicits bid for relocation and submits to RUPC for concurrence (if applicable) | Attests Bureau Director's signature on agreement
|  |  |  | Returns fully executed agreement to Utility Company and others as appropriate; finalizes and submits contract in Workday |  | Receives executed agreement
|  |  |  | Reviews Utility Company's bids received and their recommendation to award contract for reasonableness; informs Utility Company of acceptance/rejection (if applicable) |  | Schedules relocation work with contractor (or company forces) | Provides guidance on bid reviews as necessary
|  |  |  | Reviews billing for compliance with agreement and estimate; requests approval from Utility Program Administrator to pay invoice; pays 90% of invoice upon approval | Monitors process of work completion | Completes relocation and provides invoice with proof of payment and itemized costs to RUPC | Reviews and approves payment | Not a current practice for the DUC's
|  |  |  | Reviews additional costs and determines if an addendum to the agreement will be needed; if so writes proposed addendum for draft review and sends for review | Reviews addendum for compliance with Approved Relocation Work Plan | Notifies RUPC if project costs will exceed 125% of agreement costs and provides support for increased costs | Reviews draft addendum/estimate as appropriate | Some DUC's do review the addendum for compliance but this isnt a standardized process.
|  |  |  | Negotiates the addendum with utility company as ROW Agent - main point of contact with utility company | Completes a review and approves final relocation reimbursement cost and is consistent with Approved Work Plan | Reviews proposed addendum and request revisions as needed/often times involves their legal staff in negotiation | Provides guidance on modifications to addendum language and offers suggested modifications as needed; recommends review by General Counsel as needed | DUC's don’t approve the final reimbursement costs.
Receives the partially executed addendum from Utility Company and begins approval process for the DOT
|  |  |  | Prepares Staff Action for addendum and monitors status; requests signature from Bureau Director & UPA |  |  | Attests Bureau Director's signature on addendum
|  |  |  | Returns fully executed addendum to Utility Company and others as appropriate; modifies contract in and submits in Workday |  | Receives executed addendum
|  |  |  | Requests Certificate of Completion from Utility Company if not already received | Receives Certificate of Completion from Utility Company and approves/rejects; returns COC to Utility Company and RUPC | Provides Certificate of Completion to DUC
Disclaimer of Interest (release of easement interest from utility company); compiles list of parcels to be released and requests completion of document by Title & Closing
|  |  |  | Receives/reviews draft DIR from Title & Closing; sends document to Utility Company for execution; negotiates any changes with Utility Company |  | Reviews/executes DIR and returns to RUPC | Provides guidance on modifications to DIR language and offers suggested modifications as needed; recommends review by General Counsel as needed
Requests recording of fully executed DIR from Title & Closing; returns fully executed DIR to Utility Company
Requests Final Audit from Finance and monitors status
|  |  |  | Reviews Final Audit and makes final payment (modifies contract in Workday if necessary and makes final payment including release of retainage); if overpayment prepares invoice for Utility Company and requests repayment |  | Accepts final payment/makes repayment | Provides guidance on final payment/repayment as necessary
Enters U05 actual start/finish dates in PSS/MW
Closeout file to ERMS
U00
U01
U02
U03
U04
U07
U06
U05
Related events like the D2, D5, R01,etc.
Red Text | Areas where it is anticipated that PPMS/MW can help automate to a degree