**Utility notification process under current IAC**

Schedule task code: U02

relevant paragraph: 115.26(2)

plans sent: D02/field exam ("geographical limits")

response requested: existing facility locations/maps

response deadline: 90 days after notification sent

Schedule task code: U03

relevant paragraph: 115.27(1)

plans sent: D05 and R01 ("first plan")

response requested: relocation preliminary work plan

response deadline: 90 days after notification sent

Schedule task code: U04

relevant paragraph: 115.28(1)

plans sent: D05 and R01 ("second plan", latest version after final public information meeting)

response requested: relocation final work plan

response deadline: 60 days after notification sent

earliest possible completion: 150 days after R01

**Utility notification process under proposed IAC update**

Schedule task code: U01

relevant paragraph: 115.20(2)

plans sent: project concept ("geographical limits")

response requested: existing facility locations and maps/existing easement locations

response deadline: 30 days after notification sent

Schedule task code: U02

relevant paragraph: 115.21(2)

plans sent: D02/field exam ("preliminary plan")

response requested: confirmation of accuracy of facility locations depicted on plans/description of potential conflicts/recommended changes to roadway plans/identification of new easement needs

response deadline: 30 days after notification sent

Schedule task code: U03

relevant paragraph: 115.22(1)

plans sent: D05 and R01 ("semifinal plan")

response requested: relocation work plan

response deadline: 90 days after notification sent

earliest possible completion: 90 days after R01